## Dashboard
RELEASE 3 - MARKET TRIALS - DAILY DASHBOARD
Date: |  | 2018-09-25
MT Progress Summary
1) Market Trials continues in week 2 with activity seen from multiple parties 2) Commodity fix is in progress and due to run today successfully. 3) Incorrect Read data is being sent to impacted customers today.
File Summary
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Inbound | 129 | 114 | 0 | 0 | 0 | 0 | 6 | 1 | 7 | 0 | 1 | 0 | 0
Outbound | 232 | 48 | 29 | 7 | 7 | 8 | 37 | 9 | 14 | 8 | 8 | 25 | 32
Defects
Defect ID | Linked SD Plus | 1: Summary; 8: Status; 10: Target Date; 12: Priority
234 | 899187 | 1: MID file not rejected; 8: Closed; 10: 2018-09-14; 12: P3
237 | 899569 | 1: Market Flow channels closed; 8: Closed; 10: 2018-09-13; 12: P2
236 | 899331 | 1: SFR response file failed at AMT; 8: Awaiting Closure; 10: 2018-09-14; 12: P3
N/A | 901489 | 1: MARKET TRIALS - URS "N" Tolerance flag accepted; 8: Awaiting Closure; 10: 2018-09-24; 12: P3
| 901506 | 1: Read rejected for unexpected reason; 8: Fix In Progress; 10: 2018-09-25; 12: P3
| 901733 | 1: Invoicing Files not flowing out of IX; 8: Closed; 10: 2018-09-24; 12: P3
| 902786 | 1: Read rejected for unexpected reason; 8: Fix In Progress; 10: 2018-09-25; 12: P3
Queries
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Open | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closed | 30 | 19 | 2 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 1 | 0 | 0
Total | 31 | 19 | 2 | 0 | 0 | 1 | 6 | 0 | 2 | 0 | 1 | 0 | 0