## Dashboard
RELEASE 3 - TRACK 2 - MARKET TRIALS - DAILY DASHBOARD
Date: |  | 2018-12-04
MT Progress Summary
1) All Invoices have been issued, we are awaiting responses 2) Progress and completion forms have been issued to respond with updates or completion confirmation by Friday
File Summary |  |  |  | User | Occurrence
| Total |  | CMS Log in | 0 | 0
Inbound | 13 |  | DES Log in | 0 | 0
Outbound | 183 |  | Portal Log in | 0 | 0
Defects
Defect ID | Linked SD Plus | Summary | Status | Target Date | Priority
Queries
Total
Open | 1
Closed | 36
Total | 37
Open Queries
Query ID | Summary

## Healthcheck
Release 3 - Market Trials - Health check
2018-12-04
Component | RAG | Comments
` | g
IX | g
EFT | g
Basis | g
Control M | g
AMT/PO | g
ISU | g
BW | g
IDAM* | N/A | Not using for MT Release 3
PORTAL | g
SD Plus | g
CMS | g
Gemini* | N/A | Not using for MT Release 3

## File Breakdown
Inbound |  | Outbound
File Type | Files | File Type | Files
CNF | 1 | CFR | 1
DCI | 2 | CMA | 2
NOM | 1 | COI | 4
UMR | 4 | COM | 4
PCD | 5 | DDU | 14
|  | EWS | 7
|  | FRJ | 3
|  | GSR | 1
|  | INV | 58
|  | LPA | 5
|  | LPG | 1
|  | MBR | 10
|  | MDR | 2
|  | NMR | 2
|  | SIF | 28
|  | SIR | 28
|  | URS | 6
|  | ZCS | 1
|  | ASP | 4
|  | MIF | 2