## Dashboard
RELEASE 3 - TRACK 2 - MARKET TRIALS - DAILY DASHBOARD
Date: |  | 2018-11-22
MT Progress Summary
1. Commodity invoices are in validation 2. CMS and Portal are now available for testing 3. 4.
File Summary |  |  |  | User | Occurrence
| Total |  | CMS Log in | 0 | 0
Inbound | 4 |  | Portal/DES Log in | 0 | 0
Outbound | 43
Defects
Defect ID | Linked SD Plus | Summary | Status | Target Date | Priority
Queries
Total
Open | 1
Closed | 19
Total | 20
Open Queries - General
Query ID | Summary

## Healthcheck
Release 3 - Market Trials - Health check
2018-11-22
Component | RAG | Comments
` | g
IX | g
EFT | g
Basis | g
Control M | g
AMT/PO | g
ISU | g
BW | g
IDAM* | N/A | Not using for MT Release 3
PORTAL | g
SD Plus | g
CMS | g
Gemini* | N/A | Not using for MT Release 3

## File Breakdown
Inbound |  | Outbound
File Type | Files | File Type | Files
UMR | 2 | CMA | 2
DCI | 2 | DDU | 1
|  | EWS | 1
|  | FRJ | 2
|  | INV | 9
|  | LPG | 1
|  | MBR | 1
|  | SIF | 10
|  | SIR | 10
|  | URS | 5
|  | ZCS | 1