## Dashboard
RELEASE 3 - TRACK 2 - MARKET TRIALS - DAILY DASHBOARD
Date: |  | 2018-11-29
MT Progress Summary
1) Amendments invoice is being validated currently will be issued to industry by COP Friday. 2) Meter Assets is being validated internally and is being issued by COP Friday
File Summary |  |  |  | User | Occurrence
| Total |  | CMS Log in | 0 | 0
Inbound | 8 |  | DES Log in | 0 | 0
Outbound | 132 |  | Portal Log in | 0 | 0
Defects
Defect ID | Linked SD Plus | Summary | Status | Target Date | Priority
Queries
Total
Open | 3
Closed | 23
Total | 26
Open Queries
Query ID | Summary
111 | Is the company name being used on the Cadent invoices correct i.e. NG GAS DISTRIBUTION LTD OPS given that NG distribution no longer exists?

## Healthcheck
Release 3 - Market Trials - Health check
2018-11-29
Component | RAG | Comments
` | g
IX | g
EFT | g
Basis | g
Control M | g
AMT/PO | g
ISU | g
BW | g
IDAM* | N/A | Not using for MT Release 3
PORTAL | g
SD Plus | g
CMS | g
Gemini* | N/A | Not using for MT Release 3

## File Breakdown
Inbound |  | Outbound
File Type | Files | File Type | Files
CNF | 1 | CFR | 1
DCI | 2 | CMA | 2
NOM | 1 | COI | 4
UMR | 4 | COM | 4
|  | DDU | 8
|  | EWS | 7
|  | FRJ | 3
|  | GSR | 1
|  | INV | 33
|  | LPA | 5
|  | LPG | 1
|  | MBR | 10
|  | MDR | 2
|  | NMR | 2
|  | SIF | 21
|  | SIR | 21
|  | URS | 6
|  | ZCS | 1