## Slide 1: XRN5110 – November 20 Implementation Approach

## Slide 2: XRN5110 - Nov 20 Scope
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
  XRN 4801 - Additional Information in DES
  XRN 4871B - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
XRN5110 November 20 Release consists of 6 changes. Implementation is planned to start on 06 November and finish on the 07 November 2020

## Slide 3: XRN5110 Nov 20 High Level Implementation Timeline
The implementation of the 6 changes consists of code transports for Business Warehouse (BW), Process Orchestration (PO), Data Enquiry Service (DES), SAP Utilities (ISU systems) and batch configuration Control M
The Enhanced File Transfer (EFT) channels will need to be closed in order to implement the PO and IS-U changes as part of XRN4931, XRN4897 and XRN4899
06
/
11
/
2020
07
/
11
/
2020
06
/
11
/
2020
23
:
59
:
59
Final Outbound files Sent
07
/
11
/
2020
-
07
/
11
/
2020
05
:
00
:
00
-
06
:
00
:
00
Code Transports
07
/
11
/
2020
-
07
/
11
/
2020
06
:
00
:
00
-
07
:
00
:
00
QA
07
/
11
/
2020
07
:
00
:
01
Open EFT channels
06
/
11
/
2020
23
:
00
:
00
Final Inbound Files processed
07
/
11
/
2020
00
:
00
:
01
Stop
EFT outbound channels
06
/
11
/
2020
23
:
00
:
01
Stop
inbound EFT channels
07
/
11
/
2020
-
07
/
11
/
2020
:
00
:
00
-
16
:
00
:
00
15
07
/
11
/
2020
-
07
/
11
/
2020
:
00
:
00
-
17
:
00
:
00
BW & DES Transports
16
BW & DES QA
Code Transports
QA Checks
Channel Close & Open

## Slide 4: XRN5110 Nov 20 File Format Transition plan
To incorporate the mapping rules and processing logic of the files, the Enhanced File Transfer channels will need to be closed for XRN4931, XRN4897 and XRN4899
  CNF, CNC, GEA, CSS, WAO, SNO - Changes in processing logic
  MSO, CTR, CFR, URS, SFR – Changes in PO mapping
The files below will be processed as per the standard times, all received files will be processed before we close the channels
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59, prior to closing the channels
There are no changes to the file formats, so if any file arrives while the channels are closed they will be processed after the implementation
Change ID | Last inbound (Time = File Processing) | Last Outbound (Time = File Processing) | First Inbound (Time = File Processing) | First outbound processed (Time = File Processing)
XRN4931XRN4897XRN4899 | 06/11/2020 CNC - 23:00:00 CNF - 23:00:00 GEA - 23:00:00 CSS - 23:00:00 WAO - 23:00:00 SNO - 23:00:00 | 06/11/2020 MSO, CTR, CFR, URS, SFR will be processed as per normal Business As Usual schedule. Last processing at 23.59.59 | 07/11/2020 CNF - BAU time CNC - BAU time GEA - BAU time CSS - BAU time WAO - BAU time SNO - BAU time | 07/11/2020 MSO, CTR, CFR, URS, SFR will be processed as per normal Business As Usual schedule.

## Slide 5: XRN5110 Nov 20 Code Deployment timeline
Deployment window to be followed according to the below table
No | System | Available Window | Code Deployment Date / Time
01 | SAP Utilities IS-U | 5 am - 7 am | 07-Nov-2020 / 5 am - 7 am
02 | Business Warehouse/Business Object | 3 pm - 5 pm | 07-Nov-2020 / 3 pm - 5 pm (After IS-U Transport)
03 | Process Orchestration | 5 am - 7 am | 07-Nov-2020 / 5 am - 7 am
04 | Control-M | 5 am - 7 am | 07-Nov-2020 / 5 am - 7 am
05 | Data Enquiry Service | 3 pm - 5 pm | 07-Nov-2020 / 3 pm - 5 pm
* Note: Exact Times to be Confirmed with Tech Operations as part of Detailed Implementation Plan

## Slide 6: Additional Points-Data Cleansing in PIS
Part1-1st week post go live-run simulation
Part2-2nd week post go live- Identify the volume
Part3- 3rd week Agree with Tech Ops on batch window
Part4- Schedule batch for cleansing
Part5- Complete the cleansing activity
XRN4897/XRN4899 data cleansing plan of personal data of full production data set:
This will be a phased approach during the 3 month post implementation support period to accommodate the batch window processes. Information from performance testing will be used to identify the optimum processing capacity
Portfolio files (EWS, IDL and EDL sent to networks) will be updated with additional entries to notify the industry of job cleansing activities
This approach will reduce the risk of any impact on the daily batch schedule. Depending on the actual volume of cleansing the batch window will be agreed with tech ops