## Key
Change Lifecycle Status Key | Project Status
A1 - ICAF - Awaiting Capture Assignment | 1. Start-Up (Progressing through change governance)
A2 - CP proposed for ChMC
A3 - CP within initial view
A4 - CP rejected by ChMC
A5 - CP in capture with DSG
A5a - Solution Development
A5b - Undergoing Solution Impact Assessment
A5c - Solution Impact Assessment Review
A6 - CP in solution consultation
A7 - CP awaiting ChMC solution approval
A8 - CP high level solution approved at ChMC
A9 - Internal change progressing through capture
A10 - ICAF - Capture complete, awaiting CIO PM assignment
B1 - Start Up In Progress (Awaiting PAT/RACI)
B2 - Awaiting ME/Data Office/MR HLE quote
B3 - ASR/PAC HLE awaiting customer approval
B4 - EQR In progress
B5 - EQR awaiting ChMC approval
C1 - Delivery Business Case/BER in progress
C2 - Delivery Business Case awaiting IRC/XEC/Board Approval
C3 - BER Awaiting ChMC approval
Y1 - ROM in progress
Y2 - ROM completed
D1 - Change in delivery | 2. Change sanctioned/approved and in project delivery
F1 - CCR/Closedown document in progress | 3. Change delivered, awaiting closure approval/sign-off
F2 - CCR awaiting ChMC approval
X1 - Xoserve propose change not required | 4. Change proposed to be rejected by Xoserve (awaiting closure approval)
X2 - Xoserve require ChMC Sponsorship

## Change Register
XRN | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Origination Date | Xoserve Project Manager | Xoserve Platform Owner | UK Link Release | Customer Change Team Lead | Current Delivery Forecast Implementation Date | Actual Implementation Date | Shipper Impact | Network Impact | IGT Impact | NTS Transmission Impact | Primary Impacted DSC Service Area
4550 | (DCEXIT) - Gemini Re-platform | CP | LIVE | D1 - Change in delivery | 2017-12-04 | Manisha Bhardwaj | Gemini & Integration | Gemini Re-Platform | No Customer Change Team Lead | 2020-07-05 | 2020-07-05 | FALSE | FALSE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services
4627 | (CSSC) - Consequential Central Switching Services | CP | LIVE | D1 - Change in delivery | 2018-03-09 | Smitha Pichrikat | CSS | CSSC Programme | Emma Lyndon | 2022-03-30 | 2022-03-30 | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4645A | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP | LIVE | B3 - ASR/PAC HLE awaiting customer approval | 2018-04-03 | Andy Kirk | UK Link |  | James Barlow | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices
4695 | (UIG) - Investigating causes and contributors to levels and volatility of Unidentified Gas | CP | LIVE | F1 - CCR/Closedown document in progress | 2018-06-05 | Fiona Cottam | Other | UIG Task Force | No Customer Change Team Lead | 2019-03-30 | 2019-03-30 | TRUE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC
4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | CP | LIVE | D1 - Change in delivery | 2018-07-16 | Leanne Jackson | Data - Customer Services |  | Simon Harris | 2020-09-30 | 2020-09-30 | TRUE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
4738 | Shipper portfolio update of proposed Formula Year AQ/SOQ | CP | LIVE | F1 - CCR/Closedown document in progress | 2018-08-14 | Leanne Jackson | Data - Customer Services |  | Jane Goodes | 2020-03-31 | 2020-03-31 | TRUE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request
4772 | (JUN20) - Composite Weather Variable (CWV) Improvements | CP | LIVE | D1 - Change in delivery | 2018-09-26 | Surfaraz Tambe | UK Link | June2020 | David Addison | 2020-11-27 | 2020-11-27 | TRUE | TRUE | FALSE | FALSE | Service Area 15: Demand Estimation
4780b | (JUN20) - (Part B) Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | CP | LIVE | D1 - Change in delivery | No Date | Surfaraz Tambe | UK Link | June2020 | No Customer Change Team Lead | 2020-11-27 | 2020-11-27 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
4780c | (Part C) Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | CP | LIVE | B7 - Awaiting assignment to release | No Date | Emma Lyndon | CSS | Nov2020 | Simon Harris | 2020-11-07 | 2020-11-07 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
4801 | (Nov20) - Additional information to be made viewable on DES | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2018-10-30 | Ed Healy | UK Link | Nov2020 | Simon Harris | 2020-11-07 | 2020-11-07 | TRUE | FALSE | FALSE | FALSE | Service Area 22: Specific Services
4810 | Chat Bot Automated Gemini Assistant | CP | LIVE | D1 - Change in delivery | 2018-11-14 | Hannah Reddy | Gemini & Integration |  | No Customer Change Team Lead | No Date | No Date | TRUE | FALSE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services
4850 | (JUN20) - Notification of Customer Contact Details to Transporters | CP | LIVE | D1 - Change in delivery | 2019-01-30 | Surfaraz Tambe | UK Link | June2020 | Ellie Rogers | 2020-11-27 | 2020-11-27 | FALSE | TRUE | TRUE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence
4865 | (JUN20) - Amendment to Treatment and Reporting of CYCL Reads | CP | LIVE | D1 - Change in delivery | 2019-02-08 | Surfaraz Tambe | UK Link | Jun2020 | Simon Harris | 2020-11-27 | 2020-11-27 | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4869 | (DCExit) - DC ExitProgramme | CP | LIVE | D1 - Change in delivery | 2019-02-08 | Manisha Bhardwaj | Gemini & Integration | Gemini Re-Platform | Alison Cross | 2020-10-01 | 2020-10-01 | TRUE | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services
4871b | (Nov-20) - (Part B) Modification 0665 – Changes to Ratchet Regime | CP | LIVE | C1 - Delivery Business Case/BER in progress | No Date | Ed Healy | UK Link | Nov2020 | No Customer Change Team Lead | 2020-11-07 | 2020-11-07 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
4888 | (JUN20) - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | CP | LIVE | D1 - Change in delivery | 2019-03-05 | Surfaraz Tambe | UK Link | June2020 | Paul Orsler | 2020-11-27 | 2020-11-27 | TRUE | TRUE | TRUE | FALSE | Service Area 2: Provide Query Management
4896 | Failure to Supply Gas System and Template Amendment | CP | LIVE | D1 - Change in delivery | 2019-03-15 | Simon Harris | IS Ops |  | Simon Harris | 2020-06-30 | 2020-06-30 | TRUE | TRUE | FALSE | FALSE | Service Area 4: Interruption Auction Services in accordance with UNC
4897 | (Nov20) - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-03-18 | Ed Healey | UK Link | Nov2020 | James Barlow | 2020-11-07 | 2020-11-07 | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4899 | (Nov20) - Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-03-19 | Ed Healey | UK Link | Nov2020 | James Barlow | 2020-11-07 | 2020-11-07 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
4914 | MOD 0651- Retrospective Data Update Provisions inc POC | CP | LIVE | D1 - Change in delivery | 2019-04-01 | Tom Lineham | UK Link |  | Paul Orsler | No Date | No Date | TRUE | TRUE | TRUE | FALSE | Service Area 1: Manage Supply Point Registration
4930 | (JUN20) - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | CP | LIVE | D1 - Change in delivery | 2019-04-15 | Surfaraz Tambe | UK Link | June2020 | Simon Harris | 2020-11-27 | 2020-11-27 | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4931 | (Nov-20) - SUBMISSION OF SPACE IN MANDATORY DATA ON MULTIPLE SPA FILES | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-04-16 | Ed Healey | UK Link | Nov2020 | Simon Harris | 2020-11-07 | 2020-11-07 | TRUE | FALSE | FALSE | FALSE | No DSC Service Area
4932 | (JUN20) - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | CP | LIVE | D1 - Change in delivery | 2019-04-16 | Surfraz Tambe | UK Link | June2020 | Simon Harris | 2020-11-27 | 2020-11-27 | TRUE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
4941 | Auto updates to meter read frequency (MOD0692) | CP | LIVE | B7 - Awaiting assignment to release | 2019-05-07 | No Project Manager | UK Link | Nov2020 | Simon Harris | 2020-11-07 | 2020-11-07 | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | CP | LIVE | Capture | 2019-07-03 | No Project Manager | UK Link |  | Jane Goodes | No Date | No Date | TRUE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
4989A | Online end to End Credit Interest process - Defect 1063 | CP | LIVE | D1 - Change in delivery | 2019-07-29 | Julie Bretherton | UK Link | MiR Drop 7 | Simon Harris | 2020-07-04 | 2020-07-04 | TRUE | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
4989B | Online End to End Credit Interest - IIS File Format Amendment | CP | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 2020-08-25 | No Project Manager | Operations |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | CP | LIVE | Capture | 2019-07-29 | No Project Manager | UK Link |  | James Barlow | No Date | No Date | TRUE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
4992 | Modification 0687 - Creation of new charge to recover Last Resort Supply Payments | CP | LIVE | B7 - Awaiting assignment to release | 2019-07-30 | Richard Hadfield | UK Link | Nov2020 | Ellie Rogers | 2019-11-07 | 2019-11-07 | TRUE | TRUE | TRUE | FALSE | Service Area 1: Manage Supply Point Registration
4996 | (JUN20) - Jun-20 Release Delivery | CP | LIVE | F1 - CCR/Closedown document in progress | 2019-07-31 | Surfaraz Tambe | UK Link | June2020 | Simon Harris | 2020-11-27 | 2020-11-27 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5004 | Golden Bullet report | CP | LIVE | D1 - Change in delivery | 2019-08-19 | Andy Kirk | Data - Customer Services |  | Matt Smith | 2020-08-28 | 2020-08-28 | FALSE | TRUE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence
5007 | Enhancement to reconciliation process where prevailing volume is zero | CP | LIVE | Capture | 2019-09-02 | No Project Manager | UK Link |  | James Barlow | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5014 | (Nov-20) - Facilitating HyDeploy Live Trials | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-09-17 | Ed Healy | UK Link | Nov2020 | Steve Pownall | 2020-11-07 | 2020-11-07 | TRUE | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5036 | (MiR7) - Updates to must read process | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-10-31 | Julie Bretherton | UK Link | MiR Drop 7 | Emma Smith | 2020-07-04 | 2020-07-04 | TRUE | TRUE | TRUE | FALSE | Service Area 1: Manage Supply Point Registration
5038 | Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691) | CP | LIVE | Capture | 2019-10-31 | No Project Manager | UK Link |  | Ellie Rogers | 2020-03-12 | 2020-03-12 | TRUE | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
5065 | (MiR7) - Addition of Email Address to DES Last Accessed Report | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2019-12-16 | Julie Bretherton | UK Link | MiR Drop 7 | Simon Harris | 2020-07-04 | 2020-07-04 | TRUE | TRUE | TRUE | FALSE | Service Area 18: Provision of User Reports and Information
5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | CP | LIVE | Capture | 2019-12-27 | No Project Manager | UK Link |  | James Barlow | No Date | No Date | TRUE | TRUE | TRUE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5080 | Failure to Supply Gas (FSG/GSOP1) – System Changes | CP | LIVE | Capture | 2020-01-14 | No Project Manager | Customer |  | Steve Pownall | 2020-10-31 | 2020-10-31 | TRUE | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
5091 | Deferral of creation of Class change reads at transfer of ownership | CP | LIVE | Capture | 2020-01-27 | No Project Manager | UK Link |  | James Barlow | No Date | No Date | TRUE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5092 | iConversion Phase 2 | CP | LIVE | F1 - CCR/Closedown document in progress | 2020-01-29 | Rachel Addison | Gemini & Integration |  | Rachel Addison | 2020-05-14 | 2020-05-14 | FALSE | FALSE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services
5093 | Update of AUG Table to reflect new EUC bands | CP | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 2020-01-29 | No Project Manager | UK Link |  | Ellie Rogers | No Date | No Date | TRUE | FALSE | FALSE | FALSE | Service Area 15: Demand Estimation
5110 | (Nov-20) - November 20 Release | CP | LIVE | D1 - Change in delivery | 2020-02-05 | Ed Healey | UK Link | Nov2020 | No Customer Change Team Lead | 2020-11-07 | 2020-11-07 | TRUE | TRUE | TRUE | FALSE | No DSC Service Area
5118 | (MiR8) Change to how ‘Actual MR date’ field is populated in UK Link | CR | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) |  | Bali Bahia | UK Link | MiR Drop 8 | Emma Smith | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Internal
5120A | MAP to UKL Monthly Comparison Service | CP | LIVE | A10 - Capture complete, awaiting Stage Gate A Approval | 2020-02-26 | No Project Manager | Data - Customer Services |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information
5120B | UK Link Comparison Services | CP | LIVE | Capture | 2020-02-19 | No Project Manager |  |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information
5121 | Supplier Portfolio Service | CP | LIVE | Capture | 2020-02-27 | No Project Manager | Other |  | Sue Wagstaff | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 14: Shipper Agreed Reads
5122 | Gemini System Enhancements - Delivery | CP | LIVE | C1 - Delivery Business Case/BER in progress | 2020-02-28 | Hannah Reddy | Gemini & Integration |  | Hannah Reddy | No Date | No Date | TRUE | TRUE | FALSE | TRUE | Service Area 20: UK Link Gemini System Services
5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | CP | LIVE | Capture | 2020-03-10 | No Project Manager | UK Link |  | Jaimee LeResche | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | CP | LIVE | Capture | 2020-03-24 | No Project Manager | UK Link |  | Charan Singh | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | CP | LIVE | Capture | 2020-03-24 | No Project Manager | UK Link |  | Steve Pownall | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | CP | LIVE | Capture | 2020-03-30 | No Project Manager | UK Link |  | Megan Troth | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC
5145 | DSC Service Description Table cosmetic change to Service Line Table v11 | CP | LIVE | D1 - Change in delivery | 2020-03-30 | Angela Clarke | Other |  | No Customer Change Team Lead | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5146 | Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | CP | LIVE | Capture | 2020-03-30 | No Project Manager | IS Ops |  | Ellie Rogers | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 11: NExA Supply Meter Points
5147 | Optimising the Must Read process for IGT Customers | CP | LIVE | Capture | 2020-03-30 | No Project Manager | UK Link |  | Paul Orsler | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 22: Specific Services
5152 | (MiR7) - Minor Release drop 7 Parent | CP | LIVE | F2 - CCR awaiting ChMC approval | 2020-04-02 | Julie Bretherton | UK Link | MiR Drop 7 | Julie Bretherton | 2020-07-04 | 2020-07-04 | FALSE | FALSE | FALSE | FALSE | Internal
5153 | iConversion Phase 2 non NG interfaces (Part 2 Funded separately) | CP | LIVE | D1 - Change in delivery | 2020-04-02 | Nicola Patmore | Gemini & Integration |  | No Customer Change Team Lead | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Internal
5164 | CSEP Data Assurance – Performance Monitoring Capability | CP | LIVE | D1 - Change in delivery | 2020-04-30 | Charlie Haley | Data - Strategy |  | No Customer Change Team Lead | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5167 | Report Product Class 4 Read Performance (MOD 672) | CP | LIVE | D1 - Change in delivery | 2020-05-05 | No Project Manager | Data - Strategy |  | James Rigby | 2020-08-28 | 2020-08-28 | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5169 | MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19 | CP | LIVE | Capture | 2020-05-05 | No Project Manager | UK Link |  | David Addison | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5170 | MOD0723 (Urgent): Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | CP | LIVE | Capture | 43956 | No Project Manager | UK Link |  | David Addison | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5171 | MOD0724 (Urgent): Amendment to Ratchet charges during COVID-19 period | CP | LIVE | Capture | 2020-05-05 | No Project Manager | UK Link |  | David Addison | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5172 | Urgent Mod - Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | CP | LIVE | Capture | 2020-05-07 | No Project Manager | Other |  | David Addison | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5174 | (MiR8) Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | CR | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 2020-05-13 | Bali Bahia | UK Link | MiR Drop 8 | Emma Smith | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Internal
5180 | Inner Tolerance Validation for replacement reads and read insertions | CP | LIVE | Capture | 2020-05-19 | No Project Manager | IS Ops |  | James Barlow | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5181 | (MiR8) Acceptance of Consumption Adjustment where meter removed after meter point set to Dead | CP | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 2020-05-18 | Bali Bahia | UK Link | MiR Drop 8 | Emma Smith | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity
5183 | Access to Daily Biomethane Injections | CP | LIVE | Unassigned Customer Change Backlog | 2020-05-28 | No Project Manager | Data - Customer Services |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request
5186 | Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | CP | LIVE | Capture | 2020-06-01 | No Project Manager | UK Link |  | Ellie Rogers | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 11: NExA Supply Meter Points
5187 | Modification 0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | CP | LIVE | Capture | 2020-06-01 | No Project Manager | UK Link |  | Ellie Rogers | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 11: NExA Supply Meter Points
5188 | Interim Data Loads of MAP Id into UK Link | CP | LIVE | Capture | 2020-06-04 | No Project Manager | UK Link |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration
5192 | CMS Reference Number in Amendment Invoice Supporting Data | CP | LIVE | Unassigned Customer Change Backlog | 2020-06-19 | No Project Manager | UK Link |  | Emma Smith | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices
5195 | Ceased Responsibility Date Following Shipper Withdrawal (IDL) | CP | LIVE | Capture | 2020-06-25 | No Project Manager | UK Link |  | Jane Goodes | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 21: Data Flows and Services to Network Operators
5196 | Address Amendments Validation | CP | LIVE | Capture | 2020-06-26 | No Project Manager | UK Link |  | Jane Goodes | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 21: Data Flows and Services to Network Operators
5197 | QMP File Validation in CMS – Current Address field | CP | LIVE | Capture | 2020-06-26 | No Project Manager | UK Link |  | Jane Goodes | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 21: Data Flows and Services to Network Operators
5199 | Amendments to V12 of the SDT Service Description Table | CP | LIVE | D1 - Change in delivery | 2020-06-26 | No Project Manager | Other |  | No Customer Change Team Lead | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 21: Data Flows and Services to Network Operators
5200 | Shipper Pack Transition to Data Discovery Platform | CP | LIVE | Capture | 2020-06-29 | No Project Manager | Data - Strategy |  | Rachel Taggart | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information
5203 | Perspective Supply Metering Point AQ and EUC | CP | LIVE | Capture | 2020-07-03 | No Project Manager | Data - Customer Services |  | Jane Goodes | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5206 | TPI/PCW Access | CP | LIVE | Capture | 2020-07-08 | No Project Manager | UK Link |  | Simon Harris | No Date | No Date | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request
5209 | Amendments to the CDSP Service Document - Budget & Charging Methodology v4 | CP | LIVE | A2 - CP proposed for ChMC | 2020-07-16 | No Project Manager | Finance |  | Nick Stace | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5210 | Daily CV Determination Interim Service: DN Invoicing Options | CP | LIVE | Unassigned Customer Change Backlog | 2020-07-23 | No Project Manager | UK Link |  | Emma Smith | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5218 | CDSP provision of Class 1 read service | CP | LIVE | Capture | 2020-08-03 | Bruce Kamen | CIF |  | Bruce Kamen | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5225 | (MiR8) Minor Release Drop 8 | CP | LIVE | Capture | 44050 | Bali Bahia | UK Link | MiR Drop 8 | Bali Bahia | No Date | No Date | FALSE | FALSE | FALSE | FALSE | No DSC Service Area
5231 | Provision of a FWACV Service | CP | LIVE | Capture | 44070 | Bruce Kamen | CIF |  | Steve Pownall | No Date | No Date | TRUE | TRUE | FALSE | FALSE | No DSC Service Area
5235 | Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) | CP | LIVE | A1 - CIF - Awaiting Capture Assignment | 44092 | No Project Manager | CIF |  | No Customer Change Team Lead | 44500 | 44500 | TRUE | TRUE | FALSE | FALSE | No DSC Service Area
5236 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | CP | LIVE | A1 - CIF - Awaiting Capture Assignment | 44092 | No Project Manager | CIF |  | No Customer Change Team Lead | No Date | No Date | TRUE | FALSE | FALSE | FALSE | No DSC Service Area
5237 | Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736 / 0736A) | CP | LIVE | A1 - CIF - Awaiting Capture Assignment | 44092 | No Project Manager | CIF |  | No Customer Change Team Lead | No Date | No Date | TRUE | FALSE | FALSE | FALSE | No DSC Service Area
5238 | New Distribution Network Report – Forecast Invoice Values | CP | LIVE | A1 - CIF - Awaiting Capture Assignment | 44085 | No Project Manager | CIF |  | No Customer Change Team Lead | No Date | No Date | FALSE | TRUE | FALSE | FALSE | No DSC Service Area