## Slide 1: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4992a: Post Implementation Support completed on 26/05 Fix successfully deployed on 27/05 for issue identified with the level of aggregation in the RTB invoice XRN5188b: Post Implementation Support completed on 26/05 MAP ID data interim load completed on 25/05 Closedown in progress for all November 21 in scope changes Decision in July ChMC: Approval of Nov 21 Change Completion Report (CCR) |  | XRN5289 | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope - XRN4941 - MOD0692 - Auto updates to meter read frequency In scope - XRN5007 - Enhancement to reconciliation process where prevailing volume is zero​ In Scope - XRN5072 - Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ In Scope - XRN5142 - New allowable values for DCC Service Flag in DXI File from DCC​ In Scope - XRN5180 - Inner tolerance validation for replacement reads and read insertions​ In Scope - XRN4780C – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) In Scope - XRN4992a - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process In Scope - XRN5188b - Interim Data Loads of MAP Id into UK Link Descoped - XRN5091 - Deferral of creation of Class change reads at transfer of ownership​ Descoped - XRN5186 MOD0701 – Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ Descoped - XRN5187 MOD0696 – Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 27th June 2022
Complete
On Track
At Risk
Overdue
Not Baselined