## Sheet1
RELEASE 3 - MARKET TRIALS - DAILY DASHBOARD
Date: |  | 2018-12-27
MT Progress Summary
1) Testing continues for Week 3 of Market Trials 2) Commodity runtime issue has been fixed with a root cause analysis and will be re-run 28/09/18 am. 3) All but 4 changes have closed testing
File Summary
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Inbound | 150 | 134 | 0 | 0 | 0 | 0 | 6 | 1 | 8 | 0 | 1 | 0 | 0
Outbound | 284 | 62 | 34 | 8 | 8 | 10 | 42 | 10 | 21 | 9 | 9 | 31 | 40
Defects
Defect ID | Linked SD Plus | 1: Summary; 8: Status; 10: Target Date; 12: Priority
234 | 899187 | 1: MID file not rejected; 8: Closed; 10: 2018-09-14; 12: P3
237 | 899569 | 1: Market Flow channels closed; 8: Closed; 10: 2018-09-13; 12: P2
236 | 899331 | 1: SFR response file failed at AMT; 8: Closed; 10: 2018-09-14; 12: P3
N/A | 901489 | 1: MARKET TRIALS - URS "N" Tolerance flag accepted; 8: Closed; 10: 2018-09-24; 12: P3
| 901506 | 1: Read rejected for unexpected reason – Lower than latest read; 8: Closed; 10: 2018-09-25; 12: P3
| 901733 | 1: Invoicing Files not flowing out of IX; 8: Closed; 10: 2018-09-20; 12: P3
| 902786 | 1: Reads rejected for unexpected reason – tolerance higher; 8: Retest; 10: 2018-09-28; 12: P3
| 903820 | 1: Missing rejected Energy value; 8: Retest; 10: 2018-10-03; 12: P3
| 903838 | 1: Missing S72 record in AQR file; 8: Retest; 10: 2018-10-03; 12: P3
Queries
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Open | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closed | 40 | 26 | 2 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 1 | 0 | 0
Total | 40 | 26 | 2 | 0 | 0 | 1 | 6 | 0 | 4 | 0 | 1 | 0 | 0
Open Queries
Query ID | Summary