## Sheet1
XRN Ref | Change Ref | Change Title | Change description | Status | Impacted Users | Comments
XRN3477 | UKLP112 | Missing Key Data Items from iGTs to Shippers (plot Number) | A requirement to include the Plot number within current Shippers File Formats. | Primary Scope | iGT / Shippers
XRN4284 | 122 | PAF Indicator field inclusion on VAD and ACR files | A requirement to include the PAF Indicator field on VAD and ACR file formats. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4287 | 140 | .DUP &.DUUS file type registration in AMT V1 | A requirement to support the duplicate invoice & supporting information from the new UK Link application | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4288 | UKLP147 | DDS/DDU file amendment | A requirement for the following changes to the DN DDS and DDU files: 1. Twin stream Meters - For DDS and DDU files to only contain the first Asset for a twin stream Meter i.e. suppress any instances where there is a second record for an MPRN. 2. Rolling AQ updates – For the DDU file to not include any records relating to rolling AQ updates. | Primary Scope | DNs
XRN4290 | UKLP194 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | A requirement to create an enduring solution for National Grid to receive the billing history data to feed into the analysis, that will be conducted as part of the Phase 4 and Charging Review (Gas).The data is required from Nexus Implementation date on an enduring basis (annual and monthly basis which is dependent on that particular report) via report/s which should have the flexibility to be run by a number of users (within Market Change Gas). | Change Removed |  | Industry request to remove as no business benefit
XRN4291 | UKLP197 | Addition of New fields from CMS being available in BW/IP reporting environment | Addition of new fields from CMS to Xoserve' s SAP Business Warehouse to enable use in future reporting services. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN3995 | UKLP222 | Theft Risk Assessment Service Tip-off Hotline Data Provision – Enduring Solution | A requirement for an enduring solution for the Energy Theft Tip-Off Services provider to identify an MPRN for an address where they receive a tip-off/notification of a suspected theft of gas situation. Xoserve would provide a monthly report to the Energy Theft Tip-Off Services provider via a .csv file. | Primary Scope | Energy Theft Tip Off Services (ETTOS)
XRN4295 | UKLP223 | Allow for a capacity revision on a Seasonally Large Supply Point | A requirement to support UNC code B4.9.2 - The current design does not allow for a capacity revision for a Seasonal Supply Point. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4297 | UKLP226 | Provide the DMSP with the AQ in the O13 record on the GCC file | Requirements: 1. Provide the DMSP with the site AQ value in order they can accurately validate class 1 Readings prior to submission to Xoserve. 2. Trigger the GCC file following a ‘finalised ratchet’ to the DMSP. 3. Supply the MNEPOR value for any NTS data logged SMP’s | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4299 | UKLP251 | Reports required under UNC TPD V16.1 in Nexus (reports required by MOD 520A) | A requirement for a number of reports. DNs are to provide a number of reports both to the industry in general and also to Performance Assurance Committee members. | In Scope | DNs/Shippers
XRN4300 | UKLP256 | NDM Twin Stream Read Validation | A requirement to support NDM twin stream and automated Read input validation process. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4303 | UKLP267 | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | A requirement to adjust file format that allows the User to set ‘n’ when providing site visit Reads via the SFN file, this indicates that, following site visit, the Reads taken have not fixed the fault. | Primary Scope | Shippers
XRN4304 | UKLP270 | Amend referral rules for class 2 smaller LSP’s | A requirement to accept Class 2 Meter Points and to be a configurable upper value with the ability to increase/decrease if required. There could be a significant number of Class 2 Meter Points, some of which will have lower AQ/SOQ value (LSP’s that still require nomination). | Primary Scope | DNs
XRN4449 | UKLP273 | PSR Requirements - Vulnerable Customer Data Requirements | A requirements to be in place to assist customers in vulnerable situations; - Aligned vulnerable customer needs codes between Gas and electricity - Mapping of existing vulnerable customer needs code to new vulnerable customer needs code | Primary Scope | iGT / DNs / Shippers
XRN4309 | UKLP287 | Back billing for domestic (SSP) sites needs to be reflect the correct adjustment start date | A requirement to ensure correct adjustment period is billed for SSP sites as part of the back billing (GSR site visit) process. | Primary Scope | Shippers
XRN2381.5B | UKLP292 | Changes to the upper parameter of the XDO partial refresh file | A requirement to ensure that the obligations in the Smart Energy Code are fully met. At present a request greater than 30k MPRNs cannot be met. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a partial request of any size up to a full portfolio. | Primary Scope | DCC
XRN4311 | UKLP300 | Unique Sites – Adding profiles | A requirement to enable the correct profiles to be added automatically and not manually. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4316 | UKLP315 | Meter Point Details Report and Sector Breakdown Report | A requirement to develop two reports to validate the amendment invoices. 1. Meter Point Details Report 2. Sector Breakdown Report | Primary Scope
XRN4318 | UKLP325 | Annual shrinkage submission (.ORD ) received from Networks is not getting apportioned correctly when the adjustment period is spanning across Nexus Go live date (01-June-2017) | A requirement to correct the smearing process for Annual shrinkage in SAP because the current design is considering the variance period as 6 months and this will not work as expected with the new Go live date as 01-June-2017. If the error persists it will result in incorrect charges present in the amendment invoice (AMS) and will have financial impacts to Networks revenue. | Change Removed - 27th November 2017 |  | Please click to Refer to presentation at DSC for more information
XRN4248 | N/A | Quarterly smart Metering reporting for HSE and DNs | A requirement to produce a quarterly report to be provided as a national report to the HS&E and as a DN level report to each network summarising Meter exchanges and installations. | Primary Scope | HSE DNs
XRN3386 | N/A | New DN role for CMS | A requirement to create a new role that includes all activities that can be undertaken within DNs to facilitate more efficient working practices. | Primary Scope | DNs iGTs
XRN3283 | N/A | Recording of DN Siteworks / New Network Connection Reference in Central System | A requirement to receive Network connection(s) reference numbers and the ability to store these reference numbers in a central system. | Primary Scope | DNs
XRN4249 | N/A | Address Solution | The current address (PAF) validation will not be enduring. The current PAF validation tool process (GB mailing) has not been built into the SAP system and as a result, an alternative validation tool needs to be determined to replace this. | Secondary Scope | Shippers DNs
XRN4513 | UKLP359 | Validate all address fields - CMS |  | Secondary Scope | Shippers DNs
XRN4514 | UKLP367 | MIV File changes for MUR Invoice |  | Secondary Scope | Xoserve

## Sheet2
100
100
0