## RT Summary
XRN4361 - UK Link Future Release 2 Regression Testing Report
2018-06-22
|  | XRN ID | CR ID | Change RAG | Execution Start Date | Assurance End Date | Total | Test Case Executed | Awaiting Assurance | Passed Assurance | Failed Assurance | Defects Raised | Defects Resolved | Risk | Return To Green
|  | XRN3477 | CR112 | 100 | 2018-05-21 | 2018-06-01 | 4 | 4 | 0 | 4 | 0 | 1 | 1
|  | XRN4288 | CR147 | 100 | 2018-05-21 | 2018-06-11 | 13 | 13 | 0 | 13 | 0 | 2 | 2
|  | XRN4304 | CR270 | 100 | 2018-05-25 | 2018-06-13 | 14 | 14 | 0 | 14 | 0 | 1 | 1
|  | XRN4303 | CR267 | 100 | 2018-05-21 | 2018-06-05 | 10 | 10 | 0 | 10 | 0 | 0 | 0
|  | XRN3283 | COR3283 | 100 | 2018-06-04 | 2018-06-16 | 16 | 16 | 0 | 16 | 0 | 1 | 1
|  | XRN3386 | COR3386 | 100 | 2018-05-28 | 2018-06-06 | 7 | 7 | 0 | 7 | 0 | 0 | 0
|  | XRN4514 | CR367 | 100 | 2018-06-05 | 2018-06-16 | 10 | 10 | 0 | 10 | 0 | 0 | 0
|  | XRN4299 | CR251 | 100 | 2018-06-05 | 2018-06-08 | 1 | 1 | 0 | 1 | 0 | 0 | 0
|  | XRN4513 | CR359 | 100 | 2018-05-21 | 2018-06-06 | 15 | 15 | 0 | 15 | 0 | 0 | 0
|  | XRN2831.5 | CR292 | 100 | 2018-05-21 | 2018-05-24 | 1 | 1 | 0 | 1 | 0 | 0 | 0
|  | XRN4449 | CR273 | 100 | 2018-05-25 | 2018-06-15 | 22 | 22 | 0 | 22 | 0 | 6 | 6
|  | XRN4249 | XRN4249 | 100 | 2018-05-21 | 2018-06-12 | 12 | 12 | 0 | 12 | 0 | 5 | 5
|  | XRN4309 | CR287 | 100 | 2018-05-28 | 2018-06-14 | 11 | 11 | 0 | 11 | 0 | 3 | 3
[7 empty] | 136 | 136 | 0 | 136 | 0 | 19 | 19
Status | Regression
Passed | 136
Failed | 0
In Progress | 0
Not Started | 0
Defects | Count
Open | 0
In Progress | 4
Closed | 19
Brief Summary:
A total of 136 test cases have been executed and passed through to assurance.
A total of 136 test cases have been assured.
Defects :
19 defects have been identified and 19 have been closed.

## PT Summary
XRN4361 - UK Link Future Release 2 Regression Testing Report
2018-06-22
|  | XRN ID | CR ID | Change RAG | Execution Start Date | Assurance End Date | Total | Test Case Executed | Awaiting Assurance | Passed Assurance | Failed Assurance | Defects Raised | Defects Resolved | Risk | Return To Green
|  | XRN3477 | CR112 | 100 | 2018-05-21 | 2018-06-01 | 4 | 4 | 0 | 4 | 0 | 1 | 1
|  | XRN4288 | CR147 | 100 | 2018-05-21 | 2018-06-11 | 13 | 13 | 0 | 13 | 0 | 2 | 2
|  | XRN4304 | CR270 | 100 | 2018-05-25 | 2018-06-13 | 14 | 14 | 0 | 14 | 0 | 1 | 1
|  | XRN4303 | CR267 | 100 | 2018-05-21 | 2018-06-05 | 10 | 10 | 0 | 10 | 0 | 0 | 0
|  | XRN3283 | COR3283 | 100 | 2018-06-04 | 2018-06-16 | 16 | 16 | 0 | 16 | 0 | 1 | 1
|  | XRN3386 | COR3386 | 100 | 2018-05-28 | 2018-06-06 | 7 | 7 | 0 | 7 | 0 | 0 | 0
|  | XRN4514 | CR367 | 100 | 2018-06-05 | 2018-06-16 | 10 | 10 | 0 | 10 | 0 | 0 | 0
|  | XRN4299 | CR251 | 100 | 2018-06-05 | 2018-06-08 | 1 | 1 | 0 | 1 | 0 | 0 | 0
|  | XRN4513 | CR359 | 100 | 2018-05-21 | 2018-06-06 | 15 | 15 | 0 | 15 | 0 | 0 | 0
|  | XRN2831.5 | CR292 | 100 | 2018-05-21 | 2018-05-24 | 1 | 1 | 0 | 1 | 0 | 0 | 0
|  | XRN4449 | CR273 | 100 | 2018-05-25 | 2018-06-15 | 22 | 22 | 0 | 22 | 0 | 6 | 6
|  | XRN4249 | XRN4249 | 100 | 2018-05-21 | 2018-06-12 | 12 | 12 | 0 | 12 | 0 | 5 | 5
|  | XRN4309 | CR287 | 100 | 2018-05-28 | 2018-06-14 | 11 | 11 | 0 | 11 | 0 | 3 | 3
[7 empty] | 136 | 136 | 0 | 136 | 0 | 19 | 19
Status | Regression
Passed | 136
Failed | 0
In Progress | 0
Not Started | 0
Defects | Count
Open | 0
In Progress | 4
Closed | 19
Brief Summary:
Cycle 1 has finished execution and assurance
Cycle 2 has finished execution and assurance
Defects:
3 Defects identified and 3 closed
Brief Summary:
A total of 136 test cases have been executed and passed through to assurance.
A total of 136 test cases have been assured.
Defects :
19 defects have been identified and 19 have been closed.

## UAT Summary
XRN4361 - UK Link Future Release 2 Acceptance Testing Report
2018-06-22
|  | XRN ID | CR ID | Change RAG | Execution Start Date | Assurance End Date | Total | Test Case Executed | Awaiting Assurance | Passed Assurance | Failed Assurance | Defects Raised | Defects Resolved | Risk | Return To Green
|  | XRN3477 | CR112 | 100 | 2018-03-12 | 2018-03-22 | 8 | 8 | 0 | 8 | 0 | 0 | 0
|  | XRN4288 | CR147 | 100 | 2018-03-12 | 2018-03-29 | 11 | 11 | 0 | 11 | 0 | 0 | 0
|  | XRN4304 | CR270 | 100 | 2018-03-22 | 2018-04-13 | 26 | 26 | 0 | 26 | 0 | 0 | 0
|  | XRN4303 | CR267 | 100 | 2018-03-12 | 2018-03-22 | 8 | 8 | 0 | 8 | 0 | 0 | 0
|  | XRN4248 | XRN4248 | 100 | 2018-03-12 | 2018-03-19 | 3 | 3 | 0 | 3 | 0 | 0 | 0
|  | XRN3995 | CR222 | 100 | 2018-03-26 | 2018-04-03 | 4 | 4 | 0 | 4 | 0 | 0 | 0
|  | XRN3283 | COR3283 | 100 | 2018-04-02 | 2018-05-02 | 23 | 23 | 0 | 23 | 0 | 0 | 0
|  | XRN3386 | COR3386 | 100 | 2018-03-12 | 2018-03-27 | 14 | 14 | 0 | 14 | 0 | 0 | 0
|  | XRN4514 | CR367 | 100 | 2018-04-30 | 2018-05-08 | 8 | 8 | 0 | 8 | 0 | 1 | 1
|  | XRN4299 | CR251 | 100 | 2018-04-30 | 2018-05-18 | 21 | 21 | 0 | 21 | 0 | 1 | 1
|  | XRN4513 | CR359 | 100 | 2018-03-19 | 2018-04-06 | 22 | 22 | 0 | 22 | 0 | 2 | 2
|  | XRN2831.5 | CR292 | 100 | 2018-03-19 | 2018-03-23 | 3 | 3 | 0 | 3 | 0 | 0 | 0
|  | XRN4449 | CR273 | 100 | 2018-03-26 | 2018-05-03 | 57 | 57 | 0 | 57 | 0 | 8 | 8
|  | XRN4249 | XRN4249 | 100 | 2018-04-03 | 2018-05-15 | 38 | 38 | 0 | 38 | 0 | 12 | 12
|  | XRN4316 | CR315 | 100 | 2018-05-02 | 2018-05-18 | 14 | 14 | 0 | 14 | 0 | 7 | 7
|  | XRN4309 | CR287 | 100 | 2018-04-12 | 2018-05-18 | 11 | 11 | 0 | 11 | 0 | 3 | 3
[7 empty] | 271 | 271 | 0 | 271 | 0 | 34 | 34
Status | Acceptance Tests
Passed | 271
Failed | 0
In Progress | 0
Not Started | 0
Defects | Count
Open | 0
In Progress | 0
Closed | 34
Brief Summary:
1. A total of 271 Test Cases have been executed. 1 test cases is remaining based on the below identified issue.
2. A total of 271 Test Cases have passed assurance.
Defects:
34 defects have been identified, 34 have been closed.
Only 4 of the 34 defects was raised as part of assurance. The remaining 30 were raised as part of execution.

## HighLevel_Timeline
UK Link Future Release R2.0 - Acceptance Testing Plan
Workstreams | Change Reference | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
SAP ISU | UKLP112
SAP BW | XRN4248
SAP ISU/SAP BW | UKLP147
SAP ISU | UKLP270
SAP BW | UKLP222
SAP ISU/CMS/SAP BW | COR3283
SAP BW | UKLP292
SAP ISU/AMT | UKLP267
SAP ISU | UKLP273
SAP BW | UKLP251
CMS | COR3386
SAP ISU | UKLP287
CMS | UKLP359
CMS | UKLP367
SAP ISU | XRN4249
Test Data Creation, Execution, Defect Retest & Closure
Assurance
Training Development
Note on Y29: This window is for 2 additional BW TCs which are not yet approved.

## RT Dashboard
XRN ID | CR ID |  | Test Case Total |  | Planned RT dates |  | BREAKDOWN OF RT TEST CASES EXECUTED |  |  |  |  | BREAKDOWN OF RT TEST CASES ASSURED |  |  |  |  | % Completed |  |  | 2018-06-22
|  | Change RAG | Regression | Planned Completion | Execution Start Date | Assurance End Date | Not Started | In Progress | Passed | Failed | Total | Not Started | In Progress | Passed | Failed | Total
XRN3477 | CR112 | 100 | 4 | 4 | 2018-05-21 | 2018-06-01 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-21 | 290.9091
XRN4288 | CR147 | 100 | 13 | 13 | 2018-05-21 | 2018-06-11 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0 | 13 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-22 | 155
XRN4304 | CR270 | 100 | 14 | 14 | 2018-05-25 | 2018-06-13 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 14 | 0 | 14 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-28 | 156.25
XRN4303 | CR267 | 100 | 10 | 10 | 2018-05-21 | 2018-06-05 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-22 | 221.4286
XRN3283 | COR3283 | 100 | 16 | 16 | 2018-06-04 | 2018-06-16 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | ggggggggggggggggggggggggggggggggg | 100 | 2018-06-05 | 154.5455
XRN3386 | COR3386 | 100 | 7 | 7 | 2018-05-28 | 2018-06-06 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 7 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-29 | 300
XRN4514 | CR367 | 100 | 10 | 10 | 2018-06-05 | 2018-06-16 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | ggggggggggggggggggggggggggggggggg | 100 | 2018-06-06 | 160
XRN4299 | CR251 | 100 | 1 | 1 | 2018-06-05 | 2018-06-08 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | ggggggggggggggggggggggggggggggggg | 100 | 2018-06-06 | 800
XRN4513 | CR359 | 100 | 15 | 15 | 2018-05-21 | 2018-06-06 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 15 | 0 | 15 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-21 | 200
XRN2831.5 | CR292 | 100 | 1 | 1 | 2018-05-21 | 2018-05-24 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-22 | 1550
XRN4449 | CR273 | 100 | 22 | 22 | 2018-05-25 | 2018-06-15 | 0 | 0 | 22 | 0 | 22 | 0 | 0 | 22 | 0 | 22 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-28 | 138.8889
XRN4249 | XRN4249 | 100 | 12 | 12 | 2018-05-21 | 2018-06-12 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-21 | 145.4545
XRN4309 | CR287 | 100 | 11 | 11 | 2018-05-28 | 2018-06-14 | 0 | 0 | 11 | 0 | 11 | 0 | 0 | 11 | 0 | 11 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-29 | 150
|  |  | 136 | 136 |  |  | 0 | 0 | 136 | 0 | 136 | 0 | 0 | 136 | 0 | 136 | ggggggggggggggggggggggggggggggggg | 100

## PT Dashboard
XRN ID | CR ID |  | Test Case Total |  | Planned Performance dates |  | BREAKDOWN OF PT TEST CASES EXECUTED |  |  |  |  | RATIO |  | BREAKDOWN OF PT TEST CASES ASSURED |  |  |  |  | RATIO |  | % Completed
|  | Change RAG | Performance | Planned Completion | Execution Start Date | Assurance End Date | Not Started | In Progress | Passed | Failed | Total | Pass | Fail | Not Started | In Progress | Passed | Failed | Total | Pass | Fail
XRN4288 | CR147 | 100 | 8 | 8 | 2018-05-01 | 2018-05-16 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN3283 | COR3283 | 100 | 8 | 8 | 2018-05-01 | 2018-05-17 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN3386 | COR3386 | 100 | 5 | 5 | 2018-05-01 | 2018-05-17 | 0 | 0 | 5 | 0 | 5 | 100 | 0 | 0 | 0 | 5 | 0 | 5 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN4514 | CR367 | 100 | 7 | 7 | 2018-05-01 | 2018-05-17 | 0 | 0 | 7 | 0 | 7 | 100 | 0 | 0 | 0 | 7 | 0 | 7 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN4513 | CR359 | 100 | 4 | 4 | 2018-05-01 | 2018-05-17 | 0 | 0 | 4 | 0 | 4 | 100 | 0 | 0 | 0 | 4 | 0 | 4 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN2831.5 | CR292 | 100 | 1 | 1 | 2018-05-08 | 2018-05-16 | 0 | 0 | 1 | 0 | 1 | 100 | 0 | 0 | 0 | 1 | 0 | 1 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN4449 | CR273 | 100 | 47 | 47 | 2018-05-02 | 2018-05-18 | 0 | 0 | 47 | 0 | 47 | 100 | 0 | 0 | 0 | 47 | 0 | 47 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN4249 | XRN4249 | 100 | 17 | 17 | 2018-05-02 | 2018-05-23 | 0 | 0 | 17 | 0 | 17 | 100 | 0 | 0 | 0 | 17 | 0 | 17 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
XRN4316 | CR315 | 100 | 2 | 1 | 2018-05-14 | 2018-05-24 | 0 | 0 | 2 | 0 | 2 | 100 | 0 | 0 | 0 | 2 | 0 | 2 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100
|  |  | 99 | 98 |  | 2018-06-16 | 0 | 0 | 99 | 0 | 99 | 101.0204 | 0 | 0 | 0 | 99 | 0 | 99 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100

## UAT Dashboard
XRN ID | CR ID |  | Test Case Total |  | Planned UAT dates |  | BREAKDOWN OF UAT TEST CASES EXECUTED |  |  |  |  | RATIO |  | BREAKDOWN OF UAT TEST CASES ASSURED |  |  |  |  | RATIO |  | % Completed |  |  | 2018-06-22
|  | Change RAG | Acceptance | Planned Completion | Execution Start Date | Assurance End Date | Not Started | In Progress | Passed | Failed | Total | Pass | Fail | Not Started | In Progress | Passed | Failed | Total | Pass | Fail
XRN3477 | CR112 | 100 | 8 | 8 | 2018-03-12 | 2018-03-22 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-13 | 1122.2222
XRN4288 | CR147 | 100 | 11 | 11 | 2018-03-12 | 2018-03-29 | 0 | 0 | 11 | 0 | 11 | 100 | 0 | 0 | 0 | 11 | 0 | 11 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-13 | 631.25
XRN4304 | CR270 | 100 | 26 | 26 | 2018-03-22 | 2018-04-13 | 0 | 0 | 26 | 0 | 26 | 100 | 0 | 0 | 0 | 26 | 0 | 26 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-23 | 433.3333
XRN4303 | CR267 | 100 | 8 | 8 | 2018-03-12 | 2018-03-22 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-13 | 1122.2222
XRN4248 | XRN4248 | 100 | 3 | 3 | 2018-03-12 | 2018-03-19 | 0 | 0 | 3 | 0 | 3 | 100 | 0 | 0 | 0 | 3 | 0 | 3 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-14 | 2000
XRN3995 | CR222 | 100 | 4 | 4 | 2018-03-26 | 2018-04-03 | 0 | 0 | 4 | 0 | 4 | 100 | 0 | 0 | 0 | 4 | 0 | 4 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-27 | 1242.8571
XRN3283 | COR3283 | 100 | 23 | 23 | 2018-04-02 | 2018-05-02 | 0 | 0 | 23 | 0 | 23 | 100 | 0 | 0 | 0 | 23 | 0 | 23 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-04-03 | 275.8621
XRN3386 | COR3386 | 100 | 14 | 14 | 2018-03-12 | 2018-03-27 | 0 | 0 | 14 | 0 | 14 | 100 | 0 | 0 | 0 | 14 | 0 | 14 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-13 | 721.4286
XRN4514 | CR367 | 100 | 8 | 8 | 2018-04-30 | 2018-05-08 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | 0 | 0 | 8 | 0 | 8 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-01 | 742.8571
XRN4299 | CR251 | 100 | 21 | 21 | 2018-04-30 | 2018-05-18 | 0 | 0 | 21 | 0 | 21 | 100 | 0 | 0 | 0 | 21 | 0 | 21 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-05-01 | 305.8824
XRN4513 | CR359 | 100 | 22 | 22 | 2018-03-19 | 2018-04-06 | 0 | 0 | 22 | 0 | 22 | 100 | 0 | 0 | 0 | 22 | 0 | 22 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-20 | 552.9412
XRN2831.5 | CR292 | 100 | 3 | 3 | 2018-03-19 | 2018-03-23 | 0 | 0 | 3 | 0 | 3 | 100 | 0 | 0 | 0 | 3 | 0 | 3 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-20 | 3133.3333
XRN4449 | CR273 | 100 | 57 | 57 | 2018-03-26 | 2018-05-03 | 0 | 0 | 57 | 0 | 57 | 100 | 0 | 0 | 0 | 57 | 0 | 57 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-03-27 | 235.1351
XRN4249 | XRN4249 | 100 | 38 | 38 | 2018-04-03 | 2018-05-15 | 0 | 0 | 38 | 0 | 38 | 100 | 0 | 0 | 0 | 38 | 0 | 38 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-04-05 | 195
XRN4316 | CR315 | 100 | 14 | 14 | 2018-05-02 | 2018-05-18 | 0 | 0 | 14 | 0 | 14 | 100 | 0 | 0 | 0 | 14 | 0 | 14 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 2018-04-23 | 240
XRN4309 | CR287 | 100 | 11 | 11 | 2018-04-12 | 2018-05-18 | 0 | 0 | 11 | 0 | 11 | 100 | 0 | 0 | 0 | 11 | 0 | 11 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100 | 0 | 100.0809
|  |  | 271 | 271 |  |  | 0 | 0 | 271 | 0 | 271 | 100 | 0 | 0 | 0 | 271 | 0 | 271 | 100 | 0 | ggggggggggggggggggggggggggggggggg | 100

## FR2_TestPlan
CRID | Test Scenario | Test Boundary | Data Conditions | Special Data Conditions | Files Involved | Execution Status | Linked Defect | Planned Execution Start Date | Planned Execution End Date | Actual Execution Start Date | Actual Execution End Date | Assurance Status | Assurance Planned Start Date | AssurancePlanned End Date | Actual Assurance End Date | Comments
CR112 | IMC file received for iGT SMP creation(FOM request) with DLVRY_PNT_ALIAS & ELECTED_SHIPPER_SHORT_CODE populated, AES file should be sent with T08 record replaying all address details received | AES Trigger till AMT Market flow | Class 1 iGT DM | ELECTED_SHIPPER_SHORT_CODE provided with IMC AQ >5.8600000 | IMC, IMR & AES | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-12 | Passed | 2018-03-14 | 2018-03-14 | 2018-03-14
CR112 | IMC file received for iGT SMP creation(FOM request) with DLVRY_PNT_ALIAS & ELECTED_SHIPPER_SHORT_CODE populated, AES file should be sent with T08 record replaying all address details received | AES Trigger till AMT Market flow | Class 4 iGT NDM | ELECTED_SHIPPER_SHORT_CODE provided with IMC AQ <73200 | IMC, IMR & AES | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-12 | Passed | 2018-03-14 | 2018-03-14 | 2018-03-14
CR147 | Run the Monthly rolling AQ updates, no trigger should be created for DDU files | DDU files in AMT | Run Rolling AQ update on Class 1 Twin Stream site. Execute DDU. Trigger and DDU file is not expected for test MPRN. | Class 1 Twin Stream Site. DDU is not expected | DDU | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-14 | Passed | 2018-03-14 | 2018-03-15 | 2018-03-15
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as N, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 4 IGT | Site with existing DRE fault | SFN and SFR | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-12 | Passed | 2018-03-14 | 2018-03-14 | 2018-03-16
CR112 | ITC file received with transportation rate updates, AES should be sent to elected shipper | AES Trigger till AMT Market flow | Class 4 iGT NDM | Delivery point Alias available for SMP (Pre-registration) AQ < 73200 , Existing: Greenfield site, Elected shipper already present with DPAS | ITC,ITR | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-15 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-15
CR112 | IMC file received with DLVRY_PNT_ALIAS but no elected shipper, AES file should not be triggered | No AES required to go out from SAP System | Class 4 iGT NDM | ELECTED_SHIPPER_SHORT_CODE not provided with IMC Delivery point Alias available for SMP (Pre-registration) AQ < 73200 , Existing: Greenfield site | IMC,IMR | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-15 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-15
CR112 | IMA file received with New elected shipper, AES should be sent with all the address details and DES to de-elected shipper | AES and DES file should go out till AMT. | Class 1 DM iGT | ELECTED_SHIPPER_SHORT_CODE available on SMP already changed by IMA AQ >5.8600000 | IMA,IME & AES | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-15 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-15
CR112 | ITC file received with transportation rate updates, AES should not be sent to elected shipper. | No AES file required to go out | Class 1 DM iGT | Post – Registration transportation rate updates AQ >5.8600000 | ITC, ITR | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-15 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-15
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by iGT Response file from iGT (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response IGT Meter point | NA | NA | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-19 | Passed | 2018-03-14 | 2018-03-14 | 2018-03-20
XRN4248 | Login to BI Portal or direct to BI login page with the below credentials Username:<<Username>>> Password:<<<Password>>> and press Enter. Refreshing the Report Note: If there is unexpected error and report does not open you should be able to reopen the report | BW | Report name: • Rpt_id_1250_HSE_Quarterly_Smart_Metering_DN_ Level |  |  | Passed |  | 2018-03-12 | 2018-03-14 |  | 2018-04-11 | Passed | 2018-03-19 | 2018-03-19 | 2018-04-17
CR112 | IMA file received for iGT SMP amendment(FOM request) populated, AES file should be sent with T08 record replaying all address details received | AES Trigger till AMT Market flow | Class 1 iGT DM | Delivery point alias is present However, ELECTED_SHIPPER provided with IMA file first time Pre-registration | IMA, IME, & AES | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-13 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-14
CR112 | IMA file received for iGT SMP amendment(FOM request) populated, AES file should be sent with T08 record replaying all address details received | AES Trigger till AMT Market flow | Class 4 iGT NDM | Delivery point alias is present However, ELECTED_SHIPPER provided with IMA file first time Pre-registration | IMA, IME, & AES | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-13 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-14
CR147 | Run the Monthly rolling AQ updates, no trigger should be created for DDU files | DDU files in AMT | Without executing Rolling AQ update, execute AQ correction on a Class 4 Twin Stream site. Trigger and DDU file is expected with appropriate values in M29 segment. | Class 4 Twin Stream Site. DDU is expected | DDU | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-16 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-19
CR147 | Run the Monthly rolling AQ updates, no trigger should be created for DDU files | DDU files in AMT | Rolling AQ update on Class 1 GT site which leads to change in EUC. Trigger and DDU file is expected with appropriate value in M29 segment. | Class 1 GT site. DDU is expected | DDU | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-16 | Passed | 2018-03-20 | 2018-03-21 | 2018-03-19
CR147 | Run the Annual FYAQ /FYSOQ updates, trigger should be created for DDU files | DDU files in AMT | Annual FYAQ /FYSOQ updates on a Class 3 GT site. Trigger and DDU file is expected with appropriate value in M29 segment with the updated values. | Class 3 GT site. DDU is expected with the updated FYAQ/FYSOQ values. | DDU | Passed |  | 2018-03-19 | 2018-03-20 |  | 2018-03-20 | Passed | 2018-03-21 | 2018-03-22 | 2018-03-21
CR147 | Run EUC update for 1st Oct, trigger should be created for DDU files and files should populate the EUC effective from 1st Oct | DDU files in AMT | Run EUC update for 1st Oct on a Class 1 GT Twin Stream site. Trigger and DDU file is expected with appropriate value in M29 segment and EUC effective from 1st Oct | Class 1 GT Twin Stream site. DDU is expected with EUC effective from 1st Oct | DDU | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-21 | Passed | 2018-03-22 | 2018-03-23 | 2018-03-23
CR147 | Run EUC update for 1st Oct, trigger should be created for DDU files and files should populate the EUC effective from 1st Oct | DDU files in AMT | Run EUC update for 1st Oct on a Class 1 GT LDZ Direct Connect Shorthaul site. Trigger and DDU file is expected with appropriate value in M29 segment and EUC effective from 1st Oct | Class 1 GT LDZ Direct Connect Shorthaul site. DDU is expected with EUC effective from 1st Oct | DDU | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-21 | Passed | 2018-03-26 | 2018-03-27 | 2018-03-23
CR147 | Run EUC update for 1st Oct, trigger should be created for DDU files and files should populate the EUC effective from 1st Oct | DDU files in AMT | No EUC update /Twin Stream update for Class 4 GT Twin Stream site. Trigger and DDU file is not expected. | Class 4 GT Twin Stream site. DDU is not expected. | DDU | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-22 | Passed | 2018-03-27 | 2018-03-28 | 2018-03-23
CR147 | RGMA updates the changes to meter model for a twin stream site, only one of the meters should be | DDU files in AMT | RGMA updates the changes to meter model for a Class 1 Twin Stream where changes occur to only one meter. Trigger and DDU file is expected with appropriate value in M29 segment and only one of the meters information must be present. | Class 1 Twin Stream Site. DDU is expected with details of only one meter ( Imperial_Meter_Indicator) | DDU | Passed |  | 2018-03-23 | 2018-03-26 |  | 2018-03-26 | Passed | 2018-03-27 | 2018-03-28 | 2018-03-28
CR147 | RGMA updates the changes to meter model for a twin stream site, only one of the meters should be | DDU files in AMT | RGMA updates the changes to meter model for a Class 1 Twin Stream where changes occur to both meters. Trigger and DDU file is expected with appropriate value in M29 segment and only one of the meters information must be present. | Class 1 Twin Stream Site. DDU is expected with details of only one meter ( Imperial_Meter_Indicator) | DDU | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-26 | Passed | 2018-03-28 | 2018-03-29 | 2018-03-28
CR147 | Verify meter details sent for scenario 4, same details are sent in DDS | DDS file in BW | Verify meter details sent for scenario 4, same details are sent in DDS | 1. Run DDS file generation job and check the DDS file whether same device is included like DDU | DDU, DDS | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-14 | Passed | 2018-03-29 | 2018-03-29 | 2018-03-15
CR147 | Verify meter details sent for scenario 4, same details are sent in DDS | DDS file in BW | Verify meter details sent for Scenario 4 are not included in EQL file as BW uses same table for EQL | 1. Run EQL file generation job and check the EQL file doesn’t include the MPRN in EQL file | DDU | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-14 | Passed | 2018-03-29 | 2018-03-29 | 2018-03-15
COR3283 | UIP / Xoserve raises FOM contact with site works reference number through the CMS screen. CMS process the contact and generate the ACR file with the address artifcats including Site Works Ref and sends the file to SAP-ISU. SAP processes the file and site works reference number should be stored in SAP along with the address against the requetsed MPRN. SAP sends the response file (ARS). CMS loads the response file and clears the contact. | Successful ARS to CMS | GT Site (Greenfield) 1. Request from UIP | - Alpha numeric Site works number - Contact created in CMS through QMP file for UIP | QMP, ACR ARS | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-02 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-04
COR3283 | Nomination request received from proposing shipper is referred for Capacity referral, existing siteworks reference should be displayed on Nomination referral screen at Portal | Successful ARS to CMS | GT Site (Greenfield) 1. Request from DNO | - Alpha numeric Site works number - Contact created in CMS through QMP File | QMP, ACR ARS | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-03 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-04
COR3283 | Request Meter Asset selection from Portal screen for a particular MPRN, details screen should display the existing site works reference at DN Portal | SMP Creation successful (If the Site works reference updated through MNC incorrectly, DNs can update it later through DN Portal) | Site type - 0001 LDZ Direct Connect (Greenfield) 1. Xoserve internal screens (SAP ISU - ZSMP) FOM request | - Except LPG, CSO and iGTs - FOM request - MPRN should be already present in the system | - | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-03 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-04
COR3283 | To check the NEI file loading onto CMS | Offer Supplied and Meter Point details Maintenance screen displayed the existing site works | Site with existing Site works reference GT, DM, Class 1 AQ>73200 | - Site works received in Nomination file same as that of existing | NOM, NMR, NRF | Passed |  | 2018-04-10 | 2018-04-10 |  | 2018-04-04 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-09
COR3283 | FOM and MNC contact received through CMS without site works reference, the request be accepted | Offer Supplied | Unique Sites - NTS Shorthaul site Referral for NeXA should display existing site works DM Class 1 | - Site Nomination file same as that of existing, existing site works should be displayed on portal screen | NOM, NMR, NRF | Passed |  | 2018-04-11 | 2018-04-11 |  | 2018-04-04 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-09
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed | Capacity Amendment LI | Site with existing Site works reference GT, DM, Class 2 | Existing site works reference | SPC, SCR, CRF | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-03-20 | Passed | 2018-04-10 | 2018-04-10 | 2018-03-23
COR3283 | UIP / Xoserve raises FOM contact with site works reference number through the CMS screen. CMS process the contact and generate the ACR file with the address artifcats including Site Works Ref and sends the file to SAP-ISU. SAP processes the file and site works reference number should be stored in SAP along with the address against the requetsed MPRN. SAP sends the response file (ARS). CMS loads the response file and clears the contact. The address data with site works reference flows to BW and inturn to DES (on request basis). Xoserve/Network logs onto DES to see the site works reference number, which was updated through CMS against the MPRN. Network user logs onto portal screen to amend the site works reference number. The site works ref number is successfully amended in portal. Xoserve user logs on to SAP-ISU, where the amended site works ref number is present against the MPR. The same data is flown to BW and inturn to DES post to the data load (on request basis). Xoserve / Network logs in back to DES to see the latest (amended) site works reference number. Xoserve logs onto CMS to check the original FOM contact,only to find the previous site works reference number which was raised by the UIP originally. | Site Works Reference Display at Portal | Site with existing Site works reference GT, DM, Class 1 | - Site with existing Site works reference | NA | Passed |  | 2018-04-12 | 2018-04-12 |  | 2018-04-06 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-09
COR3283 | Migration – Migration for any existing site works from Legacy (archived data) to ISU to be validated | Updated site works reference for installation EANL  ZZ_SITE_WORK_REF | 1. GT - Greenfield Site With incorrect site works reference | - Greenfield Site with existing Site works reference | NA | Passed |  | 2018-04-12 | 2018-04-12 |  | 2018-04-06 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-12
COR3283 | Use a QMP file in which the site works reference number exceeding 30 characters to raise FOM/MNC contacts | Meter Asset selection’ display, Site works reference should not be populated | GT, DM, Class 1 Existing site | - Site with existing site works reference Screen Navigation : Amendment Request from Portal (Meter Asset  Meter Point details Maintenance – Delete  change to blank and submit) | NA | Passed |  | 2018-04-16 | 2018-04-16 |  | 2018-04-06 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-12
COR3283 | FOM contact received through CMS without site works reference, the request be accepted | Successful ARS to CMS | GT Site (Greenfield) 1. Request from UIP - Screen | - Alpha numeric Site works number - Contact created in CMS from UIP through SCREEN | ARS | Passed |  | 2018-04-17 | 2018-04-17 |  | 2018-04-18 | Passed | 2018-04-18 | 2018-04-18 | 2018-04-20
COR3283 | Migration – Migration for any existing DN site works reference from CMS to ISU to be validated | Data Validation for site works reference | Site works reference migration from CMS to ISU | NA | NA | Passed |  | 2018-04-11 | 2018-04-11 |  | 2018-04-20 | Passed | 2018-04-16 | 2018-04-26 | 2018-04-27
COR3283 | Migration – Migration for any existing site works from Legacy (archived data) to ISU to be validated | Data Validation for site works reference | Site works reference migration from Legacy to ISU | NA | NA | Passed |  | 2018-04-17 | 2018-04-17 |  | 2018-04-20 | Passed | 2018-04-18 | 2018-04-26 | 2018-04-27
COR3283 | Run the BW report, to check the population of Site works reference BB_GSR_report_Network BB_MUS_Report_1 Plot_Report 2017-08-01-13-00-19 | Greenfield and un-registered sites | Greenfield and un-registered sites | NA | NA | Passed |  | 2018-04-18 | 2018-04-18 |  | 2018-04-19 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-20
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed | Site works reference will be added in right page of Meter Point Information tab | Site works reference will be added in right page of Meter Point Information tab | 1.Login by DNs & Xoserve --> DES screen should display the site works ref.(Only portfolio view) 2. Login by Shippers or other parties to DES --> Site works reference should not be displayed | NA | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-03-27 | Passed | 2018-04-16 | 2018-04-16 | 2018-03-29
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed |  | Site works reference will be added in right page of Meter Point Information tab | 1.Login by DNs & Xoserve --> DES screen should display the site works ref.(Only portfolio view) 2. Login by Shippers or other parties to DES --> Site works reference should not be displayed | NA | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-03-27 | Passed | 2018-04-16 | 2018-04-16 | 2018-03-29
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed |  | Site works reference will be added in right page of Meter Point Information tab | 1.Login by DNs & Xoserve --> DES screen should display the site works ref.(Only portfolio view) 2. Login by Shippers or other parties to DES --> Site works reference should not be displayed | NA | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-03-27 | Passed | 2018-04-16 | 2018-04-16 | 2018-03-29
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed |  | Site works reference will be added in right page of Meter Point Information tab | 1.Login by DNs & Xoserve --> DES screen should display the site works ref.(Only portfolio view) 2. Login by Shippers or other parties to DES --> Site works reference should not be displayed | NA | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-03-27 | Passed | 2018-04-16 | 2018-04-16 | 2018-03-29
COR3283 | Login to DES screen and query for an MPRN details, site works reference should be displayed |  | Site works reference will be added in right page of Meter Point Information tab | 1.Login by DNs & Xoserve --> DES screen should display the site works ref.(Only portfolio view) 2. Login by Shippers or other parties to DES --> Site works reference should not be displayed | NA | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-03-27 | Passed | 2018-04-16 | 2018-04-16 | 2018-03-29
COR3283 | UIP / Xoserve raises FOM contact with site works reference number through the CMS screen. CMS process the contact and generate the ACR file with the address artifcats including Site Works Ref and sends the file to SAP-ISU. SAP processes the file and site works reference number should be stored in SAP along with the address against the requested MPRN. SAP sends the response file (ARS). CMS loads the response file and clears the contact. The address data with site works reference flows to BW and inturn to DES (on request basis). Xoserve/Network logs onto DES to see the site works reference number, which was updated through CMS against the MPRN. Network user logs onto portal screen to amend the site works reference number. The site works ref number is successfully amended in portal. Xoserve user logs on to SAP-ISU, where the amended site works ref number is present against the MPR. The same data is flown to BW and in turn to DES post to the data load (on request basis). Xoserve / Network logs in back to DES to see the latest (amended) site works reference number. Xoserve logs onto CMS to check the original FOM contact, only to find the previous site works reference number which was raised by the UIP originally. | Generate the ACR file with Site work Reference number to PO>ISU>DES>PORTAL screens scenario | Generate the ACR file with Site work Reference number to PO>ISU>DES>PORTAL screens scenario | NA | NA | Passed |  | 2018-04-16 | 2018-04-16 |  | 2018-04-22 | Passed | 2018-04-16 | 2018-05-02 | 2018-05-01
COR3283 | Migration – Migration for any existing DN site works reference from CMS to ISU to be validated | Site works reference migration from CMS to ISU | Site works reference migration from CMS to ISU | NA | NA | Passed |  | 2018-04-17 | 2018-04-17 |  | 2018-04-20 | Passed | 2018-04-17 | 2018-04-26 | 2018-04-27
COR3283 | Migration – Migration for any existing site works from Legacy (archived data) to ISU to be validated | Site works reference migration from Legacy to ISU | Site works reference migration from Legacy to ISU | NA | NA | Passed |  | 2018-04-24 | 2018-04-24 |  | 2018-04-20 | Passed | 2018-04-18 | 2018-04-26 | 2018-04-27
COR3283 | Use a QMP file in which the site works reference number exceeding 30 characters to raise FOM/MNC contacts | 1. Request from UIP 2. Request from Xoserve | 1. Request from UIP 2. Request from Xoserve | GT MPRNS should be used | NA | Passed |  | 2018-04-20 | 2018-04-20 |  | 2018-04-19 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-19
COR3283 | UIP/Xoserve logs a FOM via screen the site works reference number exceeding 30 characters | 1. Request from UIP 2. Request from Xoserve | 1. Request from UIP 2. Request from Xoserve | GT MPRNS should be used | NA | Passed |  | 2018-04-23 | 2018-04-23 |  | 2018-04-19 | Passed | 2018-04-23 | 2018-04-23 | 2018-04-19
CR222 | File layout & Naming is as per requirement | Check the file format layout and naming | File layout & Naming is as per requirement | NA | NA | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-21 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-21
CR222 | GT/iGT Sites are included | check all GT/IGT sites are included | GT/iGT Sites are included | NA | NA | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-21 | Passed | 2018-03-30 | 2018-03-30 | 2018-03-21
CR222 | iGT sites are included | check all GT sites are included | iGT sites are included | NA | NA | Passed |  | 2018-03-30 | 2018-03-31 |  | 2018-03-21 | Passed | 2018-04-02 | 2018-04-02 | 2018-03-21
CR222 | LPG, Unique Sites are excluded | Check all LPG,Unique sites are excluded | LPG, Unique Sites are excluded | NA | NA | Passed |  | 2018-04-01 | 2018-04-02 |  | 2018-03-21 | Passed | 2018-04-03 | 2018-04-03 | 2018-03-21
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as N, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 3 GT | Site with existing DRE fault | SFN and SFR | Passed |  | 2018-03-12 | 2018-03-13 |  | 2018-03-12 | Passed | 2018-03-14 | 2018-03-14 | 2018-03-14
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as N, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 3 GT, | Site Without existing DRE fault | SFN and SFR | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-14 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-14
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as N, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 4 IGT, | Site Without existing DRE fault | SFN and SFR | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-14 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-14
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by MRA. Network will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should download the MJO file first. GT Meter point | NA | NA | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-16 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-16
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as X, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 3 GT, | Site Without existing DRE fault | SFN and SFR | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-14 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-16
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field populated as X, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 4 IGT, | Site Without existing DRE fault | SFN and SFR | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-14 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-16
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field as X, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 3 GT, | Site with existing fault | SFN and SFR | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-14 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-15
CR267 | End to End Test SFN file with DRE_FAULT_CORRECTED field as X, warning should be raised in AMT and file should be rejected with New rejection code (SFN00005) | SFN Rejection file | Class 4 IGT, | Site with existing fault | SFN and SFR | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-14 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-15
CR270 | Offer Supplied - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent | Offer supplied | Class: 2 Site Type: GT, All DNOs ( LDZ level Differentiation ) Requested SOQ & SHQ same as current | Existing Site, Shipper change Lower Range =73,200 Upper Range = Different for each DNO | NOM,NMR | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-19 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-19
CR270 | Offer Supplied - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent | Offer supplied | Class: 2 Site Type: GT, All DNOs ( LDZ level Differentiation ) Requested SOQ greater & SHQ same , ratio b/w 4 to 16 | Existing Site, Shipper change Lower Range =73,200 Upper Range = Different for each DNO | NOM,NMR | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-22 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-27
CR270 | Offer Supplied - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent | Offer supplied | Class: 2 Site Type: GT, All DNOs ( LDZ level Differentiation ) Requested SOQ lesser & SHQ greater | Existing Site, Shipper change Lower Range =73,200 Upper Range = Different for each DNO | NOM,NMR | Passed |  | 2018-03-23 | 2018-03-26 |  | 2018-03-22 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-27
CR270 | Offer Supplied - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent | Offer supplied | Class: 2 Site Type: GT, All DNOs ( LDZ level Differentiation ) Requested both SOQ & SHQ greater, ratio b/w 4 to 16 | Existing Site, Shipper change Lower Range =73,200 Upper Range = Different for each DNO | NOM,NMR | Passed |  | 2018-03-23 | 2018-03-26 |  | 2018-03-22 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-27
CR270 | Offer Supplied - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent | Offer supplied | Class: 2 Site Type: GT, All DNOs ( LDZ level Differentiation ) Requested SOQ is same & SHQ is greater than prevailing | Existing Site, Shipper change Lower Range =73,200 Upper Range = Different for each DNO | NOM,NMR | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-22 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-27
CR270 | Existing Site Reconfirmation - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to Igt | Confirmation effective date | Class: 2 Site Type: IGT, All DNOs ( LDZ level Differentiation ) Requested SOQ & SHQ same as current | Existing Site Reconfirmation | NOM,NMR, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-26 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-29
CR270 | Existing Site Reconfirmation - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to Igt | Confirmation effective date | Class: 2 Site Type: IGT, All DNOs ( LDZ level Differentiation ) Requested SOQ greater & SHQ same , ratio b/w 4 to 16 | Existing Site Reconfirmation | NOM,NMR,NRF, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-28 | Passed | 2018-03-29 | 2018-03-29 | 2018-03-29
CR270 | Existing Site Reconfirmation - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to Igt | Confirmation effective date | Class: 2 Site Type: IGT, All DNOs ( LDZ level Differentiation ) Requested SOQ lesser & SHQ greater | Existing Site Reconfirmation | NOM,NMR,NRF, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-27 | Passed | 2018-03-30 | 2018-03-30 | 2018-04-03
CR270 | Existing Site Reconfirmation - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to Igt | Confirmation effective date | Class: 2 Site Type: IGT, All DNOs ( LDZ level Differentiation ) Requested both SOQ & SHQ greater, ratio b/w 4 to 16 | Existing Site Reconfirmation | NOM,NMR,NRF, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-28 | Passed | 2018-03-30 | 2018-03-30 | 2018-04-03
CR270 | Existing Site Reconfirmation - Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to Igt | Confirmation effective date | Class: 2 Site Type: IGT, All DNOs ( LDZ level Differentiation ) Requested SOQ is same & SHQ is greater than prevailing | Existing Site Reconfirmation | NOM,NMR,NRF, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-28 | Passed | 2018-03-30 | 2018-03-30 | 2018-03-29
CR270 | Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to iGT | Confirmation effective date | Class change ( 3 to 2) - Medium GT, | Existing Site Shipper Change | NOM,NMR, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-29 | 2018-03-30 |  | 2018-03-30 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-05
CR270 | Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to iGT | Confirmation effective date | Class change ( 3 to 2) - Medium iGT | Existing Site Shipper Change | NM,NMR,NRF, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-29 | 2018-03-30 |  | 2018-03-30 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-06
CR270 | Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), no capacity referral should be sent to DNO but should be sent to iGT | Confirmation effective date | Class Change (1 to 2) – Low Priority IGT | Existing Site Shipper Change | NOM,NMR, CNF,CFR,TRF,MRI,MDS/AAQ | Passed |  | 2018-03-30 | 2018-04-02 |  | 2018-04-03 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-05
CR270 | Nomination Request Received with requested SOQ/SHQ values greater than that of prevailing SOQ/SHQ and ratio between >16 /<24, Capacity referral should not be sent | Offer supplied | Class: 2 Site Type: GT | Existing Site AQ between (>73,200 kWh / <732,000kWh), | NOM,NMR | Passed |  | 2018-03-30 | 2018-04-02 |  | 2018-03-30 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-05
CR270 | Nomination Request Received with requested SOQ/SHQ values greater than that of prevailing SOQ/SHQ and ratio between >16 /<24, Capacity referral should not be sent | Offer supplied | Class: 2 Site Type: iGT (Referral to iGT) | Existing Site AQ between (>73,200 kWh / <732,000kWh), | NOM,NMR, NRF | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-03 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-05
CR270 | Nomination Request received with Requested SOQ greater than prevailing SOQ but Requested SHQ less or equal to prevailing SHQ values and ratio between >16 /<24, Capacity referral should not be sent | Offer supplied | Class: 2 Site Type: GT | Existing Site AQ between (>73,200 kWh / <732,000kWh) | NOM,NMR | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-03 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-05
CR270 | Capacity Amendment effective date - Scenario 1 applicable for Capacity amendment request received through SPC No Referral | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: GT, Requested SOQ & SHQ same as Prevailing | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-06
CR270 | Capacity Amendment effective date - Scenario 1 applicable for Capacity amendment request received through SPC No Referral | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: GT, Requested SOQ greater & SHQ same as Prevailing , Ratio b/w 4/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-06
CR270 | Capacity Amendment effective date - Scenario 1 applicable for Capacity amendment request received through SPC No Referral | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: GT, Requested SOQ lesser & SHQ greater as Prevailing , Ratio b/w 4/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-04-06 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-09
CR270 | Capacity Amendment effective date - Scenario 2 applicable for Capacity amendment request received through SPC No Referral to DNO but Referral triggered to IGT | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: IGT, Requested both SOQ & SHQ greater as Prevailing, Ratio b/w 4/16 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR,CRF | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-04-06 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-09
CR270 | Capacity Amendment effective date - Scenario 2 applicable for Capacity amendment request received through SPC No Referral to DNO but Referral triggered to IGT | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: IGT, Requested SOQ is same & SHQ is greater as Prevailing , Ratio b/w 4/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR,CRF | Passed |  | 2018-04-05 | 2018-04-06 |  | 2018-04-05 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-09
CR270 | Capacity Amendment effective date - Scenario 4 applicable for Capacity amendment request received through SPC Requested SOQ/SHQ values greater than that of prevailing SOQ/SHQ and ratio between >16 /<24 No Referral for GT site | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: GT, Requested both SOQ & SHQ greater as Prevailing , Ratio b/w 16/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR | Passed |  | 2018-04-05 | 2018-04-06 |  | 2018-04-05 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-09
CR270 | Capacity Amendment effective date - Scenario 4 applicable for Capacity amendment request received through SPC Requested SOQ/SHQ values greater than that of prevailing SOQ/SHQ and ratio between >16 /<24 No Referral DNO but Referral sent to IGT | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: IGT, Requested both SOQ & SHQ greater as Prevailing , Ratio b/w 16/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR,CRF | Passed |  | 2018-04-06 | 2018-04-09 |  | 2018-04-06 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-09
CR270 | Capacity Amendment effective date - Scenario 5 applicable for Capacity amendment request received through SPC No Referral | Capacity Amendment effective date | Lower Range =73,200 Upper Range = Different for each DNO Class: 2 Site Type: GT, Requested SOQ is greater & SHQ is same as Prevailing , Ratio b/w 16/24 | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC,SCR | Passed |  | 2018-04-06 | 2018-04-09 |  | 2018-04-06 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-09
CR270 | Nomination request received with requested AQ between (>73,200 kWh / <732,000kWh), capacity referral for iGT site sent. However, iGT rejects the referral request, NRF sent with rejection | NRF with rejection | Class : 2 Site Type: IGT | Existing Site AQ between (>73,200 kWh / <732,000kWh) | NOM, NMR,NRF | Passed |  | 2018-04-06 | 2018-04-09 |  | 2018-03-20 | Passed | 2018-04-10 | 2018-04-10 | 2018-03-20
CR270 | Nomination request received with requested AQ between (>73,200 kWh / <732,000kWh), capacity referral for iGT site sent. However, iGT rejects the referral request, NRF sent with rejection | CRF with rejection | Class : 2 Site Type: IGT | Existing Site AQ between (>73,200 kWh / <732,000kWh) | SPC, SCR,CRF | Passed |  | 2018-04-06 | 2018-04-09 |  | 2018-03-20 | Passed | 2018-04-10 | 2018-04-10 | 2018-03-20
CR287 | SCO-SAME SHIPPER scenario of the GSR process. The site is Isolated only (contract is LIVE) and both the shipper and the asset are the same as at the time of isolation. On generation of the GSR Contact, shipper sends a RGMA flow to attach from last removal date + 1 and the necessary back billing will be triggered deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and COM billing for Recon. month | Pre-Golive Isolated Only Class 4, SSP, GT Shipper LI on Site RGMA - ONJOB Meter Install | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-12 | 2018-04-16 |  | 2018-05-16 | Passed | 2018-04-13 | 2018-05-18 | 2018-05-17
CR287 | SCO-SAME SHIPPER scenario of the GSR process. The site is Isolated only (contract is LIVE) and both the shipper and the asset are the same as at the time of isolation. On generation of the GSR Contact, the SAP will automatically attach the same asset for last removal date + 1 and the necessary back billing will be triggered deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and COM billing for Recon. month | Pre-Golive Isolated Only Class 4, SSP, GT Shipper LI on Site Auto Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-12 | 2018-04-16 |  | 2018-05-15 | Passed | 2018-04-16 | 2018-05-18 | 2018-05-16
CR287 | SCN_SAME SHIPPER (MOD 425) The site is Isolated only (pre-go live) and the shipper is the same however the asset is different from the asset at the time of isolation. Shipper attaches the asset within 10 days after the GSR contact generation date from last removal date + 1, the necessary back billing will be triggered with deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and COM billing for Recon. month | Pre-Golive, Isolated Only Class 4, SSP, GT Shipper LI on Site RGMA ONUPD Meter Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-13 | 2018-04-17 |  | 2018-05-08 | Passed | 2018-04-17 | 2018-04-23 | 2018-05-10
CR287 | SCN_SAME SHIPPER (MOD 425) The site is Isolated only (pre-go live) and the shipper is the same however the asset is different from the asset at the time of isolation. Shipper fails to attach the asset within 10 days after the GSR contact generation date. Xoserve user will then manually attach the asset from last removal date + 1, the necessary back billing will be triggered with deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and COM billing for Recon. month | Pre-Golive, Isolated Only Class 4, SSP, GT Shipper LI on Site Manual Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-13 | 2018-04-17 |  | 2018-05-15 | Passed | 2018-04-18 | 2018-05-18 | 2018-05-16
CR287 | PTS-SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre- go live and both the shipper and the asset are the same as at the time of isolation. Shipper will reconfirm the site and attach the asset from last removal date + 1 within 1 month of the contact creation and the necessary back billing will be triggered with deeming commodity adjustment and capacity adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Golive Isolated and Withdrawn Class 4, GT, SSP Confirmation Status = 'LI' RGMA - ONJOB meter installation | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-16 | 2018-04-17 |  | 2018-04-20 | Passed | 2018-04-19 | 2018-05-18 | 2018-05-09
CR287 | PTS-SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre- go live and both the shipper and the asset are the same as at the time of isolation. Shipper do not attach the asset for 10 working days and hence, Meter will auto attach and the necessary back billing will be triggered with deeming commodity adjustment and capacity adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Golive Isolated and Withdrawn Class 4, GT, SSP Confirmation Status = 'CO' Auto Asset Install | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-16 | 2018-05-04 |  | 2018-05-15 | Passed | 2018-05-07 | 2018-05-18 | 2018-05-17
CR287 | SSP Post MOD -SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre- go live and same shipper and the asset is different from the one at isolation. Shipper will confirm the site and attach the asset before stop commodity start date within 1 month of the contact creation and the necessary back billing will be triggered with deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Golive Isolated and Withdrawn Class 4, GT, SSP Confirmation Status = 'CF' RGMA - ONJOB meter install | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-17 | 2018-05-04 |  | 2018-05-03 | Passed | 2018-05-07 | 2018-05-11 | 2018-05-09
CR287 | SSP Post MOD -SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre- go live and same shipper and the asset is different from the one at isolation. Shipper will confirm the site and attach the asset before stop commodity start date within 1 month of the contact creation and the necessary back billing will be triggered with deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Golive Isolated and Withdrawn Class 4, GT, SSP Confirmation Status = 'CO' RGMA - ONJUPD meter install | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-18 | 2018-04-19 |  | 2018-04-26 | Passed | 2018-04-24 | 2018-05-18 | 2018-05-16
CR287 | SSP Post MOD -SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre- go live and same shipper and the asset is different from the one at isolation. Shipper will confirm the site and attach the asset from stop commodity start date within 1 month of the contact creation and the necessary back billing will be triggered with deeming adjustment from the Stop Commodity effective start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Golive Isolated and Withdrawn Class 4, GT, SSP Confirmation Status = 'LI' RGMA - ONUPD meter install | Asset installation date is on the stop commodity start date | NA | Passed |  | 2018-04-18 | 2018-05-04 |  | 2018-05-08 | Passed | 2018-05-07 | 2018-05-18 | 2018-05-16
CR287 | Non GSR Site and No CMS contact, the site is Isolated pre- go live, asset install received for date before stop commodity start date. Commodity Adjustment should be triggered from the start of stop commodity start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Go Live, Non GSR Isolated Only Class 4, GT, SSP Shipper LI on Site RGMA ONUPD Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-24 | Passed | 2018-04-26 | 2018-05-02 | 2018-05-03
CR287 | Non GSR Site and No CMS contact, the site is Isolated and withdrawn pre- go live, Shipper sends a confirmation and RGMA asset install received for date before stop commodity start date. Adjustment should be triggered from the start of stop commodity start date | Amendment billing for BB Period and CAP/COM billing for Recon. month | Pre-Go Live, Non GSR Isolated & Withdrawn Class 4, GT, SSP Confirmation Status = 'CO' RGMA ONJOB Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-04-23 | 2018-04-25 |  | 2018-04-27 | Passed | 2018-04-27 | 2018-05-18 | 2018-05-17
CR292 | MPRNs input file is being processed in BW | Input file processed successfully in BW | MPRNs input file is being processed in BW |  | NA | Passed |  | 2018-03-19 | 2018-03-20 |  | 2018-03-14 | Passed | 2018-03-21 | 2018-03-21 | 2018-03-20
CR292 | XDO File is being generated with all input data | XDO file generated with complete MPRNs as per Input list | XDO File is being generated with all input data |  | NA | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-14 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-20
CR292 | XDO file is split after 1 Million records | XDO Files are split after 1 million records | XDO Files are split after 1 million records |  | NA | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-14 | Passed | 2018-03-23 | 2018-03-23 | 2018-03-20
CR251 | 2A.1 - Count of Est reads for individual month by Shipper & Class 2A.1 - Count of check reads for individual month by Shipper & Class | 2A.1 - Count of Est reads for individual month by Shipper & Class 2A.1 - Count of check reads for individual month by Shipper & Class | 2A.1 - Count of Est reads for individual month by Shipper & Class 2A.1 - Count of check reads for individual month by Shipper & Class | NA | NA | Passed |  | 2018-04-30 | 2018-05-01 |  | 2018-05-04 | Passed | 2018-05-02 | 2018-05-16 | 2018-05-17
CR251 | 2A.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | 2A.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | 2A.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | NA | NA | Passed |  | 2018-04-30 | 2018-05-01 |  | 2018-05-01 | Passed | 2018-05-02 | 2018-05-02 | 2018-05-09
CR251 | 2A.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | 2A.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | 2A.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | NA | NA | Passed |  | 2018-05-01 | 2018-05-02 |  | 2018-05-01 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-15
CR251 | 2A.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | 2A.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | 2A.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | NA | NA | Passed |  | 2018-05-01 | 2018-05-02 |  | 2018-05-02 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-15
CR251 | 2A.5 – Percentage of Read Performance by Month, Shipper & Class. | 2A.5 – Percentage of Read Performance by Month, Shipper & Class. | 2A.5 – Percentage of Read Performance by Month, Shipper & Class. | NA | NA | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-10 | Passed | 2018-05-04 | 2018-05-16 | 2018-05-18
CR251 | 2A.6 – Percentage of Reads where logic check* failed as a % of submitted readings | 2A.6 – Percentage of Reads where logic check* failed as a % of submitted readings Tolerance Failue due to incorrect application of the market breaker/override flag | 2A.6 – Percentage of Reads where logic check* failed as a % of submitted readings Tolerance Failue due to incorrect application of the market breaker/override flag | NA | NA | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-02 | Passed | 2018-05-04 | 2018-05-04 | 2018-05-09
CR251 | 2A.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | 2A.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | 2A.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | NA | NA | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-10 | Passed | 2018-05-08 | 2018-05-16 | 2018-05-15
CR251 | 2A.8 – Count of AQ Corrections by reason code, Month & Shipper | 2A.8 – Count of AQ Corrections by reason code, Month & Shipper | 2A.8 – Count of AQ Corrections by reason code, Month & Shipper | NA | NA | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-01 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-15
CR251 | 2A.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | 2A.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | 2A.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | NA | NA | Passed |  | 2018-05-04 | 2018-05-07 |  | 2018-05-02 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-08
CR251 | 2A.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | 2A.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | 2A.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | NA | NA | Passed |  | 2018-05-04 | 2018-05-07 |  | 2018-05-02 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-08
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. MRA will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response Network user should download the MJO file first. GT Meter point | NA | NA | Passed |  | 2018-03-14 | 2018-03-15 |  | 2018-03-19 | Passed | 2018-03-16 | 2018-03-16 | 2018-03-20
XRN4248 | Validate the Report Title ,Header, Footer ,Format and layout, Export the report in default format and in (Pdf,Excel) formats | BW | Report name: • Rpt_id_1251_HSE_Quarterly_Smart_Metering_National_Level_Report |  |  | Passed |  | 2018-03-14 | 2018-03-16 |  | 2018-04-11 | Passed | 2018-03-19 | 2018-03-19 | 2018-04-17
XRN4248 | Enter T-Code SE16N and search for table EASTL,EGERR,ETVP and validate the data with BW | BW | Report name: • Rpt_id_1252_HSE_Historic_Smart_Metering |  |  | Passed |  | 2018-03-16 | 2018-03-16 |  | 2018-04-11 | Passed | 2018-03-19 | 2018-03-19 | 2018-04-17
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response GT Meter point | NA | NA | Passed |  | 2018-03-15 | 2018-03-16 |  | 2018-03-14 | Passed | 2018-03-17 | 2018-03-17 | 2018-03-15
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by MRA. Network will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should download the MJO file first. IGT Meter point | NA | NA | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-20 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-26
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. MRA will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response IGT user should download the MJO file first. IGT Meter point | NA | NA | Passed |  | 2018-03-16 | 2018-03-19 |  | 2018-03-20 | Passed | 2018-03-20 | 2018-03-20 | 2018-03-26
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Networks should be able to see the files uploaded by MRAs in file search | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should upload MJI. Network should be able perform file search for its MRA MPRS GT Meter point | NA | NA | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-19 | Passed | 2018-03-21 | 2018-03-21 | 2018-03-20
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. IGT should be able to see the files uploaded by MRAs in file search | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should upload MJI. IGT should be able perform file search for the MPRs under its MRAs iGT Meter point | NA | NA | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-16 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-16
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Xoserve should be pushing the contact to Networks if they are acting as MRAs Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status." Xoserve should be pushing the contact to Networks if they are acting as MRAs | CMS | Valid MUR file should be present MJI file should contain invalid record and contact should be paused to Xoserve queue GT Meter point | NA | NA | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-21 | Passed | 2018-03-23 | 2018-03-23 | 2018-03-26
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Xoserve should be pushing the contact to IGT if they are acting as MRAs Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status." Xoserve should be pushing the contact to Networks if they are acting as MRAs | CMS | Valid MUR file should be present MJI file should contain invalid record and contact should be paused to Xoserve queue IGT Meter point | NA | NA | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-21 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-22
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. A child iGT MRA downloads only its MUR details and the rest is downloaded by the parent iGT | CMS | Valid MUR file should be present IGT Meter point | NA | NA | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-21 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-26
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. The entire file is downloaded by the parent iGT. However some of the MJIs are uploaded by the child MRAs and some uploaded by parent iGT | CMS | Valid MUR file should be present IGT Meter point | NA | NA | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-21 | Passed | 2018-03-27 | 2018-03-27 | 2018-03-27
COR3386 | MUR file is loaded and the contacts are generated. The parent MRA EMR logs onto CMS and they are able to download the data for the iGTs - ESP,BGC,ELK,HPN |  |  |  |  | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-27 | Passed | 2018-03-27 | 2018-03-27 | 2018-03-26
COR3386 | "MUR file is loaded and the contacts are generated. The parent MRA GFM logs onto CMS and they are able to download the data for the Networks - TGT & GT5 " |  |  |  |  | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-23 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-26
CR359 | SIT_ADD_01_01 | Valid data should be provided through UI screen by Shipper for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. | "1. Shipper should login to Xoserve system by giving valid credentials in login page. 2. Click on ""CMS "" link 3.Click on ""ADD"" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. ""5. User clicks on """"Close"""" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. "" 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on ""Download"" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on ""Browse"" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status " 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | "Shipper should be able to see ""CMS Home"" Screen. CMS Home page should be displayed. ADD screen should be displayed. ""CRN should be generated with the message """"Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"""" With """"Close"""" button."" CMS Home page should be displayed. CMS Home page should be displayed. ""All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text """"File has downloaded successfully """" should be displayed."" VAD and REA files should be generated. """"""<Filename >.VAD is uploaded successfully"""" / <Filename >.REA is uploaded successfully """" should be displayed on screen. Files should be placed in shared area."" Site type should be Single Contact status should be updated as AWAC. " "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-22 | Passed | 2018-03-24 | 2018-03-24 | 2018-03-28
CR359 | SIT_ADD_01_02 | Valid data should be provided through UI screen by Shipper for successful logging of contact for iGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. | 1. Shipper should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Shipper should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-19 | 2018-03-20 |  | 2018-03-22 | Passed | 2018-03-21 | 2018-03-21 | 2018-03-28
CR359 | SIT_ADD_01_03 | Valid data should be provided through UI screen by Xoserve for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. | 1. Xoserve should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Xoserve should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-22 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-28
CR359 | SIT_ADD_01_04 | Valid data should be provided through UI screen by IGT for successful logging of contact for IGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. | 1. IGT should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | IGT should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-20 | 2018-03-21 |  | 2018-03-22 | Passed | 2018-03-22 | 2018-03-22 | 2018-03-28
CR359 | SIT_ADD_01_05 | Valid data should be provided through UI screen by Network for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. | 1.Network should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Shipper should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-21 | Passed | 2018-03-23 | 2018-03-23 | 2018-03-28
CR359 | SIT_ADD_01_06 | Valid data should be provided through UI screen by Xoserve for successful logging of contact for IGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. | 1. Xoserve should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Xoserve should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-21 | 2018-03-22 |  | 2018-03-21 | Passed | 2018-03-23 | 2018-03-23 | 2018-03-28
CR359 | SIT_UNC_01_01 | Valid data should be provided through UI screen by XOSERVE for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool. Response files, VAD, REA uploaded through UI Screen. For the CRN generated, status in CMS should be closed as valid. | 1. XOSERVE should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "UNC" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | XOSERVE should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-23 | Passed | 2018-03-26 | 2018-03-26 | 2018-03-29
CR359 | SIT_UNC_01_02 | Valid data should be provided through UI screen by XOSERVE for successful logging of contact for iGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. For the CRN generated, status in CMS should be closed as valid. | 1. XOSERVE should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "UNC" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | XOSERVE should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-22 | 2018-03-23 |  | 2018-03-23 | Passed | 2018-03-27 | 2018-03-27 | 2018-03-29
CR359 | SIT_UNC_01_03 | Valid data should be provided through UI screen by Shipper for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. | 1. Shipper should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "UNC" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Shipper should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-23 | 2018-03-26 |  | 2018-03-23 | Passed | 2018-03-27 | 2018-03-27 | 2018-03-28
CR359 | SIT_UNC_01_04 | Valid data should be provided through UI screen by Shipper for successful logging of contact for IGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. + | 1. Shipper should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "UNC" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Shipper should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-23 | 2018-03-26 |  | 2018-03-23 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-28
CR359 | SIT_UNC_01_05 | Valid data should be provided through UI screen by Network Operator for successful logging of contact. Address should be checked for duplication, along with MPRN status and site type in UK Link. BTI file should be Downloaded; Response files, VAD & REA should be generated. Files should be uploaded through UI Screen; should again be checked for duplication. Duplicate records should be rejected. All the contacts which are in AMNC status should be fetched and the Address and MPRN should be created on UK Link. | 1. Network Operator should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS" link 3.Click on "UNC" contact code among the table of contact codes. "4. Logged in user should enter all valid data and click on Submit button. (No Open request exist)" "5. User clicks on ""Close"" button in the success msg. " 10. Run the batch job "ADDCR00SS.KSH" . 11.Run ARS file upload job. 12. Check CMS Database for CRN status | Network Operator should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with a pop up message stating ""Contact Successfully logged. Make a note of following detail. Thank You Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>""" CMS Home page should be displayed. "All the AWAC and AMNC contacts should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as valid. | NA | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-26 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-28
CR359 | SIT_UNC_01_06 | Valid data should be provided through UI screen by iGT for successful logging of contact. Address should be checked for duplication, along with MPRN status and site type in UK Link. BTI file should be Downloaded; Response files, VAD & REA should be generated. Files should be uploaded through UI Screen; should again be checked for duplication. Duplicate records should be rejected. All the contacts which are in AMNC status should be fetched and the Address and MPRN should be created on UK Link. | 1. iGT should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS" link 3.Click on "UNC" contact code among the table of contact codes. "4. Logged in user should enter all valid data and click on Submit button. (No Open request exist)" "5. User clicks on ""Close"" button in the success msg. " 10. Run the batch job "ADDCR00SS.KSH" . 11.Run ARS file upload job. 12. Check CMS Database for CRN status | Network Operator should be able to see "CMS Home" Screen. CMS Home page should be displayed. UNC screen should be displayed. "CRN should be generated with a pop up message stating ""Contact Successfully logged. Make a note of following detail. Thank You Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>""" CMS Home page should be displayed. "All the AWAC and AMNC contacts should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as valid. | NA | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-27 | Passed | 2018-03-28 | 2018-03-28 | 2018-03-28
CR359 | SIT_ADD_02_01 | Valid data should be provided through UI screen by Xoserve for successful logging of contact for GT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. | 1. Xoserve should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Xoserve should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-27 | Passed | 2018-03-29 | 2018-03-29 | 2018-04-04
CR359 | SIT_ADD_02_02 | Valid data should be provided through UI screen by Xoserve for successful logging of contact for iGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. | 1. Xoserve should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Xoserve should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. The 'Proposed Address' is created in SAP UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-27 | Passed | 2018-03-29 | 2018-03-29 | 2018-04-04
CR359 | SIT_ADD_02_03 | Valid data should be provided through UI screen by Xoserve for successful logging of contact for iGT meter point Site ownership data, meter point status and address should be checked in UK Link. BTI file should be Downloaded for verification of address on royal mail batch tool.Response files, VAD, REA uploaded through UI Screen. | 1. Xoserve should login to Xoserve system by giving valid credentials in login page. 2. Click on "CMS " link 3.Click on "ADD" contact code among the table of contact codes. 4. Logged in user should enter all valid data and click on Submit button. "5. User clicks on ""Close"" button in the success msg. Note: Site ownership data, meter point status and address should be checked in UK Link. " 6. Login to CMS-System with valid credentials of process user (Xoserve). 7. User selects BTI file from drop down list and clicks on "Download" button. 8. wait for the BTI to be processed offline for verifying addresses 9.Navigate to Upload File screen. Click on "Browse" and select VAD & REA files to be uploaded. 10.Verify Site type 11. Verify contacts status 12. Run the batch job "ACRGN00Ss.KSH" . 13.Receive response ARS file and Run ARS file upload job. 14. Check CMS Database for CRN status for records in ARS file. | Xoserve should be able to see "CMS Home" Screen. CMS Home page should be displayed. ADD screen should be displayed. "CRN should be generated with the message ""Contact logged Successfully. Contact Reference Number: <CRN> Logging Time: <Time at which contact is logged>"" With ""Close"" button." CMS Home page should be displayed. CMS Home page should be displayed. "All CRNs in ADRT status should be picked up and BTI file should be generated which should be stored in Shared area. Status should be updated to ABVT. Text ""File has downloaded successfully "" should be displayed." VAD and REA files should be generated. """<Filename >.VAD is uploaded successfully"" / <Filename >.REA is uploaded successfully "" should be displayed on screen. Files should be placed in shared area." Site type should be Single Contact status should be updated as AWAC. "All the AWAC contacts (with CRN and verified address details) written in to ACR file and should be sent to UK link. The Sub Building Name is removed from SAP UK link should process the ACR file and should send response back in ARS file to CMS." "Batch job should be successful. " Contact status should be Closed as Valid and Premises details in UKLink should be amended with the new address details for success records. | NA | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-28 | Passed | 2018-03-30 | 2018-03-30 | 2018-04-04
CR359 | SIT_ADD_03_01 |  | ` | Proposed address | Address in SAP | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-28 | Passed | 2018-03-30 | 2018-03-30 | 2018-04-04
CR359 | SIT_ADD_03_02 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-03-29 | 2018-03-30 |  | 2018-03-29 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-04
CR359 | SIT_ADD_03_03 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-03-29 | 2018-03-30 |  | 2018-03-29 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-04
CR359 | SIT_ADD_03_04 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-03-30 | 2018-03-31 |  | 2018-04-02 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-04
CR359 | SIT_ADD_03_05 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-03-30 | 2018-03-31 |  | 2018-04-02 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-04
CR359 | SIT_ADD_03_06 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-04
CR359 | SIT_ADD_03_07 |  | Column | Proposed address | Address in SAP | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-04
CR367 | SIT_MIV_01_01 | CMS rejected readings should be sent in the must read submission file (MUP) to UK Link | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3. MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). "6. MRA user upload the file (MJI, LTI, RJI) In Contact Management>File Upload screen, Select the 'File Type'(MJI, LTI, RJI) and click on 'Upload File' button" 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button. MJI file should contain incorrect record. "9.Upload the file UK link (Run batch Job) " 10. Trigger MDP file loading to process MDP response file | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. Contact should not get rejected and CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should reject the contact and error message will be sent to CMS in MDP file. " Contact should be sent Xoserve desk user to process further |  | Passed |  | 2018-04-30 | 2018-05-01 |  | 2018-04-25 | Passed | 2018-05-02 | 2018-05-02 | 2018-04-26
CR367 | SIT_MIV_01_02 | CMS rejected readings should be sent in the must read submission file (MUP) to UK Link | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3. MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). "6.MRA user upload the file (MJI, LTI, RJI) In Contact Management>File Upload screen, Select the 'File Type'(MJI, LTI, RJI) and click on 'Upload File' button" 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button. MJI file should contain incorrect record. "9.Upload the file UK link (Run batch Job) " 10. Trigger MDP file loading to process MDP response file | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. Contact should not get rejected and CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should reject the contact and error message will be sent to CMS in MDP file. " Contact should be sent Xoserve desk user to process further |  | Passed |  | 2018-04-30 | 2018-05-01 |  | 2018-04-25 | Passed | 2018-05-02 | 2018-05-02 | 2018-04-26
CR367 | SIT_MIV_02_01 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard ‘0’ readings on to the MIV file for Must Read invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3. MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). "6.MRA user upload the file (MJI, LTI, RJI) In Contact Management>File Upload screen, Select the 'File Type'(MJI, LTI, RJI) and click on 'Upload File' button" 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system. This has been passed to our Billing Department for invoicing." "CRN which are in FWDS and CLRD status will be picked up and MIV file will be sent to SAP for billing process. '0' reading CRN should not be sent in MIV file" |  | Passed |  | 2018-05-01 | 2018-05-02 |  | 2018-04-30 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-02
CR367 | SIT_MIV_02_02 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from iGT (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard ‘0’ readings on to the MIV file for Must Read invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3.MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). "6.MRA user upload the file (MJI, LTI, RJI) In Contact Management>File Upload screen, Select the 'File Type'(MJI, LTI, RJI) and click on 'Upload File' button" 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system. This has been passed to our Billing Department for invoicing." iGT MPRs not present in the MIV file |  | Passed |  | 2018-05-01 | 2018-05-02 |  | 2018-04-30 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-01
CR367 | SIT_MIV_03_01 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard NULL readings on to the MIV file for Must Read invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3.MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system. This has been passed to our Billing Department for invoicing." "CRN which are in FWDS and CLRD status will be picked up and MIV file will be sent to SAP for billing process. CRN having NULL reading should not be sent in MIV file" |  | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-02 | Passed | 2018-05-04 | 2018-05-04 | 2018-05-08
CR367 | SIT_MIV_03_02 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from iGT (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard NULL readings on to the MIV file for Must Read invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of iGT to bulk download contacts (MJO, LTO, RJO) "3.iGT user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of iGT to bulk upload the response to MUR contacts(MJI, LTI and RJI files). "6.iGT user upload the file (MJI, LTI, RJI) In Contact Management>File Upload screen, Select the 'File Type'(MJI, LTI, RJI) and click on 'Upload File' button" 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. iGT should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD iGT should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system. This has been passed to our Billing Department for invoicing." iGT MPRs are not present in the MIV file |  | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-02 | Passed | 2018-05-04 | 2018-05-04 | 2018-05-04
CR367 | SIT_MIV_04_01 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard any CRNs which were FWDS in the last month and auto closed (NATO > CLRD) in 40 Business days in the current month from the must reads invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3.MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job 12. Trigger auto closure Job. 13. MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system. This has been passed to our Billing Department for invoicing." "CRN which are in FWDS status will be picked up and MIV file will be sent to SAP for billing process. CRN having NULL reading should not be sent in MIV file" Contact should be closed as valid Contact which were sent in MIV earlier should not be present in the MIV file. |  | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-02 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-08
CR367 | SIT_MIV_04_01 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard any CRNs which were FWDS in the last month and auto closed (NATO > CLRD) in 40 Business days in the current month from the must reads invoice | 1.Process MUR file by running 'MURPR00Ss.KSH' batch job. 2.Login to CMS with valid credentials of MRA to bulk download contacts (MJO, LTO, RJO) "3.MRA user download the file (MJO, LTO, RJO) In Contact Management>File Download screen, Select the 'File Type (MJO, LTO, RJO) and click on 'Download' button" 4.On click of 'Save As' 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 5.Login to CMS with valid credentials of MRA to bulk upload the response to MUR contacts(MJI, LTI and RJI files). 7.Select the file and click on 'Browse' button 8.Click on 'Upload' button "9.Upload the file UK link (Run batch Job) Execute <> batch job to upload the reads SAP" 10.Receive response MDP from SAP and trigger "MDPFL00Ss.KSH" 11. Run MIV file generation job 12. Trigger auto closure Job. 13. MIV file generation job | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. MRA should successfully login to CMS Save As' pop-up window should be displayed. User should be able to save file successfully. CRN status should be set to MJOD/LTOD/RJOD MRA should successfully login to CMS "Upload File' pop-up window should be displayed with following fields: 'Browse', 'Upload' and 'Close' button" User should be able to select file (MJI, LTI, RJI) "File should be uploaded successfully and same should be updated in incoming_file table. CRN status should be set to AWRD and MUP file will be sent to SAP for read upload." "System should successfully update the reads on UKLink. Contact status should be 'AWRD' " Response should be received. Reads Accepted by UK link and Contact should be closed as Valid. Resolution text should be "I am pleased to inform you that a read has been successfully uploaded to our source system." IGT MPRN is not available in the MIV file Contact should be closed as valid IGT MPRN is not available in the MIV file |  | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-02 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-08 | The point is to prove that anyting that was on the MIV in month 1 as it was at FWDS, does not appear on the MIV in month 2 when it is at CLRD. This just shows inclusion of FWDS in one month, need to see it not on an MIV the following month when CLRD
CR273 | Direct confirmation Request received with multiple S84 segments containing reusable (re-mapped) priority codes, request should be accepted with old priority codes deleted and new effective from confirmation effective date (Re-used Need Codes: 4, 8, 9,10,12, 14,15,19,22) | LIVE Confirmations | Class: 4 Site Type: GT AQ < 73200 Existing Site | Site with existing special needs along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - No PSR_CODE_EXPIRY_DATE populated - Language (free text) | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-27 | Passed | 2018-03-28 | 2018-03-29 | 2018-04-05 | test results are as expected so therefore passes assurance
CR273 | Direct confirmation Request received with multiple S84 segments containing reusable (re-mapped) priority codes, request should be accepted with old priority codes deleted and new effective from confirmation effective date (Re-used Need Codes: 4, 8, 9,10,12, 14,15,19,22) | LIVE Confirmations | Class: 4 Site Type: IGT AQ < 73200 Existing Site | Site with existing special needs along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - No PSR_CODE_EXPIRY_DATE populated - Language (free text) | CNF, CFR, TRF, IDL/EWS/EWS | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-28 | Passed | 2018-03-28 | 2018-03-28 | 2018-04-24 | email sent to Sib to confirm Action codes in the IDL file are updating correctly
CR273 | Direct confirmation Request received with multiple S84 segments containing combination of No-Match and reusable need codes, request should be accepted (Re-used: 04, 08,09,10,12,14,15,19,22 No Match : 03,17,18,20) | LIVE Confirmations | Class: 4 Site Type: GT AQ < 73200 Existing Site | Request combination of New/Existing and redundant need codes along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE populated - Language combination of No-Match and Re-usable | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-03-26 | 2018-03-27 |  | 2018-03-27 | Passed | 2018-03-28 | 2018-03-28 | 2018-04-09
CR273 | Direct confirmation Request received with multiple S84 segments containing combination of No-Match and reusable need codes, request should be accepted (Re-used: 04, 08,09,10,12,14,15,19,22 No Match : 03,17,18,20) | LIVE Confirmations | Class: 4 Site Type: IGT AQ < 73200 Existing Site | Request combination of New/Existing and redundant need codes along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE populated - Language combination of No-Match and Re-usable | CNF, CFR, TRF, IDL/EWS | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-03-28 | Passed | 2018-03-29 | 2018-03-29 | 2018-04-06 | email sent to Rajeev
CR273 | Direct confirmation Request received with multiple S84 segments containing combination of new and reusable need codes, request should be accepted (Re-Used – 04, 08,09,10,12,14,15,19,22 New– 01, 02, 23 to 34) | LIVE Confirmations | Class : 3, Site Type : GT AQ < 73200, Brownfield | No Special need codes on the site along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE not populated for priority codes except 29, 32, 33, 34 - Language (allowable values?) - Alternate priority service contact name - Alternate priority service contact phone number provided | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-04-04 | Passed | 2018-04-03 | 2018-04-03 | 2018-04-27 | Production defect 969 is to be fixed 04/05 ( incrrect values in TRF )
CR273 | Direct confirmation Request received with multiple S84 segments containing combination of new and reusable need codes, request should be accepted (Re-Used – 04, 08,09,10,12,14,15,19,22 New– 01, 02, 23 to 34) | LIVE Confirmations | Class : 3, Site Type : GT AQ < 73200, Greenfield | No Special need codes on the site along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE not populated for priority codes except 29, 32, 33, 34 - Language (allowable values?) - Alternate priority service contact name - Alternate priority service contact phone number provided | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-03-27 | 2018-03-28 |  | 2018-04-04 | Passed | 2018-04-03 | 2018-04-03 | 2018-03-12 | The MSN in the CFR S75 record was showing as "" but " " in TRF. This was confirmed as being as per production, see email attached. The AQ timeslices were created for 28.02.2018 to 31.03.2019 and 01.04.2019 to 31.03.2020. This is a known defect.
CR273 | Direct confirmation Request received with multiple S84 segments containing combination of new and reusable need codes, request should be accepted (Re-Used – 04, 08,09,10,12,14,15,19,22 New– 01, 02, 23 to 34) | LIVE Confirmations | Class : 3, Site Type : iGT AQ < 73200, Greenfield | No Special need codes on the site along with - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE not populated for priority codes except 29, 32, 33, 34 - Language (allowable values?) - Alternate priority service contact name - Alternate priority service contact phone number provided | CNF, CFR, TRF, IDL/EWS | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-04-04 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-19 | Data has been confirmed by Wipro to be correct - B43
CR273 | Direct Confirmation request received with Not-Used need codes post implementation, request should be accepted and details should be stored in SAP (Not Used – 05,06,07,11,13,16,21) | Live Confirmation | Class 4, GT AQ < 73200, Existing site | Site with existing priority code = 99 - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - Language (allowable values?) - PSR_CODE_EXPIRY_DATE populated | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-28 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-06 | Following confirmation of the codes updated in the EWS assurance passes
CR273 | Direct Confirmation request received with Not-Used need codes post implementation, request should be accepted and details should be stored in SAP (Not Used – 05,06,07,11,13,16,21) | Live Confirmation | Class 4, IGT AQ < 73200, Existing site | Site with existing priority code = 99 - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - Language (allowable values?) - PSR_CODE_EXPIRY_DATE populated | CNF, CFR, TRF, IDL/EWS | Passed |  | 2018-03-28 | 2018-03-29 |  | 2018-03-29 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-13 | Clarification required over the read/read date in MRI file
CR273 | Contact Amendment received in CNC with S81 & S82 both. Multiple priority codes received with combination of re-usable and new codes, request should be accepted (Re-Used – 04, 08,09,10,12,14,15,19,22 New– 01, 02, 23 to 34) | Contact Amendment Live | Class : 4 AQ < 73200 Site Type : GT | Site with existing priority codes (combination of not used codes & no-match) along with request: - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE for 29, 32, 33, 34 - Language (allowable values?) | CNC, CNR, EDL/EWS | Passed |  | 2018-03-29 | 2018-03-30 |  | 2018-03-30 | Passed | 2018-04-04 | 2018-04-04 | 2018-04-16
CR273 | Contact Amendment received in CNC with S81 & S82 both. Multiple priority codes received with combination of re-usable and new codes, request should be accepted (Re-Used – 04, 08,09,10,12,14,15,19,22 New– 01, 02, 23 to 34) | Contact Amendment Live | Class : 4 AQ < 73200 Site Type : IGT | Site with existing priority codes (combination of not used codes & no-match) along with request: - CONSENT_TO_SHARE_DATA_OBTAINED ‘Y’ - PSR_CODE_EXPIRY_DATE for 29, 32, 33, 34 - Language (allowable values?) | CNC, CNR, IDL/EWS | Passed |  | 2018-03-29 | 2018-03-31 |  | 2018-04-03 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-17
CR273 | Contact Amendment received in CNC with S82 only. Multiple priority codes received with combination of Not Used and New need codes, request should be accepted (New – 01, 02, 23 to 34 Not Used–05,06,07,11,13,16,21) | Contact Amendment Live | Site Type : GT Class 4 | Site with No priority codes Multiple S84 received in a single file with combination of New and not used need codes along with - Consent Code ‘Y’ - No PSR_CODE_EXPIRY_DATE populated - Alternate priority service contact name - Alternate priority service contact phone number provided | CNC, CNR, EDL/EWS | Passed |  | 2018-03-29 | 2018-04-01 |  | 2018-03-29 | Passed | 2018-04-05 | 2018-04-05 | 2018-04-04
CR273 | Contact Amendment received in CNC with S82 only. Multiple priority codes received with combination of Not Used and New need codes, request should be accepted (New – 01, 02, 23 to 34 Not Used–05,06,07,11,13,16,21) | Contact Amendment Live | Site Type : iGT Class 4 | Site with No priority codes Multiple S84 received in a single file with combination of New and not used need codes along with - Consent Code ‘Y’ - No PSR_CODE_EXPIRY_DATE populated - Alternate priority service contact name - Alternate priority service contact phone number provided | CNC, CNR, IDL/EWS | Passed |  | 2018-03-30 | 2018-04-02 |  | 2018-04-02 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-17
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes but one of the Consent Flag as ‘N’, request should be with rejected with code CTT00044 under S84 S72 | Request Rejection | Site Type : GT Class 4 | - Consent Code ‘N’ for one of the S84 segment - PSR_CODE_EXPIRY_DATE populated | CNF, CFR | Passed |  | 2018-03-31 | 2018-04-02 |  | 2018-04-02 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-12
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes but one of the Consent Flag as ‘N’, request should be with rejected with code CTT00044 under S84 S72 | Request Rejection | Site Type : IGT Class 4 | - Consent Code ‘N’ for one of the S84 segment - PSR_CODE_EXPIRY_DATE populated | CNC, CNR | Passed |  | 2018-04-01 | 2018-04-02 |  | 2018-04-02 | Passed | 2018-04-06 | 2018-04-06 | 2018-04-12
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes with Consent Flag as ‘Y’ but PSR Expiry date less than or equal to contact effective date, request should be rejected with code CTT00033 under S84S72 | 1. Request Rejection | Site Type : GT Class 4 | 1. Run for CNF with S82 having PSR_CODE_EXPIRY_DATE less than to contact effective date | CNF, CFR | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-02 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-12
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes with Consent Flag as ‘Y’ but PSR Expiry date less than or equal to contact effective date, request should be rejected with code CTT00033 under S84S72 | 1. Request Rejection | Site Type : GT Class 4 | 1. Run for CNC with S82 having PSR_CODE_EXPIRY_DATE less than to contact effective date | CNC, CNR | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-03 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-12
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes with Consent Flag as ‘Y’ but PSR Expiry date equal to contact effective date, request should accepted | Request acceptance and contact effective date | Site Type : GT Class 4 | 2. Run for CNF with Expiry date Equal to effective date, request should be accepted | CNF, CFR, TRF, EDL/EWS | Passed |  | 2018-04-02 | 2018-04-03 |  | 2018-04-04 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-19
CR273 | Direct confirmation or CNC Request received with multiple S84 segments containing combination of new and re-usable need codes with Consent Flag as ‘Y’ but PSR Expiry date equal to contact effective date, request should accepted | Request acceptance and contact effective date | Site Type : GT Class 4 | 2. Run for CNC with Expiry date Equal to effective date, request should be accepted | CNC, CNR, EDL/EWS | Passed |  | 2018-04-03 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-10 | 2018-04-10 | 2018-04-17
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : GT Class 4 | CNF Files with one of the below fields not populated 3. PSR code expiry date | CNF, CFR | Passed |  | 2018-04-04 | 2018-04-04 |  | 2018-04-04 | Passed | 2018-04-10 | 2018-04-10 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : iGT Class 4 | CNF Files with one of the below fields not populated 4. ALTERNATE_PRIORITY_SERVICE_CONTACT_NAME | CNF, CFR | Passed |  | 2018-04-05 | 2018-04-04 |  | 2018-04-05 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : GT Class 4 | CNF Files with one of the below fields not populated 5. ALTERNATE_PRIORITY_SERVICE_CONTACT_PHONE_NUMBER_1 | CNF, CFR | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-04-04 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : iGT Class 4 | CNF Files with one of the below fields not populated 6. ALTERNATE_PRIORITY_SERVICE_CONTACT_PHONE_NUMBER_2 (if this is provided without phone number 1, request should be rejected) 7. Test for multiple rejections in same file | CNF, CFR | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-04-04 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : GT Class 4 | CNC Files with one of the below fields not populated 3. PSR code expiry date | CNC, CNR | Passed |  | 2018-04-04 | 2018-04-05 |  | 2018-04-04 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : iGT Class 4 | CNC Files with one of the below fields not populated 4. ALTERNATE_PRIORITY_SERVICE_CONTACT_NAME | CNC, CNR | Passed |  | 2018-04-05 | 2018-04-06 |  | 2018-04-05 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-11
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : GT Class 4 | CNC Files with one of the below fields not populated 5. ALTERNATE_PRIORITY_SERVICE_CONTACT_PHONE_NUMBER_1 | CNC, CNR | Passed |  | 2018-04-05 | 2018-04-06 |  | 2018-04-05 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-06
CR273 | Request received from Portal for deleting the site works reference for an existing site under DN portfolio. In addition, once deletion is successful, go to ‘Meter Asset selection’ display to validate the successful update | Request Rejection | Site Type : iGT Class 4 | CNC Files with one of the below fields not populated 6. ALTERNATE_PRIORITY_SERVICE_CONTACT_PHONE_NUMBER_2 (if this is provided without phone number 1, request should be rejected) 7. Test for multiple rejections in same file | CNC, CNR | Passed |  | 2018-04-05 | 2018-04-06 |  | 2018-04-05 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-11
CR273 | Direct Confirmation or CNC request received with multiple priority codes but Language not populated with minimum 3 characters for one of the record. Request should be rejected with code CTT00045 (S83S72) | Request Rejection | Site Type : GT Class 4 | - Minimum 3 characters not provided for Language - Language Allowable (free text) | CNF, CFR | Passed |  | 2018-04-09 | 2018-04-10 |  | 2018-04-09 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-12
CR273 | Direct Confirmation or CNC request received with multiple priority codes but Language not populated with minimum 3 characters for one of the record. Request should be rejected with code CTT00045 (S83S72) | Request Rejection | Site Type : IGT Class 4 | - Space should be rejected | CNC, CNR | Passed |  | 2018-04-09 | 2018-04-10 |  | 2018-04-09 | Passed | 2018-04-16 | 2018-04-16 | 2018-04-12
CR273 | Direct confirmation or CNC request received with S83 language provided but no S84 received, request should be accepted and store the language | Acceptance response | Site Type GT Class 4 AQ < 73200 | Request without S84: 1. CONTACT_GENERAL_PRIORITY_SERVICE_NOTES populated along with Language 2. Alternate priority service contact name 3. Alternate priority service contact phone number provided | CNF, CFR | Passed |  | 2018-04-09 | 2018-04-10 |  | 2018-04-10 | Passed | 2018-04-16 | 2018-04-16 | 2018-04-13
CR273 | Direct confirmation or CNC request received with S83 language provided but no S84 received, request should be accepted and store the language | Acceptance response | Site Type GT Class 4 AQ < 73200 | Request without S84: 1. CONTACT_GENERAL_PRIORITY_SERVICE_NOTES populated along with Language 2. Alternate priority service contact name 3. Alternate priority service contact phone number provided | CNC, CNR | Passed |  | 2018-04-10 | 2018-04-11 |  | 2018-04-10 | Passed | 2018-04-17 | 2018-04-17 | 2018-04-13
CR273 | Run EDL for scenarios 1 to 6, all the updates should be captured within EDL with new fields included in file format for GT sites - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 | Files successful in AMT | Class : 4 Site Type : GT AQ < 73200 Existing Site | 1. Valid BP exists without priority codes and Update new Contact with priority codes (B39 segment for old codes - D without priority codes) 2. No existing contacts on site, only N should be sent the new codes, D will not be sent for BP with no existing codes | EDL | Passed |  | 2018-04-10 | 2018-04-11 |  | 2018-04-10 | Passed | 2018-04-17 | 2018-04-17 | 2018-04-18
CR273 | Run EDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B39 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT, AQ < 73200 Existing Site | 1. Site where PSR_Code_Expiry date is reached for one of the codes and with other priority codes as valid | EDL | Passed |  | 2018-04-10 | 2018-04-11 |  | 2018-04-11 | Passed | 2018-04-17 | 2018-04-17 | 2018-04-18
CR273 | Run EDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B39 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT, AQ < 73200 Existing Site | 2. CNF with PSR expiry date same as that of effective date, all D, N and U records will be sent out in EDL | CNF, CFR, EDL | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-18 | Passed | 2018-04-18 | 2018-04-18 | 2018-04-18
CR273 | Run EDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B39 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT, AQ < 73200 Existing Site | 2. CNC with PSR expiry date same as that of effective date, all D, N and U records will be sent out in EDL | CNC, CNR, EDL | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-20 | Passed | 2018-04-18 | 2018-04-18 | 2018-04-24
CR273 | Run IDL for scenarios 1 to 6, all the updates should be captured within IDL with new fields included in file format for iGT sites - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 | Files successful in AMT | Class : 4 Site Type : iGT AQ < 73200 Existing Site | 1. Dummy BP exists and create a new contact with requested priority codes ( B46 - Only N with priority service code ) | IDL/EWS | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-11 | Passed | 2018-04-18 | 2018-04-18 | 2018-04-19
CR273 | Run IDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : iGT AQ < 73200 Existing Site | 1. Site where PSR_Code_Expiry date is reached for one of the codes and with other priority codes as valid | IDL/EWS | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-04-16 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-20
CR273 | Run IDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : iGT AQ < 73200 Existing Site | 2. CNF with PSR expiry date same as that of effective date, all D, N and U records will be sent out in IDL | CNF, CFR, IDL/EWS | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-04-16 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-20
CR273 | Run IDL for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : iGT AQ < 73200 Existing Site | 2. CNC with PSR expiry date same as that of effective date, all D, N and U records will be sent out in IDL | CNC, CNR, IDL/EWS | Passed |  | 2018-04-12 | 2018-04-13 |  | 2018-04-20 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-20
CR273 | Run EWS for scenarios 1 to 6, all the updates should be captured within EWS with new fields included in file format for GT sites - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 for GT sites | Files successful in AMT | Class : 4 Site Type : GT AQ < 73200 Existing Site | 1. Dummy BP exists and create a new contact with special (action with N with priority code) | EWS | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-17 | Passed | 2018-04-23 | 2018-04-23 | 2018-04-20
CR273 | Run EWS for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT AQ < 73200 Existing Site | Site where PSR_Code_Expiry date is reached for one of the codes and with other priority codes as valid | EWS | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-19 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-20
CR273 | Run EWS for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT AQ < 73200 Existing Site | New CNF request does not have any contact details or CNC received with C37 then the existing contact will be end dated. Old Contact details will be sent in segment E24 with Action U, Priority values will be blank | CNF, CFR, EWS | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-18 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-23
CR273 | Run EWS for a scenario where PSR_CODE_EXPIRY_DATE is reached, B46 segment should be issued with ACTION “U” on the next day of expiry date | Files successful in AMT | Class : 4 Site Type : GT AQ < 73200 Existing Site | CNC with PSR expiry date same as that of effective date, all D, N and U records will be sent out in EWS | CNC, CNR, EWS | Passed |  | 2018-04-16 | 2018-04-17 |  | 2018-04-19 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-24
CR273 | Process CSS file for a SSMP site and check the response CRS file in AMT for SPECIAL_END_USR_CNDTNS_OVERRIDE field to be changed to PRIORITY_SERVICES_CONDITIONS_OVERRIDDEN | Files successful in AMT | Class : 1 SSMP Site AQ>58.6 | NA | CSS, CRS | Passed |  | 2018-04-16 | 2018-04-17 |  | 2018-04-17 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-24
CR273 | Inflight Scenario – CNF request received and accepted with old priority codes with effective date after the CR implementation, new need codes should be updated on the confirmation effective date | Confirmation effective date and daily delta output (EDL, IDL, EWS) | Class : 4 Site Type : GT AQ < 73200 Existing Site | 1. Combination of No match and Re-used codes | CNF, CFR, EDL/EWS | Passed |  | 2018-04-16 | 2018-04-17 |  | 2018-04-23 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-24
CR273 | Inflight Scenario – CNF request received and accepted with old priority codes with effective date after the CR implementation, new need codes should be updated on the confirmation effective date | Confirmation effective date and daily delta output (EDL, IDL, EWS) | Class : 4 Site Type : IGT AQ < 73200 Existing Site | 2. Combination of Not Used and Re-usable 3. Consent flag will not be updated | CNF, CFR, IDL/EWS | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-23 | Passed | 2018-04-24 | 2018-04-24 | 2018-04-24
CR273 | Inflight Scenario – CNC request received and accepted with old priority codes with effective date after the CR implementation, new need codes should be updated on the confirmation effective date | Contact effective date and daily delta output (EDL, IDL, EWS) | Class : 4 Site Type : GT AQ < 73200 Existing Site | 1. Combination of No match and Re-used codes | CNC, CNR, EDL/EWS | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-23 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-25
CR273 | Inflight Scenario – CNC request received and accepted with old priority codes with effective date after the CR implementation, new need codes should be updated on the confirmation effective date | Contact effective date and daily delta output (EDL, IDL, EWS) | Class : 4 Site Type : IGT AQ < 73200 Existing Site | 2. Combination of Not Used and Re-usable 3. Consent flag will not be updated | CNC, CNR, IDL/EWS | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-23 | Passed | 2018-04-23 | 2018-04-23 | 2018-04-25
CR273 | CNF request received and accepted with old priority codes with effective date after the CR implementation, New confirmation lapsed after implementation. This should not end date the existing values, these might have been replaced by migration program | Confirmation Lapsed with existing values effective on old contract | Class : 4 Site Type : GT AQ < 73200 Existing Site | Existing confirmation in progress prior to migration | CNF, CFR | Passed |  | 2018-04-18 | 2018-04-19 |  | 2018-04-23 | Passed | 2018-04-25 | 2018-04-25 | 2018-04-25
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 1. No Match – 03,17,18,20 replaced by 99 | NA | Passed |  | 2018-04-20 | 2018-04-21 |  | 2018-04-20 | Passed | 2018-04-26 | 2018-04-26 | 2018-04-25
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 2. Re-mapped: From - To: 4 - 14 5,6 - 8 7 - 9 | NA | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-19 | Passed | 2018-04-25 | 2018-04-25 | 2018-04-25
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 2. Re-mapped: From - To: 11 - 27 12 - 28 13 - 15 | NA | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-19 | Passed | 2018-04-26 | 2018-04-26 | 2018-04-25
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 2. Re-mapped: From - To: 16 - 22 21 - 2 22 - 1 | NA | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-20 | Passed | 2018-04-26 | 2018-04-26 | 2018-04-26
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 3. Existing to New From - To: 15 - 15 8,9,10 - 10 14 - 19 | NA | Passed |  | 2018-04-20 | 2018-04-23 |  | 2018-04-20 | Passed | 2018-04-27 | 2018-04-27 | 2018-04-26
CR273 | Data cleansing program to be tested for below scenarios: 1. No Match priority codes to be replaced by cod 99 2. Not Used codes to be mapped to reusable codes (5, 6 to be mapped to 8 ; 7 to be mapped to 9) 3. Existing values to be mapped to new values 4. None of the Portfolio files (program run +1) should include triggers for the data cleansed through new migration program (Open Item) 5. No Consent flag updates through new program | 3. Output should validate: Only one new code to be created where multiple old codes exist. | Class : 4 Site Type : GT AQ < 73200 Existing Site | 3. Existing to New From - To: 19 - 22 22 - 1 | NA | Passed |  | 2018-04-20 | 2018-04-23 |  | 2018-04-20 | Passed | 2018-04-27 | 2018-04-27 | 2018-04-26
CR273 | Need codes should be reflected correctly in BW, Run EQL on D+1 of EQL run, with new fields included in file format for GT sites - - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 Need codes should be reflected correctly in BW, Run IQL on D+1 of IQL run with new fields included in file format for iGT sites - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 | BW | Full load for BW with multiple Telephone Numbers in ISU for GT MPRN (Excluding TGT/NTS/Twin/Shared MPRNS) & iGT MPRN |  | FS_EQL FS_IQL | Passed |  | 2018-04-20 | 2018-05-01 |  | 2018-05-01 | Passed | 2018-05-02 | 2018-05-02 | 2018-05-03
CR273 | Need codes should be reflected correctly in BW, Run EQL on D+1 of EQL run, with new fields included in file format for GT sites - - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 Need codes should be reflected correctly in BW, Run IQL on D+1 of IQL run with new fields included in file format for iGT sites - Consent Flag - PSR code expiry date - Language - Alternate Priority Service contact name - Alternate priority service contact phone number 1 | BW | Full BW data - All the new fields are populated where data is present in ISU |  | FS_EQL FS_IQL | Passed |  | 2018-04-23 | 2018-04-24 |  | 2018-04-27 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-03
CR251 | Data matching between 2A and 2B | Data matching between 2A and 2B | Data matching between 2A and 2B | NA | NA | Passed |  | 2018-05-07 | 2018-05-08 |  | 2018-05-15 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-18
CR251 | 2B.1 - Count of Est reads for individual month by Shipper & Class 2B.1 - Count of check reads for individual month by Shipper & Class | 2B.1 - Count of Est reads for individual month by Shipper & Class 2B.1 - Count of check reads for individual month by Shipper & Class | 2B.1 - Count of Est reads for individual month by Shipper & Class 2B.1 - Count of check reads for individual month by Shipper & Class | NA | NA | Passed |  | 2018-05-07 | 2018-05-08 |  | 2018-05-04 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-17
CR251 | 2B.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | 2B.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | 2B.2 – Count of No Meter Recorded in the Supply Point Register for individual month by Shipper & Class | NA | NA | Passed |  | 2018-05-08 | 2018-05-09 |  | 2018-05-01 | Passed | 2018-05-10 | 2018-05-10 | 2018-05-09
CR251 | 2B.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | 2B.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | 2B.3 – Count of No Meter Recorded in the Supply Point Register and data flows received by Xoserve for individual month by Shipper & Class | NA | NA | Passed |  | 2018-05-08 | 2018-05-09 |  | 2018-05-01 | Passed | 2018-05-10 | 2018-05-10 | 2018-05-15
CR251 | 2B.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | 2B.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | 2B.4 – Percentage of Shipper Transfer Read Performance count by Month, Shipper & Class. | NA | NA | Passed |  | 2018-05-09 | 2018-05-10 |  | 2018-05-02 | Passed | 2018-05-11 | 2018-05-11 | 2018-05-15
CR251 | 2B.5 – Percentage of Read Performance by Month, Shipper & Class. | 2B.5 – Percentage of Read Performance by Month, Shipper & Class. | 2B.5 – Percentage of Read Performance by Month, Shipper & Class. | NA | NA | Passed |  | 2018-05-09 | 2018-05-10 |  | 2018-05-10 | Passed | 2018-05-11 | 2018-05-18 | 2018-05-18
CR251 | 2B.6 – Percentage of Reads where logic check* failed as a % of submitted readings | 2B.6 – Percentage of Reads where logic check* failed as a % of submitted readings Tolerance Failue due to incorrect application of the market breaker/override flag | 2B.6 – Percentage of Reads where logic check* failed as a % of submitted readings Tolerance Failue due to incorrect application of the market breaker/override flag | NA | NA | Passed |  | 2018-05-10 | 2018-05-11 |  | 2018-05-02 | Passed | 2018-05-14 | 2018-05-14 | 2018-05-09
CR251 | 2B.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | 2B.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | 2B.7 - Count of MPRNs with reading not received for 1, 2, 3 or 4 years by Month ,Shipper and AQ Band | NA | NA | Passed |  | 2018-05-10 | 2018-05-11 |  | 2018-04-23 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-15
CR251 | 2B.8 – Count of AQ Corrections by reason code, Month & Shipper | 2B.8 – Count of AQ Corrections by reason code, Month & Shipper | 2B.8 – Count of AQ Corrections by reason code, Month & Shipper | NA | NA | Passed |  | 2018-05-11 | 2018-05-14 |  | 2018-05-01 | Passed | 2018-05-15 | 2018-05-15 | 2018-04-25
CR251 | 2B.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | 2B.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | 2B.9 –Count of Standard Correction Factors for sites with AQ > 732, MWH by Month , Shipper and AQ band | NA | NA | Passed |  | 2018-05-11 | 2018-05-14 |  | 2018-05-02 | Passed | 2018-05-15 | 2018-05-15 | 2018-05-02
CR251 | 2B.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | 2B.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | 2B.10 - Count of MPRNs Where Meter Readings Replaced by Month , Shipper and AQ Band | NA | NA | Passed |  | 2018-05-14 | 2018-05-15 |  | 2018-05-02 | Passed | 2018-05-16 | 2018-05-16 | 2018-05-09
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO and validation is successful in ISU, linked addresses should be updated along with the PAF indicator as ‘P’. For the updated addresses, check NAC file notification along with EDL (B38), EWS(E21), DDU(M29) & IDL (B43) | NAC & Portfolio files in AMT | Unique GBMID, Amendment Type = A MP_STAT = LI GT site with existing GB Mail ID Existing PAF indicator = X | Valid Postcode and format with no exceptions 1. Address update is happening on an address where status is ‘X’ the Input indicator is ‘A’. Status changes ‘ X to P’ | PAF, NAC & Portofolio files | Passed |  | 2018-04-03 | 2018-04-05 |  | 2018-04-06 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-18
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO and validation is successful in ISU, linked addresses should be updated along with the PAF indicator as ‘P’. For the updated addresses, check NAC file notification along with EDL (B38), EWS(E21), DDU(M29) & IDL (B43) | NAC & Portfolio files in AMT | Unique GBMID, Amendment Type = A MP_STAT = EX Site belong to TGT with existing GB Mail ID Existing PAF indicator = P | Valid Postcode and format with no exceptions 1. Address update is happening on an address where status is ‘P’ the Input indicator is ‘A’. Status changes ‘ P to P’ | PAF, NAC & Portofolio files | Passed |  | 2018-04-03 | 2018-04-05 |  | 2018-04-06 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-19
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO and validation is successful in ISU, linked addresses should be updated along with the PAF indicator as ‘P’. For the updated addresses, check NAC file notification along with EDL (B38), EWS(E21), DDU(M29) & IDL (B43) | NAC & Portfolio files in AMT | Unique GBMID, Amendment Type = A MP_STAT = DE iGT site with existing GB Mail ID Existing PAF indicator = N | Valid Postcode and format with no exceptions 1. Address update is happening on an address where status is ‘N’ the Input indicator is ‘A’. Status changes ‘N to P’ | PAF, NAC & Portofolio files | Passed |  | 2018-04-04 | 2018-04-06 |  | 2018-04-06 | Passed | 2018-04-09 | 2018-04-09 | 2018-04-19
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO and validation is successful in ISU, linked addresses should be updated along with the PAF indicator as ‘P’. For the updated addresses, check NAC file notification along with EDL (B38), EWS(E21), DDU(M29) & IDL (B43) | NAC & Portfolio files in AMT | Unique GBMID, Amendment Type = A MP_STAT = LI iGT site with existing GB Mail ID Existing PAF indicator = P | Valid Postcode and format with no exceptions 1. Address update is happening on an address where status is ‘P’ the Input indicator is ‘A’. Status changes ‘P to P’ | PAF, NAC & Portofolio files | Passed |  | 2018-04-04 | 2018-04-06 |  | 2018-04-09 | Passed | 2018-04-10 | 2018-04-10 | 2018-04-19
XRN4249 | PAF file received from GB Mailing with amendment type ‘D’ through PO and validation is successful in ISU, PAF indicator updated to ‘X’ .No Outbound notifications files should be triggered | PAF indicator updates in ISU | Unique GBMID, Amendment Type = D GT site with existing GB Mail ID MP_STAT = LI Existing PAF indicator = X | Valid Postcode and format with no exceptions | PAF | Passed |  | 2018-04-09 | 2018-04-10 |  | 2018-04-09 | Passed | 2018-04-10 | 2018-04-10 | 2018-04-20
XRN4249 | PAF file received from GB Mailing with amendment type ‘D’ through PO and validation is successful in ISU, PAF indicator updated to ‘X’ .No Outbound notifications files should be triggered | PAF indicator updates in ISU | Unique GBMID, Amendment Type = D IGT site with existing GB Mail ID MP_STAT = LI Existing PAF indicator = P | Valid Postcode and format with no exceptions | PAF | Passed |  | 2018-04-09 | 2018-04-10 |  | 2018-04-10 | Passed | 2018-04-11 | 2018-04-11 | 2018-04-20
XRN4249 | PAF file received from GB Mailing with amendment type ‘D’ through PO and validation is successful in ISU, PAF indicator updated to ‘X’ .No Outbound notifications files should be triggered | PAF indicator updates in ISU | Unique GBMID, Amendment Type = D Site belong to TGT with existing GB Mail ID MP_STAT = EX Existing PAF indicator = N | Valid Postcode and format with no exceptions | PAF | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-11 | Passed | 2018-04-12 | 2018-04-12 | 2018-04-20
XRN4249 | PAF file received from GB Mailing with amendment type ‘I’ through PO , no updates should be done to any of the addresses. No outbound notifications files should be triggered, Should this be reported in Error Log with code QRJ01004 ‘Insert of address not processed’ | Validate no address and portfolio updates | Existing GBMID, Amendment Type = I GT Site with Existing GB Mail ID MP_STAT = LI Existing PAF indicator = X | Valid Postcode and format No exceptions | PAF | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-12 | Passed | 2018-04-13 | 2018-04-13 | 2018-04-20
XRN4249 | PAF file received from GB Mailing with combination of amendment types ‘A/D’ through PO however, one of the GB mailing ID is linked to multiple addresses, PF01 should be raised and assigned to authorized Xoserve user for action. | PF01 with no exception creation for ‘EX’ MPRN | Amendment Type = A PAF indicator = X GBMID that is linked to multiple MPRNs All MP_STAT= 'LI' | Valid Postcode and format 1. GBMID is mapped to multiple addresses | PAF | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-18 | Passed | 2018-04-17 | 2018-04-17 | 2018-05-01
XRN4249 | PAF file received from GB Mailing with combination of amendment types ‘A/D’ through PO however, one of the GB mailing ID is linked to multiple addresses, PF01 should be raised and assigned to authorized Xoserve user for action. | PF01 with no exception creation for ‘EX’ MPRN | Amendment Type = D PAF indicator = X GBMID linked to multiple MPRNs All with MP_STAT= 'EX' | Valid Postcode and format 2. GBMID received has EX MPR in SAP ISU, this should go to error log with code ‘QRJ01005 - Exception not generated. Meter Point Extinct’ | PAF | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-19 | Passed | 2018-04-17 | 2018-04-17 | 2018-04-24
XRN4249 | PAF file received from GB Mailing with combination of amendment types ‘A/D’ through PO however, one of the GB mailing ID is linked to multiple addresses, PF01 should be raised and assigned to authorized Xoserve user for action. | PF01 with no exception creation for ‘EX’ MPRN | Amendment Type = A PAF indicator = X GBMID that is linked to multiple MPRNs MP_STAT= 'LI' & 'EX' | Valid Postcode and format 3. Combination of Live and EX MPRN | PAF | Passed |  | 2018-04-13 | 2018-04-16 |  | 2018-04-27 | Passed | 2018-04-17 | 2018-04-17 | 2018-05-01
XRN4249 | PAF file received from GB Mailing with combination of amendment types ‘A’ through PO, however, post code received in the file is not available in ISU, PF02 should be raised and assigned to authorized Xoserve user for action. Resolution steps to be included in scope where user maintains the entry into the table and reprocess the exception | Exception PF02 with no exception creation for ‘EX’ MPR Generation of NAC and portfolio files after he resolution of the PF02. | Unique GBMID, Amendment Type = A MP_STAT = 'EX' | Post not found in ZMT_EZ_POSTCODE 1. GBMID received has EX MPR in SAP ISU, this should go to error log ‘QRJ01005 - Exception not generated. Meter Point Extinct’ | PAF | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-20 | Passed | 2018-04-19 | 2018-04-19 | 2018-04-25
XRN4249 | PAF file received from GB Mailing with combination of amendment types ‘A’ through PO, however, post code received in the file is not available in ISU, PF02 should be raised and assigned to authorized Xoserve user for action. Resolution steps to be included in scope where user maintains the entry into the table and reprocess the exception | Exception PF02 with no exception creation for ‘EX’ MPR Generation of NAC and portfolio files after he resolution of the PF02. | Unique GBMID, Amendment Type = A MP_STAT = 'LI' & 'EX' | Post not found in ZMT_EZ_POSTCODE 2. Combination of live and EX MPRN | PAF, NAC & Portofolio files | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-23 | Passed | 2018-04-19 | 2018-04-19 | 2018-05-01
XRN4249 | PAF file received from GB Group with combination of amendment types ‘A’ through PO, however, post code received in the file resulting in exit zone change, PF03 should be raised and assigned to authorized Xoserve user for action. | PF03 Exception and on resolution, Check NAC, MDS/AAQ and EXZ files in AMT along with portfolio updates | Unique GBMID, Amendment Type = A MP_STAT = LI Site belong to TGT with existing GB Mail ID | 1. Postcode received resulting in EXZ change(LI MPRN) | PAF, NAC, EXZ, MDS/AAQ & Portofolio files | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-27 | Passed | 2018-04-23 | 2018-04-23 | 2018-05-01
XRN4249 | PAF file received from GB Group with combination of amendment types ‘A’ through PO, however, post code received in the file resulting in exit zone change, PF03 should be raised and assigned to authorized Xoserve user for action. | PF03 Exception and on resolution, Check NAC, MDS/AAQ and EXZ files in AMT along with portfolio updates | Unique GBMID, Amendment Type = A MP_STAT = EX GT Site with existing GB Mail ID | 2. Postcode received resulting in EXZ change(EX MPRN) | PAF, NAC, EXZ, MDS/AAQ & Portofolio files | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-27 | Passed | 2018-04-23 | 2018-04-23 | 2018-05-01
XRN4249 | PAF file received from GB Group with combination of amendment types ‘A’ through PO, however, post code received in the file resulting in exit zone change, PF03 should be raised and assigned to authorized Xoserve user for action. | PF03 Exception and on resolution, Check NAC, MDS/AAQ and EXZ files in AMT along with portfolio updates | Unique GBMID, Amendment Type = A MP_STAT = LI GT Site with existing GB Mail ID | 3. Postcode received resulting in LDZ change (LI MPRN) | PAF, NAC, EXZ, MDS/AAQ & Portofolio files | Passed |  | 2018-04-23 | 2018-04-24 |  | 2018-04-30 | Passed | 2018-04-25 | 2018-04-25 | 2018-05-03
XRN4249 | Post GB Updates an email volumetric send this to all authorized Xoserve users along with below detail : 1. No. of Successful Address Updates 2. No. of Exceptions 3. No. of Error Logs 4. Total no of records received in PAF file | Email received by authorized Xoserve users successfully | All the above TCs must be executed | PAF file updates completed in system |  | Passed |  | 2018-04-23 | 2018-04-25 |  | 2018-04-30 | Passed | 2018-04-26 | 2018-04-26 | 2018-05-02
XRN4249 | AF file received from GB Group with Amendment type other than ‘A/D/I’, error log with code ‘QRJ01003’ should be raised with no address updates in ISU | Validate the Error log | Unique GBMID Amendment Type other than ‘A/D/I’ GT MPRN with MP_STAT = LI |  | PAF | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-19 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-25
XRN4249 | PAF file received from GB Group with amendment type ‘A’ through PO, Both Building number & building name not provided in file, raise an error log with code 'QRJ00382’ | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = DE | 1. Building number or building name both not provided in PAF file | PAF | Passed |  | 2018-04-17 | 2018-04-18 |  | 2018-04-19 | Passed | 2018-04-20 | 2018-04-20 | 2018-04-25
XRN4249 | PAF file received from GB Group with amendment type ‘A’ through PO, Building number not numeric in file, raise an error log with code 'QRJ00387' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = LI | 1. Building number if not numeric | PAF | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-19 | Passed | 2018-04-24 | 2018-04-24 | 2018-04-25
XRN4249 | PAF file received from GB Group with amendment type ‘A’ through PO, Incorrect building name (length more than 50), raise an error log with code ' QRJ00386' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = LI | 1. building name exceed allowable length | PAF | Passed |  | 2018-04-19 | 2018-04-20 |  | 2018-04-19 | Passed | 2018-04-24 | 2018-04-24 | 2018-04-25
XRN4249 | PAF file received from GB Mailing with amendment type ‘D’ through PO, Post Code if not provided generate error log with code 'POC00010' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = EX | 1. Post Code not provided | PAF | Passed |  | 2018-04-23 | 2018-04-24 |  | 2018-04-24 | Passed | 2018-04-25 | 2018-04-25 | 2018-04-25
XRN4249 | PAF file received from GB Mailing with amendment type ‘D’ through PO, Incorrect Length for Address Post Town generate error log with code 'QRJ00424' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = DE | 1. Incorrect Length for Proposed Address Post Town | PAF | Passed |  | 2018-04-23 | 2018-04-24 |  | 2018-04-24 | Passed | 2018-04-25 | 2018-04-25 | 2018-04-25
XRN4249 | PAF file received from GB Group with amendment type ‘A’ through PO, Incorrect Length for Proposed Address Postcode generate error log with code 'QRJ00389' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = LI | 1. Incorrect Length for Proposed Address Postcode | PAF | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-12 | Passed | 2018-04-16 | 2018-04-16 | 2018-04-25
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO, Incorrect Length for Sub Building Name generate error log with code 'QRJ00087' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = EX | 1. Incorrect Length for Sub Building Name | PAF | Passed |  | 2018-04-11 | 2018-04-12 |  | 2018-04-12 | Passed | 2018-04-16 | 2018-04-16 | 2018-04-25
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO, Incorrect Length for Dependent Locality generate error log with code 'QRJ00089' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = DE | 1. Incorrect Length for Dependent Locality | PAF | Passed |  | 2018-04-26 | 2018-04-27 |  | 2018-04-25 | Passed | 2018-04-30 | 2018-04-30 | 2018-04-26
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO, Incorrect Length for Proposed Address Principal Street Name generate error log with code 'QRJ00381' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = LI | 1. Incorrect Length for Proposed Address Principal Street Name | PAF | Passed |  | 2018-04-26 | 2018-04-27 |  | 2018-04-25 | Passed | 2018-04-30 | 2018-04-30 | 2018-04-26
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO, Principal Street Name not populated in the file for one of the records, generate error log with code ' QRJ00003' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = DE | 1. Principal Street Name not provided | PAF | Passed |  | 2018-04-26 | 2018-04-27 |  | 2018-04-25 | Passed | 2018-04-30 | 2018-04-30 | 2018-04-26
XRN4249 | PAF file received from GB Mailing with amendment type ‘A’ through PO but GBMID not found in SAP ISU system, raise an error log with code ‘QRJ01001’ | Validate the Error log |  | 1. GBMID not found in ISU system | PAF | Passed |  | 2018-04-26 | 2018-04-27 |  | 2018-04-25 | Passed | 2018-05-01 | 2018-05-01 | 2018-04-26
XRN4249 | PAF file received from GB Mailing with any amendment type through PO but GBMID not in the valid format, raise an error log with code ‘QRJ01002’ | Validate the Error log | A GBM ID not present in SAP ISU system and in incorrect format | 1. Length less than 17 | PAF | Passed |  | 2018-04-27 | 2018-04-30 |  | 2018-04-27 | Passed | 2018-05-01 | 2018-05-01 | 2018-04-30
XRN4249 | PAF file received from GB Mailing with any amendment type through PO but GBMID not in the valid format, raise an error log with code ‘QRJ01002’ | Validate the Error log | A GBM ID not present in SAP ISU system and in incorrect format | 2. Spaces in between | PAF | Passed |  | 2018-04-27 | 2018-04-30 |  | 2018-04-27 | Passed | 2018-05-01 | 2018-05-01 | 2018-04-30
XRN4249 | PAF file received from GB Mailing with any amendment type through PO but GBMID not in the valid format, raise an error log with code ‘QRJ01002’ | Validate the Error log | A GBM ID not present in SAP ISU system and in incorrect format | 3. Foreign characters | PAF | Passed |  | 2018-04-27 | 2018-04-30 |  | 2018-04-27 | Passed | 2018-05-02 | 2018-05-02 | 2018-04-30
XRN4249 | PAF file received from GB Group with amendment type ‘D’ through PO, Post Town if not provided generate error log with code ' QRJ00384' | Validate the Error log | Unique GBMID GT Site with Existing GBMID MP_STAT = LI | 1. Post Town not provided | PAF | Passed |  | 2018-04-27 | 2018-04-30 |  | 2018-04-26 | Passed | 2018-05-02 | 2018-05-02 | 2018-04-30
CR315 | Test a scenario to run AMS business audit report where for the UMR reads are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly. T-code: ZB_AMSADUIT Data: Class 4, SSP, LSP GT, iGT ZDT_UMR_RECORDS table entries with Read Status = U, REC flag = X 1. For RGMA Read, RECORD_TYPE=RGM 2. For UMR Read, RECORD_TYPE=U01 3. CMS Must Read, RECORD_TYPE=MUP 4. Estimated reads (EST) | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5 MPRNs, 7 UMR reads received. 4 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UMR, hence no separate scenario required | 5 MPRNs, 7 UMR reads received. 4 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UMR, hence no separate scenario required |  | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-02 | Passed | 2018-05-03 | 2018-05-03 | 2018-05-09
CR315 | Test a scenario to run AMS business audit report where Site Visit Reads that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly. T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT ZDT_SFN_READ_PRO table entries with OUTCOME CODE = AC, PROCESSED INDICATOR = X For the same read date corresponding REC staging tables will be updated with REC Flag = X | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 4 SFN Entries for 4 MPRNs, First one will be billed, second one will have exception and third & forth will neither be billed nor will have any exceptions | 4 SFN Entries for 4 MPRNs, First one will be billed, second one will have exception and third & forth will neither be billed nor will have any exceptions |  | Passed |  | 2018-05-02 | 2018-05-03 |  | 2018-05-09 | Passed | 2018-05-04 | 2018-05-04 | 2018-05-09
CR315 | Test a scenario to run AMS business audit report where Consumption Adjustment that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Class 1, 2, 3 & 4 SSP, LSP GT, iGT Source : CDA File, Portal & Internal Screen ZDT_CDA_CRA table with ADJUSTMENT STATUS = A | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 4 CA Entries for 4 MPRNs, 1st and 2nd billed, 3rd with exception and 4th neither billed nor in any exceptions | 4 CA Entries for 4 MPRNs, 1st and 2nd billed, 3rd with exception and 4th neither billed nor in any exceptions |  | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-11 | Passed | 2018-05-04 | 2018-05-04 | 2018-05-11
CR315 | Test a scenario to run AMS business audit report where RD1 Reads that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 4 (Combination of Prime and Sub sites) SSP, LSP GT, iGT ZDT_RD1_RVI with STATUS =U PRIME SITE IND = X or Blank ZDT_PRIME_SUB where 'status of net off calculation = U, REC flag = X and Identified based on READ DATE | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5 MPRNs, 8 UBR reads received. 5 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UBR, hence no separate scenario required | 5 MPRNs, 8 UBR reads received. 5 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UBR, hence no separate scenario required |  | Passed |  | 2018-05-03 | 2018-05-04 |  | 2018-05-15 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-15
CR315 | Test a scenario to run AMS business audit report where UBR Reads that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Class 3, SSP, LSP GT, iGT ZDT_UBR_RECORDS table entries with Read Status = U, REC flag = X 1. For RGMA Read, RECORD_TYPE=RGM 2. For UBR Read, RECORD_TYPE=U13 3. CMS Must Read, RECORD_TYPE=MUP 4. Prime_Site_IND = X with ZDT_PRIME_SUB where 'status of net off calculation = U, REC flag = X and Identified based on READ DATE 5. Estimated reads | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5 MPRNs, 8 UBR reads received. 5 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UBR, hence no separate scenario required | 5 MPRNs, 8 UBR reads received. 5 Reads will be billed, 1 will have exceptions and 2 are neither billed nor will have any exceptions. Note: RGMA activity and Must reads will update the UBR, hence no separate scenario required |  | Passed |  | 2018-05-04 | 2018-05-07 |  | 2018-05-08 | Passed | 2018-05-08 | 2018-05-08 | 2018-05-09
CR315 | Test a scenario to run AMS business audit report where DLC reads received outside closeout that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1 DM GT, iGT ZDT_DLC_RECORDS where status is U 1. For RGMA Read, RECORD_TYPE=RGM 2. For DLC Read, RECORD_TYPE=O10 3. Prime_Site_IND = X with ZDT_PRIME_SUB where 'status of net off calculation = U, REC flag = X and Identified based on READ DATE 4. Estimated reads Entry present in ZDT_DM_REC for read date and Processed Indicator = X with REC Source : D(DLC), C(CA), R(Check), I(DRE Install) & A (RGMA) | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5 MPRNs, 15 DLC reads recieved outside the close out for which entries should be present in ZDT_DM_REC 10 reads will be billed, 2 reads will have exception and 3 are neither billed nor will have any exceptions Note: RGMA activity and Must reads will update the DLC, hence no separate scenario required | 5 MPRNs, 15 DLC reads recieved outside the close out for which entries should be present in ZDT_DM_REC 10 reads will be billed, 2 reads will have exception and 3 are neither billed nor will have any exceptions Note: RGMA activity and Must reads will update the DLC, hence no separate scenario required |  | Passed |  | 2018-05-04 | 2018-05-07 |  | 2018-05-08 | Passed | 2018-05-09 | 2018-05-09 | 2018-05-09
CR315 | Test a scenario to run AMS business audit report where PCA file recieved for the NTS Tele Metered site within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1 DM NTS Telemetered For PCA entries will be created in ZDT_DM_REC for read date with with REC Source : P (PCA Input) | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 3 MPRNs, 4 PCA files with energy received, for which entries should be present in ZDT_DM_REC. 2 reads will be billed, 1 will have exception and 1 will neither be billed nor will have any exceptions. | 3 MPRNs, 4 PCA files with energy received, for which entries should be present in ZDT_DM_REC. 2 reads will be billed, 1 will have exception and 1 will neither be billed nor will have any exceptions. |  | Passed |  | 2018-05-07 | 2018-05-08 |  | 2018-05-09 | Passed | 2018-05-09 | 2018-05-09 | 2018-05-09
CR315 | Test a scenario to run AMS business audit report where UDR reads received outside closeout that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counter statistics in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 2 DM GT, iGT Tables ZDT_UDR_RECORDS table entries with Read Status = U, 1. For RGMA Read, RECORD_TYPE=RGM 2. For UBR Read, RECORD_TYPE=U12 3. CMS Must Read, RECORD_TYPE=MUP 4. Prime_Site_IND = X with ZDT_PRIME_SUB where 'status of net off calculation = U, REC flag = X and Identified based on READ DATE 5. Estimated Read Entry present in ZDT_DM_REC. with REC Source : U (UDR) | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5 MPRNs, 15 UDR reads received outside the close out for which entries should be present in ZDT_DM_REC. 10 reads will be billed, 2 reads will have exception and 3 are neither billed nor will have any exceptions. 3 Must reads will be uploaded on the above 5 MPRNs to test. Note: RGMA activity and Must reads will update the UDR, hence no separate scenario required | 5 MPRNs, 15 UDR reads received outside the close out for which entries should be present in ZDT_DM_REC. 10 reads will be billed, 2 reads will have exception and 3 are neither billed nor will have any exceptions. 3 Must reads will be uploaded on the above 5 MPRNs to test. Note: RGMA activity and Must reads will update the UDR, hence no separate scenario required |  | Passed |  | 2018-05-07 | 2018-05-08 |  | 2018-05-08 | Passed | 2018-05-10 | 2018-05-10 | 2018-05-11
CR315 | Test a scenario to run AMS business audit report combination of UMR, UBR, UDR (outside closeout) and DLC (outside closeout) reads that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT Read Status = U, Any read type | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 12 MPRNs with 12 Reads with 3 each for UMR, UBR, UDR and DLC One of each file type is billed, 2nd is in exception and 3rd neither billed nor in exception | 12 MPRNs with 12 Reads with 3 each for UMR, UBR, UDR and DLC One of each file type is billed, 2nd is in exception and 3rd neither billed nor in exception |  | Passed |  | 2018-05-08 | 2018-05-09 |  | 2018-05-09 | Passed | 2018-05-10 | 2018-05-10 | 2018-05-11
CR315 | Test a scenario to run AMS business audit report combination of Site Visit reads, RD1 reads , Consumption Adjustment and PCA file that are received within a particular billing month exit closeout and validate if either of existing valid REC bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT Any read type | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 12 MPRNs with 12 entries with 3 each for Site Visit, RD1, CA and PCA One of each file type is billed, 2nd is in exception and 3rd neither billed nor in exception | 12 MPRNs with 12 entries with 3 each for Site Visit, RD1, CA and PCA One of each file type is billed, 2nd is in exception and 3rd neither billed nor in exception |  | Passed |  | 2018-05-08 | 2018-05-09 |  | 2018-05-15 | Passed | 2018-05-11 | 2018-05-18 | 2018-05-15
CR315 | Test a scenario to run AMS business audit report for the ajustments triggerred as part of isolation, reconnection. For all the adjusment entries created within a particular billing month exit closeout and validate if either of existing valid ADJ bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table. Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT Process type=IS/RC | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception |  | Passed |  | 2018-05-09 | 2018-05-10 |  | 2018-05-12 | Passed | 2018-05-14 | 2018-05-14 | 2018-05-14
CR315 | Test a scenario to run AMS business audit report for the ajustments triggerred as part of backbilling. For all the adjusment entries created within a particular billing month exit closeout and validate if either of existing valid ADJ bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table. Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT Process type=BC/BP/BM | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception |  | Passed |  | 2018-05-10 | 2018-05-11 |  | 2018-05-12 | Passed | 2018-05-14 | 2018-05-14 | 2018-05-14
CR315 | Test a scenario to run AMS business audit report for the ajustments triggerred as part of Late meter fix and Late confirmation. For all the adjusment entries created within a particular billing month exit closeout and validate if either of existing valid ADJ bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table. Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT Data: Class 1, 2, 3 & 4 SSP, LSP GT, iGT Process type=LM | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception | 3 MPRNs, 1 will be Billed, 1 will go into exception and 1 is neither billed nor in exception |  | Passed |  | 2018-05-10 | 2018-05-11 |  | 2018-05-12 | Passed | 2018-05-15 | 2018-05-15 | 2018-05-14
CR315 | Test a scenario to run AMS business audit report for the selected 5k. For all the reads/CA/ adjusment entries created within a particular billing month exit closeout and validate if either of existing valid ADJ bill document or EMMA exception is present, if not should be reported in the table ZBT_REC_FALLOUTS table. Counters in ZBT_REC_VALIDATION should be upadted accordingly T-code: ZB_AMSADUIT | Read and Billing Reconcilation Report screen with text box to enter billing month should be displayed. | 5k MPRNs | 5k MPRNs |  | Passed |  | 2018-05-10 | 2018-05-11 |  | 2018-05-17 | Passed | 2018-05-16 | 2018-05-18 | 2018-05-17
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-03 | 2018-05-11 |  | 2018-05-03 | Passed | 2018-05-08 | 2018-05-15 | 2018-05-08
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-03 | 2018-05-11 |  | 2018-05-03 | Passed | 2018-05-08 | 2018-05-15 | 2018-05-08
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-03 | 2018-05-11 |  | 2018-05-08 | Passed | 2018-05-08 | 2018-05-15 | 2018-05-08
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-03 | 2018-05-11 |  | 2018-05-09 | Passed | 2018-05-08 | 2018-05-15 | 2018-05-14
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-24 | 2018-05-24 |  | 2018-05-24 | Passed | 2018-05-08 | 2018-05-18 | 2018-05-25
XRN4249 | TBC |  |  |  |  | Passed |  | 2018-05-03 | 2018-05-11 |  | 2018-05-07 | Passed | 2018-05-08 | 2018-05-15 | 2018-05-08
CRID |  | Job Type | Job Dependancies | Volumetric | Expected run time | Execution Status | Linked Defect | Planned Execution Start Date | Planned Execution End Date | Actual Execution Start Date | Actual Execution End Date | Assurance Planned Start Date | AssurancePlanned End Date | Actual Assurance Start Date | Actual Assurance End Date | Comments
CR273 | ZMR_CR273_PSR_UPD_OT | Primary | NA |  |  | Passed |  | 2018-05-02 | 2018-05-02 |  | 2018-05-02 | Passed | 2018-05-03 | 2018-05-17 | 2018-05-09
CR273 | ZMR_CR273_PSR_UPD_OT | Primary | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T1A_ISU_UPD_IN_DY | BAU Parallel | NA | 24 M |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T1A_ISU_UPR_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY | All GTs |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T1A_ISU_UPR_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_UPR_OU_DY_01 |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_JOB_IN_DY | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T1A_ISU_JRS_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_JOB_IN_DY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_JRS_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_JRS_OU_DY_01 |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_DMSP_DLC_DWY_03 | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_SHP_MDR_18_DWY | BAU Parallel | Dependent on T2A_ISU_DMSP_DLC_DWY_03 | GT ~ 4M iGT ~ 81K |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_DMSP_DDR_DWY_03 | BAU Parallel | Dependent on T2A_ISU_SHP_MDR_18_DWY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_DMSP_RPA_DWY_03 | BAU Parallel | Dependent on T2A_ISU_DMSP_DDR_DWY_03 |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_SHP_UDR_DWY | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T2A_ISU_SHP_MBR_DWY | BAU Parallel | Dependent on T2A_ISU_SHP_UDR_DWY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_NONCYC_MID_IN_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T1A_ISU_NONCYC_MIO_OU_DY | BAU Parallel | Dependent on T1A_ISU_NONCYC_MID_IN_DY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-15
CR273 | T2A_ISU_SHP_UMR_DWY_01 | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T2A_ISU_SHP_UMR_DWY_02 | BAU Parallel | Dependent on T2A_ISU_SHP_UMR_DWY_01 |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_UPD_IN_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_UPR_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | T1A_ISU_UPR_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_UPR_OU_DY_01 |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-17 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
CR273 | Load Delta to BW | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-16 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-18
XRN4249 | T1A_ISU_PAF | Primary | NA |  |  | Passed |  | 2018-05-02 | 2018-05-02 |  | 2018-05-02 | Passed | 2018-05-03 | 2018-05-17 | 2018-05-09
XRN4249 | T1A_ISU_PAF | Primary | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-19 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_03 | BAU Parallel | NA | GT ~ 4M iGT ~ 81K |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-19 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_04 | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-19 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_05 | BAU Parallel | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-19 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-21
XRN4249 | Error log report (Report Program ZPAF_ERROR_LOG) | Primary | NA |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_ISU_NAC_DWY | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_IDL_GENERATE_HY | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_ISU_EWS_GENERATE | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_ISU_DDU_OU_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_ISU_DDU_GEN_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | T1A_ISU_IDL_GEN_HY | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
XRN4249 | Load Delta to BW | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-10 | 2018-05-17 | 2018-05-14
CR147 | T1A_ISU_DDU_GEN_DY | Primary | NA |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-03 | Passed | 2018-05-02 | 2018-05-16 | 2018-05-09
CR147 | T1A_ISU_DDU_OU_DY | Primary | NA |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-03 | Passed | 2018-05-02 | 2018-05-16 | 2018-05-09
CR147 | T1A_ISU_DDU_GEN_DY | Primary | NA | 22 M |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR147 | T1A_ISU_IDL_GEN_DY | BAU Parallel | NA | 22 M |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR147 | T1A_ISU_DDU_OU_DY | Primary | NA | 22 M |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR147 | T1A_ISU_IDL_OU_DY | BAU Parallel | NA | 22 M |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR147 | T1A_ISU_EWS_GENERATE | BAU Parallel | NA | 22 M |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR147 | T1A_ISU_EDL_OU_DY_01 | BAU Parallel | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-10 | Passed | 2018-05-10 | 2018-05-16 | 2018-05-11
CR273 | PCUK_DUK_DDS | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-16 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-16
CR273 | PCUK_DUK_EQL | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-16 | Passed | 2018-05-11 | 2018-05-17 | 2018-05-16
CR292 | T1A_ISU_XDO_OU_DY | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-09 | 2018-05-16 | 2018-05-15
COR3386 | MURPR155s | Primary | NA |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-07 | Passed | 2018-05-03 | 2018-05-17 | 2018-05-11
COR3386 | MURPR00Ss | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-15
COR3386 | MURPR10Ss | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-15
COR3386 | MURPR155s | Primary | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-11 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-15
COR3386 | Load the delta to BW |  | NA |  |  | Passed |  | 2018-05-08 | 2018-05-08 |  | 2018-05-17 | Passed | 2018-05-09 | 2018-05-17 | 2018-05-24
COR3283 | ACRCROOSs | Primary | NA |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-07 | Passed | 2018-05-02 | 2018-05-17 | 2018-05-11
COR3283 | CMS migration | BAU Parallel |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-16 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | Legacy Migration | BAU Parallel |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-17 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | ACRCROOSs | Primary |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-17 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | T1A_ISU_NMR_OU_DY | BAU Parallel |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-17 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | T1A_ISU_NMR_OU_DY_02 | BAU Parallel |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-17 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | ARSLDOOSs | Primary |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-14 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
COR3283 | Load the delta to BW |  |  |  |  | Passed |  | 2018-05-09 | 2018-05-09 |  | 2018-05-17 | Passed | 2018-05-14 | 2018-05-17 | 2018-05-18
CR359 | ACRCROOSs | Primary |  |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-07 | Passed | 2018-05-02 | 2018-05-17 | 2018-05-11
CR359 | ACRCROOSs | Primary |  |  |  | Passed |  | 2018-05-10 | 2018-05-10 |  | 2018-05-11 | Passed | 2018-05-15 | 2018-05-17 | 2018-05-11
CR359 | ARSLDOOSs | BAU Parallel |  |  |  | Passed |  | 2018-05-10 | 2018-05-10 |  | 2018-05-11 | Passed | 2018-05-15 | 2018-05-17 | 2018-05-11
CR359 | Load the delta to BW |  |  |  |  | Passed |  | 2018-05-10 | 2018-05-10 |  | 2018-05-17 | Passed | 2018-05-15 | 2018-05-17 | 2018-05-24
CR367 | MIVCROOSs | Primary |  |  |  | Passed |  | 2018-05-01 | 2018-05-01 |  | 2018-05-07 | Passed | 2018-05-02 | 2018-05-17 | 2018-05-11
CR367 | MIVCROOSs | Primary |  |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-14 | Passed | 2018-05-08 | 2018-05-17 | 2018-05-15
CR367 | MURPR30Ss | Primary |  |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-08 | 2018-05-17 | 2018-05-15
CR367 | MURPR20Ss | Primary |  |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-08 | 2018-05-17 | 2018-05-15
CR367 | MURPR25Ss | Primary |  |  |  | Passed |  | 2018-05-07 | 2018-05-07 |  | 2018-05-11 | Passed | 2018-05-08 | 2018-05-17 | 2018-05-15
CR367 | MURPR30Ss | Primary |  |  |  | Passed |  | 2018-05-14 | 2018-05-14 |  | 2018-05-11 | Passed | 2018-05-15 | 2018-05-17 | 2018-05-15
CR367 | MDPFLOOSs | Primary |  |  |  | Passed |  | 2018-05-14 | 2018-05-14 |  | 2018-05-14 | Passed | 2018-05-15 | 2018-05-17 | 2018-05-18
CR315 | [5 empty] | Passed |  | 2018-05-16 | 2018-05-16 |  | 2018-05-22 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-24
XRN4249 | T1A_ISU_PAF | Primary | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-19 | Passed | 2018-05-17 | 2018-05-23 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_03 | BAU Parallel | NA | GT ~ 4M iGT ~ 81K |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-19 | Passed | 2018-05-17 | 2018-05-23 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_04 | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-19 | Passed | 2018-05-17 | 2018-05-23 | 2018-05-21
XRN4249 | T1A_ISU_EDL_OU_DY_05 | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-19 | Passed | 2018-05-17 | 2018-05-23 | 2018-05-21
CR273 | ZMR_CR273_PSR_UPD_OT | Primary | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T1A_ISU_UPD_IN_DY | BAU Parallel | NA | 24 M |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T1A_ISU_UPR_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY | All GTs |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T1A_ISU_UPR_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_UPR_OU_DY_01 |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_JOB_IN_DY | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T1A_ISU_JRS_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_JOB_IN_DY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_JRS_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_JRS_OU_DY_01 |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_DMSP_DLC_DWY_03 | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_SHP_MDR_18_DWY | BAU Parallel | Dependent on T2A_ISU_DMSP_DLC_DWY_03 | GT ~ 4M iGT ~ 81K |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_DMSP_DDR_DWY_03 | BAU Parallel | Dependent on T2A_ISU_SHP_MDR_18_DWY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_DMSP_RPA_DWY_03 | BAU Parallel | Dependent on T2A_ISU_DMSP_DDR_DWY_03 |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_SHP_UDR_DWY | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T2A_ISU_SHP_MBR_DWY | BAU Parallel | Dependent on T2A_ISU_SHP_UDR_DWY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_NONCYC_MID_IN_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T1A_ISU_NONCYC_MIO_OU_DY | BAU Parallel | Dependent on T1A_ISU_NONCYC_MID_IN_DY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-11 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-15
CR273 | T2A_ISU_SHP_UMR_DWY_01 | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T2A_ISU_SHP_UMR_DWY_02 | BAU Parallel | Dependent on T2A_ISU_SHP_UMR_DWY_01 |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_UPD_IN_DY | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_UPR_OU_DY_01 | BAU Parallel | Dependent on T1A_ISU_UPD_IN_DY |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | T1A_ISU_UPR_OU_DY_02 | BAU Parallel | Dependent on T1A_ISU_UPR_OU_DY_01 |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-17 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | Load Delta to BW | BAU Parallel | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-16 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-18
CR273 | PCUK_DUK_DDS | Primary | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-16 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-16
CR273 | PCUK_DUK_EQL | Primary | NA |  |  | Passed |  | 2018-05-16 | 2018-05-17 |  | 2018-05-16 | Passed | 2018-05-17 | 2018-05-18 | 2018-05-16
CR112 | IGT Address amendment received through CMS, AES file should be triggered. | AES Trigger till AMT Market flow | Class 4 iGT NDM | Delivery point Alias updated through CMS ELECTED_SHIPPER_SHORT_CODE available on SMP already | AES | Passed |  | 2018-05-21 | 2018-05-21 |  | 2018-05-30 | Passed | 2018-05-30 | 2018-05-31 | 2018-05-30
CR112 | IMA file received with Elected shipper details where delivery point alias was updated through CMS, AES should be triggered | AES Trigger till AMT Market flow | Class 4 iGT NDM | Delivery point Alias updated through CMS | IMA, AES | Passed |  | 2018-05-22 | 2018-05-22 |  | 2018-05-30 | Passed | 2018-05-31 | 2018-06-01 | 2018-05-31
CR112 | SMP Creation for CSO Site through SAP Internal screen, one successful SMP creation, no AES should be triggered | No AES for CSO Creation | Class 1 LDZ CSO | - | - | Passed |  | 2018-05-23 | 2018-05-23 |  | 2018-05-28 | Passed | 2018-05-24 | 2018-05-25 | 2018-05-30
CR112 | SMP Creation for CSO Site through SAP Internal screen, one successful SMP creation, no AES should be triggered | No AES for CSO Creation | Class 1 NTS CSO | - | - | Passed |  | 2018-05-24 | 2018-05-24 |  | 2018-05-28 | Passed | 2018-05-25 | 2018-05-29 | 2018-05-31
CR147 | Description: EUC change via postcode update through address change process (ZSMP). DDU file should include the delta. Pre-Requisite: Class 4 GT MPRN must be present. | DDU files in AMT | GT, NDM Class 4 | 1. Address change via CMS (postcode change) | - | Passed |  | 2018-05-21 | 2018-05-22 |  | 2018-05-28 | Passed | 2018-05-23 | 2018-05-24 | 2018-05-30
CR147 | Description: EUC change via postcode update through address change process (ZSMP). DDU file should include the delta. Pre-Requisite: EUC change via postcode update through address change process (ZSMP). |  | GT, NDM Class 4 | EUC change via postcode update through address change process (ZSMP). | - | Passed |  | 2018-05-21 | 2018-05-22 |  | 2018-05-28 | Passed | 2018-05-23 | 2018-05-24 | 2018-06-07
CR147 | Description: EUC change via postcode update through address change process (CMS). DDU file should include the delta. Pre-Requisite: Class 4 GT MPRN must be present. | DDU files in AMT | GT, NDM Class 4 | 2. Address change via ZSMP (postcode change) | - | Passed |  | 2018-05-22 | 2018-05-23 |  | 2018-05-30 | Passed | 2018-05-24 | 2018-05-25 | 2018-05-31
CR147 | Description: EUC change via postcode update through address change process (CMS). DDU file should include the delta. Pre-Requisite: EUC change via postcode update through address change process (CMS). | DDU files in AMT | GT, NDM Class 4 | EUC change via postcode update through address change process (CMS). | - | Passed |  | 2018-05-22 | 2018-05-23 |  | 2018-05-30 | Passed | 2018-05-24 | 2018-05-25 | 2018-06-07
CR147 | Description: EUC change via postcode update through address change process (ZSMP). DDU file should include the delta. Pre-Requisite: Class 4 GT MPRN must be present. | DDU files in AMT | GT, NDM Class 4 | EUC change via postcode update through address change process (ZSMP) | - | Passed |  | 2018-05-23 | 2018-05-24 |  | 2018-06-06 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-07
CR147 | Description: EUC change via postcode update through address change process (CMS). DDU file should include the delta. Pre-Requisite: Class 4 GT MPRN must be present. | DDU files in AMT | GT, NDM Class 4 | EUC change via postcode update through address change process (CMS) | - | Passed |  | 2018-05-23 | 2018-05-24 |  | 2018-06-06 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-07
CR147 | Description: Class change of GT site from 1 to 3. FYAQ and FYSOQ should be sent in the DDU file. Pre-Requisite: Class 1 GT site should exist. Expected Result: Class change of GT site from 1 to 3 is successful and the FYAQ and FYSOQ facts have been updated. | DDU files in AMT | GT, NDM Class 1 to 3 | - | - | Passed |  | 2018-05-24 | 2018-05-25 |  | 2018-05-31 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-04
CR147 | Description: Class change of GT site from 1 to 3. FYAQ and FYSOQ should be sent in the DDU file. Pre-Requisite: Class change of GT site from 1 to 3. Expected Result: DDU Trigger should be created for the MPRN. Once executed, DDU should pick the MPRN and send the new FYAQ and FYSOQ. | DDU files in AMT | GT, NDM Class 1 to 3 | - | - | Passed |  | 2018-05-24 | 2018-05-25 |  | 2018-05-31 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-04
CR147 | Description: Shipper transfer where SOQ and SHQ are higher than that of prevailing SOQ and SHQ. DDU should pick the revised values along with DM_EFFECTIVE_DATE Pre Requisite: Class 1 GT site should exist Expected Result: Shipper transfer is successful with requesting SOQ and SHQ are higher than that of prevailing SOQ and SHQ. | DDU files in AMT | GT, DM Class 1 (Referral) | - | - | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-05 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-06
CR147 | Description: Shipper transfer where SOQ and SHQ are higher than that of prevailing SOQ and SHQ. DDU should pick the revised values along with DM_EFFECTIVE_DATE Pre-Requisite: Shipper transfer where SOQ and SHQ are higher than that of prevailing SOQ and SHQ Expected Result: DDU Trigger should be created for the MPRN. Once executed, DDU should pick the revised values along with DM_EFFECTIVE_DATE. | DDU files in AMT | Site: Class 1 GT site | - | - | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-08 | Passed | 2018-06-07 | 2018-06-11 | 2018-06-11
CR147 | Description: Meter point status change from LI to Dead from Portal. DDU file should pick the delta. Pre-Requisite: Class 4 Withdrawn site must exist. Expected Result: DDU Trigger should be created for the MPRN. Once executed, DDU should pick the MPRN. | DDU files in AMT | Class 4 NDM Withdrawn site | - | - | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | Passed | 2018-06-01 | 2018-06-04 | 2018-05-31
CR147 | Description: Meter point status change from LI to Dead from Portal. DDU file should pick the delta. Pre-Requisite: Meter point status change from LI to Dead from Portal. Expected Result: DDU Trigger should be created for the MPRN. Once executed, DDU should pick the MPRN. | DDU files in AMT | Site: Class 4 Withdrawn Site | - | - | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | Passed | 2018-06-01 | 2018-06-04 | 2018-05-31
CR147 | Run DDS File | DDS file ran successfully |  |  |  | Passed |  | 2018-06-01 | 2018-06-02 |  | 2018-06-01 | Passed | 2018-06-04 | 2018-06-05 | 2018-06-05
CR267 | SFN Rejection file | To test whether the file is rejecting for SFN file with DRE_FAULT_CORRECTED field as space | Site with existing DRE fault |  | SFN and SFR | Passed |  | 2018-05-21 | 2018-05-22 |  | 2018-05-22 | Passed | 2018-05-23 | 2018-06-05 | 2018-06-05
CR267 | SFN Rejection file | To test whether the file is rejecting for SFN file with DRE_FAULT_CORRECTED field as space | Site with existing DRE fault | iGT |  | Passed |  | 2018-05-31 | 2018-05-31 |  | 2018-06-01 | Passed | 31/6/18 | 2018-06-01 | 2018-06-04
CR267 | SFN Rejection file | To test whether the file is rejecting for SFN file with DRE_FAULT_CORRECTED field populated as blank | Site with existing DRE fault |  | SFN and SFR | Passed |  | 2018-05-22 | 2018-05-23 |  | 2018-05-22 | Passed | 2018-05-24 | 2018-05-25 | 2018-05-30
CR267 |  |  | Site With existing DRE fault |  | SFN and SFR | Passed |  | 2018-05-22 | 2018-05-23 |  | 2018-05-22 | Passed | 2018-05-24 | 2018-05-25 | 2018-05-30
CR267 | Acceptance in SFR file, ends the fault and loads the read. | To test whether the file is accepting for SFN file with DRE_FAULT_CORRECTED field populated as Y | Site with existing DRE fault |  | SFN and SFR | Passed |  | 2018-05-23 | 2018-05-24 |  | 2018-05-23 | Passed | 2018-05-25 | 2018-05-29 | 2018-05-30
CR267 |  |  | Site with existing DRE fault |  | SFN and SFR | Passed |  | 2018-05-23 | 2018-05-24 |  | 2018-05-23 | Passed | 2018-05-25 | 2018-05-29 | 2018-05-31
CR267 | SFN Rejection file | To test whether the file is rejecting for SFN file with DRE_FAULT_CORRECTED field populated as Y | No existing fault |  | SFN and SFR | Passed |  | 2018-05-24 | 2018-05-25 |  | 2018-05-25 | Passed | 2018-05-29 | 2018-05-30 | 2018-05-30
CR267 |  |  | No existing fault |  | SFN and SFR | Passed |  | 2018-05-24 | 2018-05-25 |  | 2018-05-25 | Passed | 2018-05-29 | 2018-05-30 | 2018-05-30
CR267 | Acceptance in SFR file, ends the fault and loads the read. | To test whether the file is accepting for SFN file with DRE_FAULT_CORRECTED field populated as blank | No existing fault |  | SFN and SFR | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-25 | Passed | 2018-05-29 | 2018-05-30 | 2018-05-30
CR267 |  |  | No existing fault |  | SFN and SFR | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-28 | Passed | 2018-05-29 | 2018-05-31 | 2018-05-31
CR270 | Nomination Request Received with requested AQ between (>73,200 kWh / <732,000kWh), capacity referral should be sent |  | Existing Greenfield site Site Type: GT Nomination request to Class - 2 (DM) Request referred & offer supplied through NRF file | Existing GT Site, Greenfield Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-30 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-01
CR270 |  |  | Existing Greenfield site Site Type: IGT Nomination request to Class - 2 (DM) Request referred & offer supplied through NRF file | Existing IGT Site, Greenfield Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF, IGR | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-31 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-01
CR270 |  |  | Existing Brownfield site Site Type: GT Nomination request to Class - 2 (DM) Request referred & offer supplied through NRF file | Existing GT Site, Brownfield Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-05-30 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-01
CR270 |  |  | Existing Brownfield site Site Type: IGT Nomination request to Class - 2 (DM) Request referred & offer supplied through NRF file | Existing IGT Site, Brownfield Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF, IGR | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-05-31 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-01
CR270 | Nomination Request Received with requested AQ > 58.6 kWh, Capacity referral should be sent |  | Existing class-2 site Site Type: GT Nomination request (Class change: 2 to 1) Request referred & offer supplied through NRF file | Existing class-2 GT Site, Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | Passed | 2018-06-01 | 2018-06-04 | 2018-06-04
CR270 |  |  | Existing class-2 site Site Type: IGT Nomination request (Class change: 2 to 1) Request referred & offer supplied through NRF file | Existing class-2 IGT Site, Lower Range =73,200 Upper Range = Different for each DNO | NOM, NMR, NRF, IGR | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-06-01 | Passed | 2018-06-01 | 2018-06-04 | 2018-06-04
CR270 | SPC file with class change request with amended SOQ values, this request should be rejected |  | Existing class-4 site Site Type: GT Class change request (Class change: 4 to 2) with amended SOQ values Request rejected as: CLS0008 | Existing GT Site, Class change from 4 to 2 through SPC, AQ between (>73,200 kWh / <732,000kWh) Class change request with amended SOQ values | SPC, SCR | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-01 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-06
CR270 | Capacity Amendment Received with requested SOQ/SHQ values greater than that of prevailing SOQ/SHQ and ratio between >16 /<24, Capacity referral should be sent |  | Class: 2 Site Type: GT site Referral to DNO is sent & accepted. | Existing GT Site AQ >732,000 kWh | SPC, SCR, CRF | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-01 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-07
CR270 |  |  | Existing IGT Site AQ >732,000 kWh | SPC, SCR, CRF |  | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-04 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-07
CR270 | Nomination request received with requested SOQ/SHQ values less or equal than that of prevailing but ratio >4 or <24, the request should be rejected |  | Existing GT Site Requested SOQ/SHQ ratio < 4 AQ between (>73,200 kWh / <732,000kWh) | NOM, NMR |  | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-05 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-06
CR270 |  |  | Existing IGT Site Requested SOQ/SHQ ratio > 24 AQ between (>73,200 kWh / <732,000kWh) | NOM, NMR |  | Passed |  | 2018-06-04 | 2018-06-06 |  | 2018-06-04 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-05
CR270 | Nomination request for a class change from 4 to 2, capacity referral should be sent for the AQ >732,000kWh |  | Existing class-4 GT Site, AQ >732,000kWh | NOM, NMR, NRF |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-05 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-07
CR270 |  |  | Existing class-4 IGT Site, AQ >732,000kWh | NOM, NMR, NRF, IGR |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-06 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-07
CR270 | Direct confirmation from 4 to 2 with AQ < 73,200, request should be accepted |  | AQ < 73,200 No Referral | CNF, CFR, TRF, MRI |  | Passed |  | 2018-06-09 | 2018-06-10 |  | 2018-06-06 | Passed | 2018-06-12 | 2018-06-13 | 2018-06-07
COR3283 | Nomination request received for a greenfield site and referred for capacity, no site works reference should be displayed on Nomination referral screen | Nomination Referral acceptance | Greenfield Existing Site, Site works received in NOM file | - Alpha numeric Site works number in NOM file - Site with no existing site works reference stored in SAP | NOM,NMR, NRF | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-07 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-08
COR3283 | Nomination request received for a greenfield site and referred for capacity, no site works reference should be displayed on Nomination referral screen |  | Class - 1, Existing Site, Site works received in NOM file | - Alpha numeric Site works number in NOM file - Site with no existing site works reference stored in SAP | NOM,NMR, NRF | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-07 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-08
COR3283 | Nomination request received for a greenfield site and referred for capacity, no site works reference should be displayed on Nomination referral screen |  | GT, Class 1, DM Site with no site works reference stored in SAP | - Site works present on site and received different number in NOM file, file rejected, NMR should be sent with site works received in NOM File | NOM, NMR, NRF | Passed |  | 2018-06-06 | 2018-06-07 |  | 2018-06-07 | Passed | 2018-06-08 | 2018-06-11 | 2018-06-08
COR3283 | Capacity Amendment request received for exiting site with no site works reference stored in SAP, no site works reference should be displayed on amendment referral screen | Capacity referral acceptance | GT, Class 2, DM Site with no site works reference stored in SAP | Site with no site works reference stored in SAP | SPC, SCR, CRF | Passed |  | 2018-06-06 | 2018-06-07 |  | 2018-06-11 | Passed | 2018-06-08 | 2018-06-11 | 2018-06-12
COR3283 | DNs amends the Site works reference through DN Portal, no historic data should be displayed on portal screen | Meter Asset Selection – Display only screen output | GT, Class 1, DM | Pre-Requisite – Amend the site works from one value to another, on display, only latest record should be displayed | - | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-12 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-13
COR3283 | FOM creation request received for a LPG site, site works reference field should not be editable and SMP creation successful | Successful SMP Creation | LPG SMP Creation - ZSMP | Site works reference filed should be disabled in ZSMP screen for LPG site | - | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-11 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-12
COR3283 | FOM creation request through Xoserve internal screen, site works reference not populated before Save, Site works reference field is optional, hence, request should be saved successfully without site works reference | SMP Creation successful without site work referrence | GT, Sitetype: 0001 - LDZ Direct Connect | 1. SMP Creation through internal screen FOM request | NA | Passed |  | 2018-06-11 | 2018-06-12 |  | 2018-06-11 | Passed | 2018-06-13 | 2018-06-14 | 2018-06-12
COR3283 | FOM creation request through Xoserve internal screen, site works reference not populated before Save, Site works reference field is optional, hence, request should be saved successfully without site works reference |  | Unique site, Sitetype: 0006 NTS Direct Connect | 1. SMP Creation through internal screen FOM request | NA | Passed |  | 2018-06-11 | 2018-06-12 |  | 2018-06-11 | Passed | 2018-06-13 | 2018-06-14 | 2018-06-12
COR3283 | FOM creation request through Xoserve internal screen, site works reference not populated before Save, Site works reference field is optional, hence, request should be saved successfully without site works reference |  | Unique site, Sitetype: 0013 LDZ CSO | 2. CSO should not have site works reference editable FOM request | NA | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-12 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-13
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully | SMP Creation successful with site work referrence provided | GT, Sitetype: 0001 - LDZ Direct Connect | 1. SMP Creation through internal screen MNC request | NA | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-12 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-13
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  | Unique site, Sitetype: 0003 LDZ DIR CON-Tele | 1. SMP Creation through internal screen MNC request | NA | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-06-12 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-13
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  | Unique site, Sitetype: 0019 NTS Direct Connect Tele | 1. SMP Creation through internal screen MNC request | NA | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-06-12 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-13
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  |  |  |  | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-06 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-07
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  |  |  |  | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-12 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-13
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  |  |  |  | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-06-11 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-12
COR3283 | GT SMP creation for MNC request through Xoserve internal screen, site works reference should be editable and populated, SMP should be created successfully |  |  |  |  | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-06-11 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-12
CR273 | Direct Confirmation received with S83 received without S84 (No Need codes), request should be accepted | LIVE Confirmations/Contacts | Class 4 Site Type: GT, AQ < 73200 | Site with existing reusable need codes | CNF, CFR, TRF, MRI | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-31 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-01
CR273 |  |  | Class 4 Site Type: IGT, AQ < 73200 | Site with existing no match need codes | CNF, CFR, TRF, MRI | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-06-01 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-04
CR273 |  |  | LPG site | Site with existing no match need codes | CNF, CFR, TRF, MRI | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-11 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-12
CR273 | Direct confirmation or Contact updates received with duplicate need code within S84, request should be rejected with SPN00010 | Confirmation/Contact Rejection | Class 4 AQ < 73200 Site Type : GT, | - Duplicate New need codes | CNF, CFR, TRF, MRI | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-05-31 | Passed | 2018-05-30 | 2018-05-31 | 2018-05-31
CR273 |  |  | Class 4 AQ < 73200 Site Type : IGT | - Duplicate reusable need codes along with Consent flag Y | CNC, CNR | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-05-31 | Passed | 2018-05-31 | 2018-06-01 | 2018-06-01
CR273 |  |  | Class 4 AQ < 73200 Site Type : IGT, | - Duplicate along with invalid code ( SPN00010 and other SPN0001) | CNF, CFR, TRF, MRI | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-05-31 | Passed | 2018-05-31 | 2018-06-01 | 2018-06-01
CR273 |  |  | Class 4 AQ < 73200 Site Type : GT | - Duplicate along with invalid code ( SPN00010 and other SPN0001) | CNC, CNR | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-31 | Passed | 2018-06-01 | 2018-06-04 | 2018-06-01
CR273 | CNF and Contact update (CNC) received with No need code (No S83 & S84), request should be accepted | LIVE Confirmations/Contacts | Class 3 Site Type : GT, AQ < 73200 | Valid BP exists with need code and Update new Contact without special need | CNF, CFR, TRF, MRI | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-06-04 | Passed | 2018-06-01 | 2018-06-04 | 2018-06-05
CR273 |  |  | Class 4 Site Type : IGT AQ < 73200 | Valid BP exists with need code and Update new Contact without special need | CNC, CNR | Passed |  | 2018-05-31 | 2018-06-01 |  | 2018-06-01 | Passed | 2018-06-04 | 2018-06-05 | 2018-06-05
CR273 |  |  | Class 4 Site Type : GT AQ < 73200 | Contact should be end dated with need code but premise customer name should be retained 2. Site with existing priority values which are already live in system but have a PSR_CODE_EXPIRY_DATE greater to the end date mentioned in C37 | CNC, CNR | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-05 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-12
CR273 | Run EDL for scenarios 1 to 4, all the updates should be captured within EDL for GT sites | Files successful in AMT | Class 3 & 4 Site Type : GT, AQ < 73200 | Run EDL for scenarios 1 to 4 Valid BP exists with special need and Update new Contact without special need (D without special need N without special need) | EDL | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-07 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-08
CR273 | Run IDL for scenarios 1 to 4, all the updates should be captured within IDL for GT sites | Files successful in AMT | Class 3 & 4 Site Type : IGT, AQ < 73200 | Run IDL for scenarios 1 to 4 Valid BP exists with special need and Update new Contact without special need (D without special need N without special need) | IDL | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-08 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-12
CR273 | Run EWS for scenarios 1 to 3, all the updates should be captured within EWS for GT sites | Files successful in AMT | Class 3 & 4 Site Type : GT, AQ < 73200 | Run EWS for scenarios 1 to 3 Valid BP exists with special need and Update new Contact without special need action with U with special need | EWS | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-07 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-08
CR273 | Run IQL for IGT Sites | Files successful in BODS | BW | BW |  | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-01 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-11
CR273 | Run EQL for GT Sites | Files successful in BODS | BW | BW | - | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-04 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-08
CR273 | Confirmation request received with S84 CONSENT_TO_SHARE_DATA_OBTAINED populated as ‘Blank’, request should be rejected at Marketflow with ERR/FRJ response | Confirmation/Contact Rejection | Class 3 Site Type : GT, AQ < 73200 | CNF with S84  CONSENT_TO_SHARE_DATA_OBTAINED = Blank | CNF | Passed |  | 2018-06-06 | 2018-06-07 |  | 2018-06-07 | Passed | 2018-06-08 | 2018-06-11 | 2018-06-08
CR273 |  |  | Class 4 Site Type : iGT AQ < 73200 | CNC with S84  CONSENT_TO_SHARE_DATA_OBTAINED = Blank | CNC | Passed |  | 2018-06-06 | 2018-06-07 |  | 2018-06-07 | Passed | 2018-06-08 | 2018-06-11 | 2018-06-08
CR273 | Confirmation request received with S84 CONSENT_TO_SHARE_DATA_OBTAINED populated as ‘space’, request should be rejected at SAP ISU with rejection code CTT00044 under S84 S72 | Confirmation/Contact Rejection | Class 3 Site Type : GT, AQ < 73200 | CNF with S84  CONSENT_TO_SHARE_DATA_OBTAINED = ‘Space’ | CNF, CFR | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-12 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-12
CR273 |  |  | Class 4 Site Type : iGT AQ < 73200 | CNF with S84  CONSENT_TO_SHARE_DATA_OBTAINED = ‘Space’ | CNC, CNR | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-12 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-12
CR273 | CNC request received for class-1 site with combination of existing and new priority codes priority codes should be rejected with CNF00030 | Contact Rejection | Class 1 AQ > 5.86 | Class 1 AQ > 5.86 | CNC, CNR | Passed |  | 2018-06-09 | 2018-06-10 |  | 2018-06-08 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-11
CR273 | CNC request received for class-4 LSP site with combination of existing and new priority codes priority codes should be rejected with CNF00030 | Contact Rejection | Class 4 AQ > 73200 (LSP) | Class 4 AQ > 73200 (LSP) | CNC, CNR | Passed |  | 2018-06-09 | 2018-06-10 |  | 2018-06-11 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-12
CR273 | Non Registered shipper (Not the owner) sends a CNC file with priority codes, request should be rejected | Contact Rejection | Site Type : GT, AQ < 73200 | Non Registered shipper (Not the owner) sends a CNC file | CNC, CNR | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-12 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-12
CR287 | PTS-SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn post- go live and both the shipper and the asset are the same as at the time of isolation. Shipper will confirm the site and attach the asset from last removal date + 1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation date | Capacity and Commodity billing | Post Go Live Class 4, GT, SSP Isolated and Withdrawn Confirmation status = CO RGMA ONJOB Asset install | Asset installation date is before the stop commodity start date | ONJOB | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-05 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-05
CR287 | PTS-SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn post- go live and both the shipper and the asset are the same as at the time of isolation. Shipper will confirm the site and attach the asset from last removal date + 1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation date | Capacity and Commodity billing | Post Go Live Class 4, GT, LSP Isolated and Withdrawn Confirmation status = CO RGMA ONJOB Asset install | Asset installation date is before the stop commodity start date | ONJOB | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-06-12 | Passed | 2018-06-01 | 2018-06-04
CR287 | SCO-SAME SHIPPER scenario of the GSR process. The site is Isolated only (contract is LIVE) and both the shipper and the asset are the same as at the time of isolation and the gas has flown. On generation of the GSR Contact, the SAP will automatically attach the same asset for last removal date + 1 and the necessary back billing will be triggered with adjustment from the asset installation date | Commodity billing | Post Go Live Isolated Only Class 4, iGT, SSP Shipper Live on Site Auto Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-06-11 | Passed | 2018-06-01 | 2018-06-04 | 2018-06-12
CR287 | PTS-SAME SHIPPER scenario of the GSR process The site is Isolated and withdrawn pre - go live and both the shipper and the asset are the same as at the time of isolation. Shipper will confirm the site and attach the asset from last removal date + 1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation date | Capacity and Commodity billing | Pre-Go Live Isolated and Withdrawn Class 4, LSP, GT Confirmation status = CO RGMA ONUPD Asset install | Asset installation date is before the stop commodity start date | ONUPD | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-20 | Passed | 2018-06-05 | 2018-06-06
CR287 | SSP-SAME SHIPPER Different asset scenario of the GSR process The site is Isolated and withdrawn pre - go live and shipper is same and the asset is different as at the time of isolation. Shipper will confirm the site and attach the asset from last removal date + 1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation date | Capacity and Commodity billing | Pre-Go Live Isolated and Withdrawn Class 4-3, LSP, GT Confirmation status = CF RGMA ONJOB Asset Attach | Asset installation date is before the stop commodity start date | ONJOB | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-21 | Passed | 2018-06-05 | 2018-06-06
CR287 | SCO-SAME SHIPPER scenario of the GSR process. The site is Isolated only (contract is LIVE) and both the shipper and the asset are the same as at the time of isolation. On generation of the GSR Contact, the SAP will automatically attach the same asset for last removal date + 1 and the necessary billing will be triggered with adjustment from the asset installation date | Commodity billing | Pre-Go Live Isolated Only Class 4, LSP, GT Shipper LI on site Auto Attach asset | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-05 | Passed | 2018-06-06 | 2018-06-07 | 2018-06-07
CR287 | SCN_SAME SHIPPER (MOD 425) The site is Isolated only (pre-go live) and the shipper is the same however the asset is different from the asset at the time of isolation. Shipper fails to attach the asset within 10 days after the GSR contact generation date. Xoserve user will then manually attach the asset from last removal date + 1 and neccessary billing will be triggered with adjustment from the asset installation date | Commodity billing | Pre-Go Live Isolated Only Class 4-3, LSP, GT Confirmation status = CF Manual Asset Attach | Asset installation date is before the stop commodity start date | NA | Passed |  | 2018-06-04 | 2018-06-05 |  | 2018-06-12 | Passed | 2018-06-06 | 2018-06-07
CR287 | Non GSR Site and No CMS contact, the site is Isolated pre- go live, asset install received for date before stop commodity start date. Adjustment should be triggered from the start of stop commodity start date | Commodity billing | Pre-Go Live Isolated Only Class 4, LSP, GT Shipper LI on site RGMA ONUPD Asset install | Asset installation date is before the stop commodity start date | ONUPD | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-05 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-07
CR287 | SSP-DIFFERENT SHIPPER scenario, The site is Isolated and Withdrawn and both the shipper and the asset are the different from at the time of isolation. New Shipper will confirm the site and attach the asset from move out Date +1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation | Capacity and Commodity billing | Pre-Go live Isolated and Withdrawn Class 4, SSP, GT RGMA ONUPD Asset attach | Asset installation date after the stop commodity start date | ONUPD | Passed |  | 2018-06-07 | 2018-06-07 |  | 2018-06-13 | Passed | 2018-06-08 | 2018-06-11
CR287 | SSP-DIFFERENT SHIPPER scenario, The site is Isolated and Withdrawn and both the shipper and the asset are the different from at the time of isolation. New Shipper will confirm the site and attach the asset from move out Date +1 within 1 month of the contact creation and the necessary back billing will be triggered with adjustment from the asset installation | Capacity and Commodity billing | Pre-Go live Isolated and Withdrawn Class 4, LSP, GT RGMA ONJOB Asset attach | Asset installation date after the stop commodity start date | ONJOB | Passed |  | 2018-06-08 | 2018-06-11 |  | 2018-06-13 | Passed | 2018-06-12 | 2018-06-13
CR287 | SSP_SAME SHIPPER scenario of the GSR process (MOD425). The site is Isolated and withdrawn with the same shipper and but the asset is different from the one at isolation.There will be a class change (from Class 4 to Class 3). Shipper confirms the site with a change in class (4 to 3), an EMMA case is raised at 'RQ' for the Xoserve user to attach the asset manually at CO status | Capacity and Commodity billing | Pre-Go live Isolated and Withdrawn Class 4-3, LSP, GT Manual Asset attach Switch Status = CO | Asset installation date after the stop commodity start date |  | Passed |  | 2018-06-11 | 2018-06-12 |  | 2018-06-15 | Passed | 2018-06-13 | 2018-06-14
CR251 | Run Existing Report Shipper Performance Pack . | Reports is running successfully | 2A.1 - Count of Est reads for individual month by Shipper & Class 2A.1 - Count of check reads for individual month by Shipper & Class | NA | NA | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-04 | Passed | 2018-06-06 | 2018-06-08 | 2018-06-04
CR292 | Able to generate XDO File with all input data | XDO file processed successfully in BW | MPRNs input file is being processed in BW |  |  | Passed |  | 2018-05-21 | 2018-05-22 |  | 2018-05-21 | Passed | 2018-05-23 | 2018-05-24 | 2018-05-24
XRN4249 | PAF file received for GB Mailing ID with 'P' | Successful Update and ARS and NAC is sent out | LDZ iGT | Address change request from CMS with contact code 'ADD' |  | Passed |  | 2018-05-21 | 2018-05-21 |  | 2018-05-25 | Passed | 2018-05-22 | 2018-05-23 | 2018-06-07
XRN4249 |  | Successful Update and ARS, NAC and EXZ is sent out | LDZ GT | Address change request leading to Exit Zone change from CMS with contact code 'UNC' |  | Passed |  | 2018-05-22 | 2018-05-22 |  | 2018-06-05 | Passed | 2018-05-23 | 2018-05-24 | 2018-06-07
XRN4249 | PAF file received for GB Mailing ID with 'P' | Successful Update and NAC is sent out | LDZ GT | Address change request from ZSMP |  | Passed |  | 2018-05-23 | 2018-05-23 |  | 2018-05-29 | Passed | 2018-05-24 | 2018-05-25 | 2018-06-07
XRN4249 |  | Successful Update and NAC and EXZ is sent out | LDZ GT | Address change request leading to Exit Zone change from ZSMP |  | Passed |  | 2018-05-24 | 2018-05-24 |  | 2018-06-05 | Passed | 2018-05-25 | 2018-05-29 | 2018-06-11
XRN4249 | PAF file received for GB Mailing ID with 'P' updating it to 'X' | Successful Update and NAC is sent out | LDZ iGT | Address change request from CMS with contact code 'ADD' |  | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-06-07 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-11
XRN4249 |  | Successful Update and NAC is sent out | LDZ GT | Address change request from ZSMP |  | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-07 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-11
XRN4249 | Site linked to the GB mailing ID has an elected Shipper | Successful Update and NAC, AES is sent out | LDZ iGT | PAF file received (Address Change) for GB Mailing ID with 'P' updating it to 'P' |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-07 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-11
XRN4249 | PAF file received (Address Change) for GB Mailing ID with 'X' updating it to 'P' | Successful Update, CFR and Portfolio with new PAF indicator | LDZ GT (Class 4) | PSR code change request through CNF |  | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-06-05 | Passed | 2018-05-31 | 2018-06-01 | 2018-06-12
XRN4249 |  | Successful Update, CNR and Portfolio with new PAF indicator | LDZ iGT (Class 4) | PSR code change request through CNC |  | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-06-04 | Passed | 2018-05-31 | 2018-06-01 | 2018-06-12
XRN4249 | PAF file received (Address Change) for GB Mailing ID with 'P' updating it to 'P' | DDU with new FYAQ, FYSOQ and address details is sent out | LDZ GT | Annual FYAQ/FYSOQ is executed |  | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-14 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-14
XRN4249 | PAF file received (Address Change) for GB Mailing ID with 'P' updating it to 'P' | DDU with new EUC and address details is sent out | LDZ GT | Annual EUC is executed |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-06-07 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-12
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard ‘0’ readings on to the MIV file for Must Read invoice | Valid MUR file should be present Read should be '0' GT Meter point | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-05 | 2018-06-06 |  | 2018-06-05 | Passed | 2018-06-07 | 2018-06-08 | 2018-06-06
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from iGT (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard ‘0’ readings on to the MIV file for Must Read invoice | Valid MUR file should be present read should be '0' IGT Meter point IGT MPRNs not present in the MIV file | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-05-29 | Passed | 2018-06-11 | 2018-06-12 | 2018-05-30
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard NULL readings on to the MIV file for Must Read invoice | Valid MUR file should be present read should be NULL GT Meter point | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-07 | 2018-06-08 |  | 2018-05-30 | Passed | 2018-06-11 | 2018-06-12 | 2018-06-01
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from iGT (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard NULL readings on to the MIV file for Must Read invoice | Valid MUR file should be present read should be NULL iGT Meter point iGT MPRs are not present in the MIV file | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-11 | 2018-06-12 |  | 2018-06-07 | Passed | 2018-06-13 | 2018-06-14 | 2018-06-12
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard any CRNs which were FWDS in the last month and auto closed (NATO > CLRD) in 40 Business days in the current month from the must reads invoice | Valid MUR file should be present CRN should not be sent twice in MIV file GT Meter point | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-12 | 2018-06-12 |  | 2018-06-07 | Passed | 2018-06-13 | 2018-06-14 | 2018-06-12
CR367 | MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. Response file from Network (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. Discard any CRNs which were FWDS in the last month and auto closed (NATO > CLRD) in 40 Business days in the current month from the must reads invoice | Valid MUR file should be present CRN should not be sent twice in MIV file IGT Meter point | MURPR00Ss.KSH batch job should successfully validate the file for Header and footer and load into incoming_file table. |  |  | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-06 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-12
CR367 | [5 empty] | Passed |  | 2018-06-12 | 2018-06-13 |  | 2018-06-07 | Passed | 2018-06-14 | 2018-06-15 | 2018-06-08
CR367 | [5 empty] | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-06-06 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-08
CR367 | [5 empty] | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-05-28 | Passed | 2018-06-15 | 2018-06-16 | 2018-05-30
CR367 | [5 empty] | Passed |  | 2018-06-13 | 2018-06-14 |  | 2018-05-30 | Passed | 2018-06-15 | 2018-06-16 | 2018-06-01
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. MRA will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response Network user should download the MJO file first. GT Meter point | NA |  | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-06 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-08
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by MRA. Network will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should download the MJO file first. IGT Meter point | NA |  | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-06-04 | Passed | 2018-05-30 | 2018-05-31 | 2018-06-06
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Generate MJO file and same should be downloaded by Network. MRA will not be able to download MJO file once MRA downloaded it. Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status. | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response IGT user should download the MJO file first. IGT Meter point | NA |  | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-28 | Passed | 2018-06-01 | 2018-06-04 | 2018-05-30
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Networks should be able to see the files uploaded by MRAs in file search | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should upload MJI. Network should be able perform file search for its MRA MPRS GT Meter point | NA |  | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-30 | Passed | 2018-06-01 | 2018-06-04 | 2018-05-30
COR3386 | MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. IGT should be able to see the files uploaded by MRAs in file search | CMS | Valid MUR file should be present Reads are present Comments should be other than 'Asset' in MRA response MRA user should upload MJI. IGT should be able perform file search for the MPRs under its MRAs iGT Meter point | NA |  | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-05-30 | Passed | 2018-06-05 | 2018-06-06 | 2018-05-30
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts.If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Xoserve should be pushing the contact to Networks if they are acting as MRAs Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status." Xoserve should be pushing the contact to Networks if they are acting as MRAs | CMS | Valid MUR file should be present MJI file should contain invalid record and contact should be paused to Xoserve queue GT Meter point | NA |  | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-05-28 | Passed | 2018-06-05 | 2018-06-06 | 2018-05-30
COR3386 | "MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites.MUR file should be received by CMS from BW to log MUR contacts. If MUR file is valid, MUR contacts should be logged to obtain must reads for eligible sites. Xoserve should be pushing the contact to IGT if they are acting as MRAs Response file from MRA (MJI, LTI & RJI file) should be validated and placed in shared area for uploading reads on SAP. System should close the Contacts and update the Contact status." Xoserve should be pushing the contact to Networks if they are acting as MRAs | CMS | Valid MUR file should be present MJI file should contain invalid record and contact should be paused to Xoserve queue IGT Meter point | NA |  | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-06-04 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-06
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-21 | 2018-05-21 |  | 2018-05-23 | Passed | 2018-05-22 | 2018-05-23 | 2018-05-24
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-22 | 2018-05-22 |  | 2018-05-25 | Passed | 2018-05-23 | 2018-05-24 | 2018-05-30
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-23 | 2018-05-23 |  | 2018-05-24 | Passed | 2018-05-24 | 2018-05-25 | 2018-05-24
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-24 | 2018-05-25 |  | 2018-06-01 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-04
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-29 | Passed | 2018-05-29 | 2018-05-30 | 2018-05-30
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-25 | 2018-05-28 |  | 2018-05-23 | Passed | 2018-05-29 | 2018-05-30 | 2018-05-24
CR359 | NA | CMS | Proposed address | Address in SAP |  | Passed |  | 2018-05-28 | 2018-05-28 |  | 2018-05-31 | Passed | 2018-05-29 | 2018-05-30 | 2018-06-01
CR359 | CM S: ADD Contact created in CMS for Shipper through QMP (GT/iGT), - if GT site works is already available it should not be overridden 2. Existing siteworks reference is blank in CMS but populated in QMP file for ADD contact, siteworks will not be stored at CMS and ACR file will flow to SAP without site works reference |  |  |  |  | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-05-24 | Passed | 2018-05-30 | 2018-05-31 | 2018-05-24
CR359 | [5 empty] | Passed |  | 2018-05-28 | 2018-05-29 |  | 2018-05-24 | Passed | 2018-05-30 | 2018-05-31 | 2018-05-24
CR359 | [5 empty] | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-05-24 | Passed | 2018-05-31 | 2018-06-01 | 2018-05-24
CR359 | [5 empty] | Passed |  | 2018-05-29 | 2018-05-30 |  | 2018-05-25 | Passed | 2018-05-31 | 2018-06-01 | 2018-05-30
CR359 | [5 empty] | Passed |  | 2018-05-30 | 2018-05-31 |  | 2018-05-24 | Passed | 2018-06-01 | 2018-06-04 | 2018-05-24
CR359 | [5 empty] | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-05-31 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-01
CR359 | [5 empty] | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-05-29 | Passed | 2018-06-05 | 2018-06-06 | 2018-05-30
CR359 | [5 empty] | Passed |  | 2018-06-01 | 2018-06-04 |  | 2018-05-23 | Passed | 2018-06-05 | 2018-06-06 | 2018-06-01
CR315 | [5 empty] | Passed |  | 2018-05-23 | 2018-05-23 | 2018-05-22 | 2018-05-24 | Passed | 2018-05-24 | 2018-05-24 | 2018-05-24

## Defects
Defect ID | Test Cycle | Detected on Date | Change ID | Primary Business Process Impacted | Priority | Severity | Status | Summary | Target Fix Date | Target Production Deployment Date | Target Production Release
72 | Acceptance | 2018-03-22 | CR359 | CMS | 2-Medium | 2-Medium | Rejected | 'Dependent Street has not updated
73 | Acceptance | 2018-03-26 | XRN4449 | AMT | 2-Medium | 2-Medium | Closed - Deployed to Production | R2 - CR273 - AT: CNF filelevel validation fail in AMT amrketflow | 2018-03-27
74 | Acceptance | 2018-03-27 | XRN4449 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | CR-273_AT: IDL sent with Action = D in B46 segment contains New PSR code details | 28/30/2018
75 | Acceptance | 2018-03-28 | CR359 | CMS | 2-Medium | 2-Medium | Closed - Deployed to Production | Dependent street not displayed in 'Fetchmeterdetails' proxy.
76 | Acceptance | 2018-03-28 | XRN4449 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | CR-273: EDL - IDOC: 80337675 - B39 segment is missing for Brownfield site.
77 | Acceptance | 2018-03-30 | XRN4449 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | CR-273: CNC - S81 record overwritten the S82 details as well in BP
78 | Acceptance | 2018-04-03 | XRN4449 | SPA | 2-Medium | 2-Medium | Rejected | Incorrect Expiry date not Showing for PSR_CODE_EXPIRY_DATE
79 | Acceptance | 2018-04-03 | XRN4249 | - | 2-Medium | 2-Medium | Closed - Deployed to Production | Values update in ADRC fields vary from PAF file values
80 | Acceptance | 2018-04-05 | XRN4249 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | Portfolio files not sent for address change through PAF file
81 | Acceptance | 2018-04-10 | XRN4249 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | PAF ammended for Incorrect Length of Sub Building Name
82 | Acceptance | 2018-04-16 | XRN4249 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | ZREP_EXCP_PF01 report issue
83 | Acceptance | 2018-04-17 | AMT Issue Multiple | AMT | 2-Medium | 2-Medium | Internal Testing Successful | RIQ-AMTGUI is down.
86 | Acceptance | 2018-04-19 | XRN4449 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | EDL and IDL reports sent out with missing few feilds
87 | Acceptance | 2018-04-19 | XRN4249 | SPA | 2-Medium | 2-Medium | Closed - Deployed to Production | PF02 exception reaised for EX Site
88 | Acceptance | 2018-04-19 | XRN4249 | Invoicing | 2-Medium | 2-Medium | Closed as Rejected | XRN4249: Runtime error on character to number conversion: Rejection QRJ00387 expected
89 | Acceptance | 2018-04-20 | UKLP287 |  | 2-Medium | 2-Medium | Closed as Rejected | COM/CAP adjustment billing failed
90 | Acceptance | 2018-04-23 | XRN4449 |  | 2-Medium | 2-Medium | Requires CR | CR_273: AT - CNC cancellation request did not end the existing request with Future effective date.
91 | Acceptance | 2018-04-23 | XRN4449 |  | 2-Medium | 2-Medium | Internal Testing Successful | Data load for DUK_BPID is not completing which is required for EQL & IQL files generation
92 | Acceptance | 2018-04-24 | UKLP287 |  | 2-Medium | 2-Medium | Requires CR | CR278 : Facts update failed during Shipper transfer with class change from 1 to 4
93 | Acceptance | 2018-04-24 | UKLP287 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR 287 : BILL ADJUST table is not updating with BC for a SSP Post MOD -SAME SHIPPER scenario
95 | Acceptance | 2018-04-26 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | UMR RECORDS MISSING IN REC FALLOUT TABLE
96 | Acceptance | 2018-04-26 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | Error log ‘QRJ01002’ failure
97 | Acceptance | 2018-04-26 | XRN4249 |  | 2-Medium | 2-Medium | Ready For Internal Testing | EWS triggered incorrectly for EZ change through PAF ammendment
98 | Acceptance | 2018-04-26 | UKLP367 |  | 2-Medium | 2-Medium | Internal Testing Successful | Allowing '0' and 'null' in Must Read file
99 | Performance | 2018-04-30 | XRN4249 |  | 2-Medium | 2-Medium | Closed - Deployed to Production | FR2.0_PT_CR4249_PAF
100 | Performance | 2018-04-30 | XRN4449 |  | 2-Medium | 2-Medium | Closed - Deployed to Production | FR2.0_PT_CR273_PSR
101 | Acceptance | 2018-05-02 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | UBR RECORDS NOT PRESENT IN FALLOUT
102 | Acceptance | 2018-05-03 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | SFN and CA entries are not showing up in fallout table
103 | Acceptance | 2018-05-06 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | RD1 reads are not captured
104 | Acceptance | 2018-05-06 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | DM REC FALLAOUTS ARE NOT CAPTURED IN FALLOUTS
105 | Acceptance | 2018-05-06 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | Adjustment (CAP/COM) entries are not captured in fallouts
106 | Acceptance | 2018-05-14 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | GB Group PAF file Data Issues
108 | Performance | 2018-05-15 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | PAF file functiona issue in Perofrmance Cycle 1 issue
109 | Performance | 2018-05-15 | UKLP315 |  | 2-Medium | 2-Medium | Assigned | Performance related issue.
110 | Acceptance | 2018-05-17 | UKLP251 |  | 2-Medium | 2-Medium | Requires CR | Read Performance report 1,2,3,4 years logic to be changed
111 | Performance | 2018-05-20 | UKLP315 |  | 2-Medium | 2-Medium | Internal Testing Successful | The program is being run cancelled, for all the 50 jobs, technical team is looking into this issue.
112 | Performance | 2018-05-20 | UKLP315 |  | 2-Medium | 2-Medium | Assigned | The program is being run for large number of records now, like 900k plus and the jobs are finished without any issues. But it is not able to pick all the entries in the system which is around 1900k plus. We need check why it is not able to consider all th
113 | Acceptance | 2018-05-21 | XRN4249 |  | 2-Medium | 2-Medium | Assigned | GB Group / Xoserve Connectivity Issues
114 | Acceptance | 2018-05-21 | XRN4249 |  | 2-Medium | 2-Medium | Assigned | Connectivity Issue between Xoserve and GB Group
115 | Customer Testing | 2018-05-21 | XRN4449 |  | 2-Medium | 2-Medium | Internal Testing Successful | MT - Duplicate rejection reason
116 | Customer Testing | 2018-05-23 | XRN4449 |  | 2-Medium | 2-Medium | Requires CR | Change Enhancement - MT CTT00030
117 | Regression | 2018-05-25 | UKLP112 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR112-RT:Address amendement through CMS is failed.
118 | Regression | 2018-05-28 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | # key appending to PAF
119 | Regression | 2018-05-29 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | Not able to connect to ER1-400 host
121 | Regression | 2018-05-29 | UKLP287 |  | 2-Medium | 2-Medium | Ready for Internal Testing | CR287 RT: GSR notification is expected to be created as “PTS_POST_MOD_SAME_SHIP” in ZMT MUS GSR table in ER1-400. But it was created as “PTS_POST_MOD_DIFF_SHIP”.
122 | Regression | 2018-05-29 | UKLP270 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR-270: Regression Offer sent without Referral for Greenfield & Brownfield sites.
123 | Regression | 2018-05-29 | UKLP273 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR-273: Regression SpecailNeed codes updated failed.
124 | Regression | 2018-05-30 | XRN4249 |  | 2-Medium | 2-Medium | Ready For Internal Testing | XRN4249-RT: DPA is updated through PAF file
125 | Regression | 2018-05-30 | UKLP273 |  | 2-Medium | 2-Medium | Internal Testing Successful | FR2-RT:CR-XRN4249 CNC file configuration issue
126 | Regression | 2018-05-31 | UKLP273 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR-273: CFR outbound Issue - PRIORITY_SERVICE_CNDTN_OVERRID field is missing in AMT file
128 | Regression | 2018-06-04 | UKLP147 |  | 2-Medium | 2-Medium | Rejected | EZ change resulted in EUC change
130 | Regression | 2018-06-06 | XRN4249 |  | 2-Medium | 2-Medium | Rejected | Address amdendment changed PAF indicator from X to N
131 | Regression | 2018-06-07 | UKLP273 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR-273: IDL file failed in Marketflow
132 | Regression | 2018-06-08 | UKLP273 |  | 2-Medium | 2-Medium | Internal Testing Successful | CR_273: S84 consent flag should be set to space in CFR outbound.
133 | Regression | 2018-06-08 | UKLP147 |  | 2-Medium | 2-Medium | Ready For Internal Testing | DDU is not triggered when SP_CATEG is changed along with SOQ update
134 | Regression | 2018-06-08 | XRN4249 |  | 2-Medium | 2-Medium | Internal Testing Successful | DDU failed to generate for FYAQ Calculation job
136 | Regression | 2018-06-11 | UKLP287 |  | 2-Medium | 2-Medium | Assigned | CR 287 RT: Unable to upload read after the contract effective date because the presence of open MRO.
137 | Regression | 2018-06-11 | COR3283 |  | 2-Medium | 2-Medium | Internal Testing Successful | COR3283 _ RT
138 | Regression | 2018-06-12 | UKLP273 |  | 2-Medium | 2-Medium | Assigned | CR-273 RT: New contact details are not sent in EDL file with Action = N
141 | Regression | 2018-06-18 | UKLP287 |  | 2-Medium | 2-Medium | Assigned