## Slide 1: DSC Delivery Sub-Group
04th February 2019

## Slide 2: Agenda (1)
Item | Title | Document Ref | Lead | Action Required From DSG
1. | Welcome and Introductions | Verbal | Chair | Introduce yourself
2. | Meeting Minutes | Verbal | Chair | Approval of the meeting minutes for the previous meeting
3. | AQ Defects | Spreadsheet published on Xoserve.com | Michele Downes/Eamonn Darcy | None – For Information and Discussion
4. | Portfolio Delivery Overview POAP | Slides only | Richard Hadfield/Julie Bretherton | None – For Information and Discussion
5. | Major Release Update |  |  | 
5a. | Release 3 | Slides Only | Peter Hopkins/Tom Lineham | None – For Information and Discussion
5b. | June 19 | Slides Only | Matt Rider | None – For Information and Discussion
5c. | September 19 - EUC | Slides Only | Matt Rider | None – For Information and Discussion
6. | New Change Proposals For Ratification of the Prioritisation Scores |  |  | 
6a. | 4806 - Additional data at National Level to support UIG Allocation validation | Change Proposal | Emma Smith | None – For Information and Discussion
6b. | 4824 - National Grid Transmission Daily Gemini Report |  |  | Removed
6c. | 4841 - MAP Access to UKL data via API (JMDG Use Case 58) |  |  | Removed

## Slide 3: Agenda (2)
Item | Title | Document Ref | Lead | Action Required From DSG
7. | Change Proposal Initial View Representations None for this meeting |  |  | 
8. | Undergoing Solution Options Impact Assessment Review |  |  | 
8a. | XRN4713 - Actual Read following Estimated Transfer Read Calculating AQ of 1 Enduring Solution | Slides Only | Simon Harris | DSG action to approve solution.
9. | Solution Options Impact Assessment Review Completed |  |  | 
9a. | XRN4772 - Composite Weather Variable (CWV) Improvements | Slides Only | David Addison | None – For Information and Discussion
10. | Defect Dashboard | Slides Only | Mark Tullett | None – For Information and Discussion
11. | Miscellaneous |  |  | 
11a. | JMDG/MIS Overview | Slides Only | Simon Harris | For Information and Discussion
11b. | XRN4634 - Data Catalogue | Verbal Update | David Addison | None – For Information and Discussion
11c. | XRN4790 – Introduction of winter read/consumption reports and associated obligation | Change Proposal | Emma Smith | DSG to approve requirements
12. | Action Updates | Action log to be published on Xoserve.com | All | Updates required on DSG owned actions (see below)
13. | AOB | Slides only | Various | TBC

## Slide 4: 3. AQ Defects
The AQ Defects spreadsheet is saved in the DSG pages on xoserve.com listed as 3. AQ defects.

## Slide 5: 4. Portfolio Delivery Overview POAP
The Portfolio POAP is saved in the DSG pages on xoserve.com listed as 4. Portfolio Overview Poap
Only 1 change: Data line item - Data Decommission XFTM & 3447 - XP1 Decommissioning
Implementation date has slipped from 28/02 to 19/03
Closedown date has slipped form 29/04 to 31/05

## Slide 6: R&N Timeline
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
2018 | 2019 | 2020
Release 2
Release 3
Feb-19
June-19
Sept-19 (EUC)
Nov-19
Minor Release D3
CSS CC
RETRO
UIG
Mod 621 – GB Charging
Feb-20
June-20
Nov-20
Assumes February Release continue to be documentation only release
Assumes RETRO will be June 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 36 months
Minor Release D4
CSSB (Procurement)

## Slide 7: 2018 / 2019 R&N Delivery Timeline
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
2018 | 2019 | 2020
R2
PIS
R3
T1 - Imp
Testing
Feb-19
Imp
Jun-19
Design
Build
Testing
Imp
PIS
EUC
Design
Build
Testing
Imp #1
Imp #2
Nov-19
Capture
Governance
Design
Build & UT
ST
SIT
UAT
MT
Imp
PIS
MR
cssB
Potential Activity
Procurement
Retro
Jun-2020
UIG
2019 / 2020
Mod621 – Uk Link Impacts
CUT
ST
SIT
UAT
UT
IDR
Imp
PIS
UKL CUT
UKL ST
UKL AT & RT
UKL PT
UKL RT
Assumes February Release continue to be documentation only release
Assumes RAASP will be June 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 36 months
Code Merge
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Potential Activity
Closedown
T2 - IMP
Closedown
CSS CC
Procurement
High Level Design
Detailed Design
Build / Test

## Slide 8: 2018 / 2019 R&N Governance Timeline
BER Approval
10/04/18
Change Pack Issue
09/11/18
ChMC Scope Approval
12/12/18
EQR Approval
06/02/18
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
2018 | 2019 | 2020
Feb-19
Jun-19
Sep-19 / EUC
Nov-19
MR
cssB
Procurement
RETRO
Potential Activity
Mod621 – Uk Link Impacts
Change Pack Issue 07/12/18
Change Pack Issue
14/06/18
BER Approval 09/01/19
No Governance planned - Awaiting BID Outcome Feb 2019
Assumes February Release continue to be documentation only release
Assumes RAASP will be June 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 36 months
Change Pack Issued
June 18
Change Pack Issue
BER Approval 09/01/10
BER Approval 09/01/19
Change Pack Issue
21/12/18
cssCC
Complete
On track
At risk
Key

## Slide 9: Change Index – R&N Allocated Change
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In Delivery | 27% | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In Delivery | 37% | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In Delivery | 67% | June 2019 | Medium | Xoserve
Feb-19 | 4454 | Cadent Billing – DN Sales (outbound services) | In Delivery | 61% | Feb 2019 | High | Cadent Gas
Feb 19 Doc Release | 4453.1 | Amendment to Job/UPD hierarchies to show ‘irrelevant’ datasets | - |  | Feb 2019 | - | Tbc
 | 4770 | NDM Sample Data – Mod 0654 Delivery | Awaiting HLE | 35% | Feb 2019 | Medium | Tbc
 | - | 1972.7 Ability to Accept Extended Reading Indexes of up to 12 characters | - | - | Feb 2019 | - | Tbc
 | - | 2024 The inclusion of rejection code SAN00001 in the rejection code list | - | - | Feb 2019 | - | Tbc
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | 31% | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories | In Delivery | 52% | June/Sep-2019 | High | Shippers
Minor Release Drop 3 | 4690 | Actual read following estimated transfer read calculating AQ of 1 | In Delivery | 32% | Feb 2019 | Medium | Shippers
 | 4717 | Use of up to date Forecast weather data in first NDM Nominations Run | Undergoing HLSOIA | 35% | Feb 2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP high level solution approved at ChMC | 41% | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | CP high level solution approved at ChMC | 28% | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | CP high level solution approved at ChMC | 29% | November 2019 | Tbc | Shipper

## Slide 10: Change Index – R&N Unallocated External Impacting Changes
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
Unallocated | 4044 | Extension of ‘Must Read’ process to include Annual Read sites | A7 - CP awaiting ChMC solution approval | 41% | Unallocated | Medium | tbc
 | 4474 | Delivery of Retro | A9 - Internal change progressing through capture | 40% | Unallocated | Tbc | DN
 | 4541 | Read Design Gaps - Missing Override Flags In RGMA and Retro Files Linked to Retro (4474) | A9 - Internal change progressing through capture | 39% | Unallocated | Tbc | DN
 | 4584 | Central Switching Services | A9 - Internal change progressing through capture | 21% | Unallocated | Tbc | Shippers
 | 4627 | Consequential Central Switching Services | A9 - Internal change progressing through capture | 57% | Unallocated | Tbc | Shippers
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | A5a - Solution Development | 48% | Unallocated | Tbc | Shipper/DN
 | 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | A5b - Undergoing Solution Impact Assessment | 30% | Unallocated | Tbc | Shippers
 | 4772 | Composite Weather Variable (CWV) Improvements | A5b - Undergoing Solution Impact Assessment | 39% | Unallocated | Tbc | Tbc
 | 4779 | UNC Modification 0657S - Adding AQ reporting to the PARR Schedule reporting suite | A5 - CP in capture with DSG | 40% | Unallocated | Tbc | Tbc
 | 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | A5 - CP in capture with DSG | 27% | Unallocated | Tbc | Tbc
 | 4789 | Updating Shipper Reporting Packs and glossary | A5 - CP in capture with DSG | 9% | Unallocated | Tbc | Tbc
 | 4795 | Amendments to the PARR (520a) reporting | A5c - Undergoing Solution Impact Review | 44% | Unallocated | Tbc | Tbc
 | 4801 | Additional information to be made viewable on DES | A3 – CP within initial view | 27% | Unallocated | Tbc | Tbc
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Awaiting ChMC Solution Approval | 32% | Unallocated | Medium | DN
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Awaiting ChMC Solution Approval | 32% | Unallocated | Medium | DN
 | 4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Awaiting ChMC Solution Approval | 32% | Unallocated | High | DN
 | 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | Awaiting ChMC Solution Approval | 32% | Unallocated | High | DN
 | 4777 | Acceptance of Contact Details Updates | A5a - Solution Development | 30% | Unallocated | Tbc | Shippers
 | 4674 | Corrective meter exchange to be reflective on DES | A9 - Internal change progressing through capture | 32% | Unallocated | Medium | Tbc

## Slide 11: 5. Major Release Update
5a. Release 3
5b. June 19
5c. September 19 - EUC

## Slide 12: 5a. Release 3 Update
January 21st 2019

## Slide 13: XRN4572 – UK Link Release 3
4th February |  | Overall Project RAG Status |  |  | G
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | G | A | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of UK Link Future Release 3 Scope |  |  |  | 
Plan/Time | The progress against each track is as below:- Track 1 (13 Changes) PIS Period officially closed and handed to IS Operations team Overall closure report to be issued to ChMC following completion of Track 2 Track 2 (XRN 4454 Cadent/ NG) All testing phases complete IDR Successfully completed on 23rd/24th January Cutover to commence 1st February over weekend period. Successful completion to be confirmed at DSG on 4th Feb PIS to commence from 4th February |  |  |  | 
Risks and Issues | Issue against XRN 4534 RGMA Validation Rules Production defects now resolved by production operations team AT in progress and due to complete by 8th Feb with RT to commence this week Further progress to be provided in February to ChMC members Next step Continue with AT and RT, monitor level of risk and provide further update to ChMC members in February |  |  |  | 
Cost | Full Delivery costs approved at ChMC in April 2018. Revision to accommodate XRN4454 (Cadent) delivery approved at December ChMC. |  |  |  | 
Resources | Additional resource support to deliver XRN4454 in place SME resource requirements for track 1 PIS, track 2 AT, MT, RT phases is being managed weekly with internal Xoserve teams. |  |  |  | 

## Slide 14: UK Link Release 3 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build & System Test | Acceptance Test | Performance Test | Market Trials | Regression Test | Imp. | PIS
Track 1 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 04/06/18 | 13/08/18 | 07/09/18 | 19/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 1 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 04/06/18* | 13/08/18 | 07/09/18 | 25/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 2 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 30/06/18* | 24/09/18 | 05/11/18 | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
Track 2 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 30/06/18* | Build Complete ST synergised with AT | 14/12/18** | N/A | 14/12/18* | 18/01/18 | 04/02/19 | 08/03/19
RAG Key – Milestones are end dates;
*Closedown expected to finish this week ** Synergised ST and AT date
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed

## Slide 15: 5b. XRN4732 June 19 Release - Update
4th February 2019

## Slide 16: XRN4732 June 19 Release
4th February 2019 |  | Overall Project RAG Status |  |  | G
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | G | A | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of UK Link June 19 Release Scope |  |  |  | 
Plan/Time | There are three changes in scope for delivery as part of the June 19 release. These changes are; XRN4670 - Reject a Replacement Read, Where the Read Provided is Identical to That Already Held in UKL for the Same Read Date 4676 - Reconciliation Issues with Reads Recorded between D-1 to D-5 incorrectly 4687 - Large Supply Point (LSP) Priority Service Register (PSR) Progress on the delivery of the June 19 release is tracking to plan. Design activities completed as scheduled on the 25th January and the project has proceeded into Build and Unit Testing activities as of the 28th January. Preparation of future planned testing activities (i.e. ST, SIT, UAT & RT) has also commenced |  |  |  | 
Risks and Issues | Risks against XRN4732 UAT/RT proposed duration is potentially not long enough Internal resources are potentially not able to provide full support to all projects that are running in parallel Next step Understand the volume of required test cases and discuss and plan the appropriate testing duration based on this Ensure resource requirements are identified and captured via the appropriate allocation process to ensure project activities are not adversely impacted |  |  |  | 
Cost | Full Delivery costs now all approved at ChMC on 9th January 2019 |  |  |  | 
Resources | Currently all resource requirements to support the delivery of this release are being met |  |  |  | 

## Slide 17: XRN4732 June 19 Release – Proposed Timeline
Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19
Initiation |  |  |  |  |  |  |  | 
Design |  |  |  |  |  |  |  | 
 |  |  | Build & UT |  |  |  |  | 
 |  |  |  | ST |  |  |  | 
 |  |  |  |  | SIT |  |  | 
 |  |  |  |  |  | OUAT/RT |  | 
 |  |  |  |  |  |  | Imp | 
 |  |  |  |  |  |  |  | PIS

## Slide 18: 5c. XRN4665 EUC - Update
4th February 2019

## Slide 19: XRN4665 EUC
4th February 2019 |  | Overall Project RAG Status |  |  | A
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | A | A | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of End User Categories Release Scope |  |  |  | 
Plan/Time | Progress on the delivery of the EUC release is so far tracking to plan. Design activities are scheduled to complete on the 1st February with the project on track to proceed into Build and Unit Testing activities as of the 4th February. Further internal discussions to continue with regard to the required timelines for all planned testing activities to ensure that adequate time is allotted to each testing phase and to ensure that the relevant resources will be available to support. |  |  |  | 
Risks and Issues | Risks against XRN4665 Build and unit testing may not complete on time Internal resources are potentially not able to provide full support to all projects that are running in parallel Next step Understand the required timelines from the Vendor and re-plan as required to ensure the plan is realistic and achievable Ensure resource requirements are identified and captured via the appropriate allocation process to ensure project activities are not adversely impacted |  |  |  | 
Cost | Full Delivery costs now all approved at ChMC on 9th January 2019 |  |  |  | 
Resources | Currently all resource requirements to support the delivery of this release are being met |  |  |  | 

## Slide 20: XRN4665 EUC – Proposed Timeline
Nov-18 | Dec-18 | Jan-19 | Feb-19 | Mar-19 | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19
Initiation |  |  |  |  |  |  |  |  |  |  | 
Design |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Build & UT |  |  |  |  |  |  |  | 
 |  |  |  | ST |  |  |  |  |  |  | 
 |  |  |  | SIT |  |  |  |  |  |  | 
 |  |  |  |  | OUAT |  |  |  |  |  | 
 |  |  |  |  |  | PT |  |  |  |  | 
 |  |  |  |  |  | RT |  |  |  |  | 
 |  |  |  |  |  |  |  | Imp - Drop 1 |  |  | Go - Live
 |  |  |  |  |  |  |  |  | PIS |  | 

## Slide 21: 6. New Change Proposals For Ratification of the Prioritisation Scores
6a. XRN4806 - Additional data at National Level to support UIG Allocation validation

## Slide 22: 6a. XRN4806 - Additional data at National Level to support UIG Allocation validation
Change Proposal can be found in the Change pages on xoserve.com

## Slide 23: 7. Change Proposal Initial View Representations
None for this meeting

## Slide 24: 8. Undergoing Solution Options Impact Assessment Review
8a. XRN4713 - Actual Read following Estimated Transfer Read Calculating AQ of 1Enduring Solution

## Slide 25: XRN4713
Actual Read following Estimated Transfer Read Calculating AQ of 1
Enduring Solution

## Slide 26: Overview
XRN4713 was raised to look into a potential enduring solution of re-estimating an estimated Shipper Transfer Read (where the next actual is lower causing a negative consumption)
XRN4690 is in progress for an interim solution to the above where, in the AQ process, if the first variance considered is a negative then roll over the AQ (as the associated positive would not be considered if AQ was to be calculated)

## Slide 27: Considerations
While looking at XRN4713 and the potential way the re-estimation process could work a number of considerations were raised
  Interim solution for XRN4690 is to protect the AQ, mitigating the need for an enduring solution (as other processes can handle negative volumes)
  Long lead time for re-estimation
    Supply Points could have a re-estimated transfer read carried out on it years after the original
      Next cyclic read being lower than the estimate
      Inserted/Replaced read (prior to the transfer) could be higher than the estimate
  Potential to cut across UNC

## Slide 28: Potential Options
Do nothing
  Pro: Solution being put in place by XRN4690 will mitigate the issues being seen with AQ
  Pro: Other downstream processes can handle negative consumption
  Con: Negative consumption (either side) is still not reflective of offtake
Re-estimate
  Con: Risk around re-opening historically closed out position
  Con: Raises issues with end consumer billing (potential backstop date associated with this)
  Con: Requires system changes (Xoserve & Shippers) due to no current process re-estimating (shipper systems may not expect or handle another estimate)
Notification (report to Shippers)
  Pro: Highlight to incoming & outgoing Shippers where a negative consumption is present pre and post a contract change (Shipper Trans / Re-Confirmation / Class Change)
  Pro: Action to then potentially agree a SAR to replace the estimate transfer read
  Pro: Allows Shippers to follow existing process
  Pro: Promotes the increase in actual reads being used for transfers (more accurate AQ, Reconciliation etc)

## Slide 29: 9. Solution Options Impact Assessment Review Completed
9a. XRN4772 - Composite Weather Variable (CWV) Improvements

## Slide 30: 9a. XRN4772 – Composite Weather Variable (CWV) Improvements
High Level Solution Option Assessment

## Slide 31: Change Overview
XRN4772 - Composite Weather Variable (CWV) Improvements
According to UNC Modification 0659 , the requirement is to get the solar radiation and precipitation values considered as a weather variable in order to improve the accuracy of the Composite Weather Variables (CWV). At this time forecast and actual temperature and wind speed are considered by the CWV calculation. By considering these additional variables it is expected that the accuracy of NDM gas nominations and allocations will improve which will have consequential benefits to the gas balancing regime managed within UK Link Gemini. Additional functional changes are to be considered within the scope of this Change Proposal to facilitate future developments in the Composite Weather Variables requested by DESC.
Solution Options
Amend the existing means that data is loaded to UK Link systems to be used in the CWV calculation process
1

## Slide 32: Option 1 - High Level Impact Assessment
1 - Add the new data items into the current file structure
SAP ISU : The AWV and FWV file formats will be modified to include values for solar radiation and precipitation for pre-defined hour. S06 file will be modified to include new weather parameters which is being shared by Demand Estimation team. This will impact to the batch uploading AWV and FWV files that are used in the process of CWV calculations. It will result in modification of table structure in ISU and downstream calculations. Currently the weightages are been stored in the ISU for the 2 parameters i.e. temperature and wind speed. Changes will be made to have the weightage for the new parameters as well and also and a way to be able to amend those values as on required. So a newly interface file was been introduced for the same which will be received from the Demand Estimation Team. SAP PO : Modifications will be required for AWV and FWV files to include new validations. Also configuration will be built for the newly introduced file containing the weightage for the parameters. SAP BW : Modification will be required for the extraction job in order to perform table restructure to include new parameters. Downstream BW changes and BW reporting changes/ new reports will be built.
Impacted Systems
Assumptions
No impacts to Gemini as AIA and CWF files remained unaffected. Impacts to external systems like MIPI are out of scope No frequency changes for the interfaces No market trials is needed Integration Testing in Gemini has only been considered End to End process testing in Gemini is out of scope.
Effort Type | Overall Impact | Release Type | High Level Cost Estimate
SI cost | Medium | Major | TBC
Weather Variable Purchase | N/A | N/A | TBC
Marketflow
SAP PO
SAP ISU
Gemini
SAP BW
CMS
DES
API
Impact
1

## Slide 33: Option 1 - System Impact Assessment
System Component:
Development Type:
Impacted User(s):
Build Type:
Change Description:
Requirement Clarity:
Change Complexity:
Integration Complexity:
Test Data Prep Complexity:
Test Execution:
Regression Testing Impact:
Performance Impact:
SAP ISU | SAP PO |  | SAP BW |  |  | 
AQ | File Formats |  | Reports |  |  | 
Code Change | Configuration Change |  | Code Change |  |  | 
Shippers | Shippers |  | Shippers |  |  | 
Existing | Existing |  | Existing |  |  | 
Code will be amended to consider the new parameters in the files and calculating Forecast / Actual weather values. New process will be configured to load the newly introduced file containing weightage of parameters. | New validations will be configured for the AWV and FWV files. New configuration will be built the newly introduced file containing weightage of the parameters |  | New parameters will be stored in BW and the reports will be built |  |  | 
G | G | G |  |  |  | 
A | A | A |  |  |  | 
G | G | G |  |  |  | 
G | G | G |  |  |  | 
A | A | A |  |  |  | 
G | G | G |  |  |  | 
G | G | G |  |  |  | 
1
Notes: System Component: File Format / Batch Job / Process Code / Report
Development Type: Interface / Online / Report / Workflow / Configuration
End User Impacted: Shipper / DN / NTS / Xoserve / Other
Build Type: New / Existing

## Slide 34: Option 1 - Process Impact Assessment
Process Area | Complexity | File Formats | Exceptions | External Screens | Batch Jobs | Performance Test?
SPA | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Metering (Reads) | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Reconciliation | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Capacity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Commodity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Amendment | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Other | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Rolling AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Formula Year AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
RGMA | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
DSC Service | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Other (Weather Values) | M | Y | N | N | Y | N
1

## Slide 35
10. Defect Summary

## Slide 36: Defect Summary Stats
Stats as per HPQC extract taken on Wednesday 30th January 2019.
Defect Landscape (Open/Closed vrs PGL/New) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | PGL Defects |  |  |  |  |  | Newly Discovered Defects |  |  |  |  |  |  | GRAND RELEASE TOTALS
 | D1 | D2 | D3 | D4 | D5 | TOTAL | D1 | D2 | D3 | D4 | D5 | Not Set | TOTAL | 
Urgent Fix (D1/D2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
Amendment Invoice Task Force | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 14 | 2 | 0 | 32 | 32
R3.06 - 8th February | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 5 | 5
On Hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 5 | 5
Requires CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 5 | 5
Release Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Future Release Dependent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Currently Unallocated | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 36 | 35 | 0 | 0 | 71 | 73
TOTAL OPEN | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 60 | 57 | 2 | 0 | 119 | 121
Closed as Rejected | 0 | 0 | 3 | 14 | 6 | 23 | 0 | 11 | 36 | 33 | 1 | 3 | 84 | 107
Closed as CR | 0 | 0 | 3 | 8 | 0 | 11 | 0 | 0 | 6 | 4 | 0 | 0 | 10 | 21
Closed - Deployed to Production | 0 | 7 | 28 | 58 | 9 | 102 | 9 | 212 | 429 | 186 | 13 | 10 | 859 | 961
TOTAL CLOSED | 0 | 7 | 34 | 80 | 15 | 136 | 9 | 223 | 471 | 223 | 14 | 13 | 953 | 1089
GRAND TOTAL | 0 | 7 | 31 | 73 | 16 | 138 | 9 | 223 | 525 | 276 | 16 | 13 | 1072 | 1210

## Slide 37: R3.05
The below fixes were all deployed to production on the 25th & 29th Jan in Release 3.05. (25th – Portal and BW, 29th – ISU)
Release 3.06 is scheduled for 8th February 2019, but will likely be a smaller release due to the code freeze in place to support Release 3 Track 2.
Defect ID | Status | Description | Release
1133 | Closed - Deployed to Production | Linked with 1206 SAP- SOLR-Performance Issue | R3.05
1186 | Closed - Deployed to Production | SPA - BB03 exception generated for none existing asset (non GSR Contact) | R3.05
1190 | Closed - Deployed to Production | TRF Billing SOQ not provided | R3.05
1206 | Closed - Deployed to Production | Linked to 1133 SAP - LDZ Capacity charge not being sent in TRF for LDZ Direct connect sites opting for NTS optional rate | R3.05
1229 | Closed - Deployed to Production | T1A_ISU_NONCYC_EMC_IN_DY FAILED | R3.05
1254 | Closed - Deployed to Production | SAP BW- DUK_SHPK MPRL Count Mismatch | R3.05
1259 | Closed - Deployed to Production | SAP - Amendment Referral due: 28.12.2018 | R3.05
1261 | Closed - Deployed to Production | SAP BW- IQL File - Rejection reads | R3.05
Defect ID | Status | Description | Deployment Date
1195 | Closed - Deployed to Production | SAP CR 4431 Incorrect Rejection Code | 19th January 2019
1270 | Closed - Deployed to Production | SAP - AQ start date is incorrectly picked by AQ correction tool for XRN4740 scenario. | 23rd January 2019
1082 | Closed - Deployed to Production | DMSP rejection code sent in case of class 3 prime outbound file URS | 30th January 2019
1151 | Closed - Deployed to Production | Gemini data table is getting updated but the details are being sent to Gemini for "LDZ DIR CON Shorthual" sites | 30th January 2019

## Slide 38: Amendment Invoice Impacting Defects – Open 1
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Defect ID | Status | Primary Business Process | Description
1073 | Clarification Required | READS | RN30 exception is getting created incorrectly on a MPRN where class change ( Class 4 to class 3 ) as well as shipper transfer has happened on the same day
1122 | Assigned | READS | Multiple RGMA reads (Final Exchange and Report read) present in the system for the same day leading to incorrect one day rec.
1123 | Awaiting CAB | READS | Incorrect energy calculated for Reconciliation on Check to Check rec where there is a Class change
1125 | Awaiting CAB | READS | SAP - Incorrect reconciliation whenever site visit read is received between two actual reads
1136 | Ready for Internal Testing | INV | SAP: Incorrect reconciliation charge created for backbilling scenario.
1137 | Ready For Assurance | READS | Incorrect energy calculated where an estimated transfer read is created with TTZ of 1 but subsequent read confirms read has not gone round the clock
1138 | DRS completed | INV | SAP- ASP/AML Presentation Mismatch Issue where the is a Class 4 read followed by a RGMA read
1153 | Assigned | RGMA | SAP-CMS reference number for a 'GSR' contact is not populating in AML file
1154 | Ready For Assurance | READS | ASP/AML mismatch for Class 4 sites following creation of an MR07 exception
1172 | Ready For Assurance | INV | SAP- Class 1 NTS Sites populating Incorrect classification as SSP instead of LSP on ASP/AML
1173 | Assigned | INV | Mismatch in ASP file & not captured in mismatch report where legacy data used for Rec
1175 | Awaiting CAB | READS | Presentation issue (AML file) from P&S sites. Linked to defect 720
1178 | Fix In Progress | RGMA | ASP/AML mismatches when Class 4 read is received for the same read date as RGMA read.(creates MR07 exception)
1199 | Ready for Internal Testing | READS | Issue with read entry screen when transfer reads are uploaded with TTZ of 1 and next read also has TTZ of 1
1207 | Retest Failed | RGMA | SAP - Incorrect volume being calculated for Class change scenario for Class 1 site
1210 | DRS Needed | INV | P&S site not populating MPRN in ASP/AML K89 field

## Slide 39
Amendment Invoice Impacting Defects – Open 2
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Note: All Amendment Invoice Impacting defects are now being tagged to the Amendment Invoice Task Force.
Defect ID | Status | Primary Business Process | Description
1214 | Assigned | INV | Re-rec documents spanning across 2 reversed bill periods causing net-off issues and mismatches.
1215 | Assigned | INV | ASP mismatch.. there were 2 manual documents for the same period for net-off but the net-off should happen against one manual document and other document should be reported in the mismatch table.
1216 | Assigned | INV | ASP mismatches due to one of the manual documents is not getting considered in the net-off even thought it should be used.
1217 | Assigned | INV | ASP mismatches due to net-off issues in read insert/break-in scenarios
1218 | Clarification Required | READS | Treatment of Check to Check Reconciliation spanning across Classes
1219 | Clarification Required | READS | SAP: Scenario 5: Issue with DM Estimation following RGMA update for CA/CL site: On back of Defect 906
1220 | Ready for Internal Testing | READS | SAP -Scenario 3 :- Class 3: sites only. Bill order date incorrect - For capped or clamped sites the read used for Rec is using the wrong date. Found as a result of defect 906
1247 | DRS Needed | READS | WC calculation process incorrectly rejecting
1249 | Assigned | INV | SAP - Incorrect values in Supporting Info (ASP & AML) for CSEPs, not showing FYAQ
1252 | Assigned | INV | Missing reconciliation date missing in ASP file for record type K89
1253 | DRS Needed | INV | SAP-Duplicate ASP File for Nov 18 Billing Period
1257 | DRS completed | READS | SAP - UBR read process reversing bill documents incorrectly
1262 | Assigned | INV | SAP-SSMP presentation issue in the ASP file.
1276 | New | INV | SAP BW- Amount of net off is not applied correctly in the AML file
1278 | New | READS | Better Estimate on Twin stream sites does not seem to be allocated aggregate energy correctly
1279 | Assigned | READS | CMS - RFA contact accepted incorrectly even though adjustment start date and end date spans across different confirmation period

## Slide 40: Amendment Invoice Impacting Defects - Closed
The below defects were deployed / closed since the last slides were issued.
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Defect ID | Status | Description | Deployment Date
720 | Closed - Deployed to Production | Charge & Presentation issue (ASP file K88) for Prime and Sub sites | 30th January 2019
958 | Closed - Deployed to Production | Unable to upload reads for Class 4 Prime site using read entry screen for asset removal/change | 30th January 2019
1000 | Closed - Deployed to Production | Class 4 prime rec checking co-terminus reads on sub site which was isolated/no devices allocated | 30th January 2019
1052 | Closed - Deployed to Production | SAP - System has generated an incorrect positive/ Negative volume when there is estimated read in rec calculation. TTZ being considered as -1 | 19th January 2019

## Slide 41: 11. Miscellaneous
11a. JMDG/MIS Overview
11b. XRN4634 - Data Catalogue
11c. XRN4790 – Introduction of winter read/consumption reports and associated obligation

## Slide 42: 11a. JMDG/MIS Overview

## Slide 43: 42 Supplier API [Twin]
Overview
Use case overview
Access to an API service would allow Suppliers to significantly improve the reliability of the switching process for consumers
JMDG progression
Assessed, prioritised, requested project team to deliver an API service with an extended data set to that of the original PCW service.
A Twin fuel service was launched on the 30th November 2018.
42
Twin Fuel
Go-live
Tech Spec
Pricing
Electricity API
MOD Approval
JMDG Decision

## Slide 44: 27 Domestic M-Number Helpline [Gas]
Solution overview
Use case overview
Replace the existing method of providing this service with an online solution
500k calls per year, used by domestic consumers
JMDG progression
Assessed, prioritised and requested project team to provide solution.
Phase 1 – Web Portal to be developed for gas consumers. Will be able to obtain MPRN, Gas Supplier and Transporter name
Phase 2 – Migration of helpline to an enhanced Web Portal
Plan
Phase 1 was delivered in September 2018. Phase 2 has commenced and is on track to launch in June
Testing
Phase 1
Phase 2
Requirements
Gathering
27

## Slide 45: 06 MAPs - Meter Asset Details [Gas]
Solution overview
Use case overview
Meter asset data on UK Link is not correctly maintained by industry participants
A reporting service will be provided to compare the MAM / MAP meter point reference number and meter serial number to that held on UK Link
JMDG progression
Assessed, prioritised, requested project team to analyse requirements with MAPs
06
Engage Maps
Portfolio
Analysis
Phase 1 – MAPs to UKLink meter asset comparison service (Dec ’18) - Completed
Phase 2 – MAP to MAP meter asset comparison service (May ‘19) – In Progress
Phase 3 – Introduction of MAP ID into UKLink (CSSC) – Enduring solution (TBC – would be linked to a UKLink Release schedule)
MAP
Engagement
Process
Modelling
Service
Set-up
JMDG
Phase 1
Phase 2
Design /
Procurement
Development

## Slide 46: 33 Third Party Services [Twin]
Overview
Use case overview
Provide data services to Third Parties
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
23
Permissions
Workshop
Raise MOD 649
A gas data permissions matrix has been created detailing current industry participants permissions to data
  This has been included as part of MOD 649 which aims to move the approval decision making powers from UNC to DSC Contract Management Committee.
The data permissions matrix will help highlight potential API services. MOD 649 will help expedite the governance process to provision data new data services to industry participants while still providing a robust approval process
MRASCo Board has been establishing precedents for third party access approach, which can supplement the gas matrix
A Third Party industry engagement approach will then be created to seek requirements for services
workshop
Engagement Plan
Start Engagement
MOD 649 Approval
JMDG

## Slide 47: 47 & 09 ASC and CT / VT Ratio (Electricity)
Solution overview
Use case overview
Two linked cases involving DNO data:
047: The MIS could also facilitate access to Current/Voltage Transformer (CT/VT) ratio. The ratios would be populated initially by the distribution network operator and can be queried by Parties should discrepancies be identified as part of meter installation, or commissioning and proving tests.
009: Proposed making EAC available to quoting suppliers, and mentioned inclusion of ASC
Initial discussions suggest data will be available but DNOs not keen on multiple access to their databases.
Possibility of ASC access via aggregator model with one authorised API gaining access. This also means less development time.
Timescales: Specification work 3 months. Solution development (subject to BSC for CT/VT) 3 months. Testing I month. Go live May to August 2019.
JMDG progression
Indicative costs received from ECOES service provider. JMDG decided to progress to full solution design. MIS project team prioritised EAC use case for February meeting. Will refocus on this for March’s meeting.
47
Progress to Full Solution

## Slide 48: 01 & 57 Central industry contact database and Industry Escalation Process
Overview
Use case overview
Central repository for industry contact details to underpin industry processes
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
09
Both cases can use the same information contained within current code processes. Initial discussions suggest data available but code administrators generally not willing to co-operate so may need changes to code to enforce compliance.
Timescales: Specification 3 months. Possible modification processes 3-9 months. Solution development 3 months. Testing I month. Go live may be incremental Feb 2019 to November 2019.
JMDG and MPB
decision making
Governance changes
and development

## Slide 49: 09 Estimated Annual Consumption (EAC)
Overview
Use case overview
Make EAC available to quoting supplier
JMDG progression
Indicative costs received from ECOES service provider. JMDG to decide on progression to full solution design based on outcomes of EAC workshop held 28/01/2019 – report provided to JMDG in enclosures for February meeting.
09
Workshop held 28th January to explore potential sources, formats, frequency of the data
Options assessment being presented to February 2019 JMDG
Followed by impact assessment of preferred option and JMDG progress/don’t progress decision
JMDG options
assessment
Second order analysis and
impact assessment
JMDG and MPB
decision making
Implementation
Options assessment
workshop

## Slide 50: 56 FiT Licensee Notifications – Smart meter installs
Options Overview
Use case overview
FiT Licensees would be better able to meet their Supply Licence obligation to administer export payments on metered data whenever possible if a mechanism existed to inform them that a smart meter (which by definition has export metering capability) has been installed on the premises of a FiT Generator
JMDG progression
JMDG agreed high priority progression. Ofgem attending December meeting to participate in discussion on solutions. Gemserv are impact assessing options for delivering the requirements JMDG wanted to progress with their service providers. We will report back in March.
56
ECOES contains meter information (meter serial number, meter type) which would allow FiT Licensees to identify if import MPAN associated with a FiT Generator had a smart meter installed
Either make relevant ECOES data through the Central FiT Registry or combine the two data sets and make available to FiT Licensees elsewhere
Another example of “Trusted Third Party API” requirement which could be handled in aggregate.
An example of where ‘push’ functionality on the API might be of benefit.
JMDG and MPB
Assessment and decision

## Slide 51: 58 MAP API [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a supply meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
58
Change Proposal has been raised and sponsored by Colin Blair (MPB Member)
Project team to provide ChMC feedback to MAPs post meeting to highlight any considerations
Dependency: Change is dependant on MOD and Data Permission Matrix (DPM) Amendment approval
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 52: 59 UKRPA Access to Gas data [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
59
Change Proposal has been raised
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 54: 11b. XRN4634 - Data Catalogue
Verbal update to be provided by David Addison

## Slide 55: XRN4790 – Introduction of winter read/consumption reports and associated obligations (MOD0652)
Approval of requirements

## Slide 56: Info
MOD sets the obligation to provide the reads and submit amended Winter Consumption where one has failed to calculate
Expected to be zero value change as UIG resource building reports
Expected to deliver via business intelligence service but can also email

## Slide 57: Requirements
Consider for what date should report be run (assign to responsible Registered User)

## Slide 58: 12. Action Updates
The latest Action Log spreadsheet will be saved on xoserve.com

## Slide 59: 13. AOB