## Open AQ Issues
Defect No. | Description | Volume | Customer Impact | Priority | Expected Fix Date | Expected Consumption Correction Date | Expected AQ Correction Date | Tracked by AMS/AML Team? | Reason why no impact to Amendment Invoice | Update as of 14th February 2019 | Status | Issue Profiled | Date Affected Meter Points Issued
1052 | The energy calculation is incorrect where there is an estimated read used for reconciliation, the TTZ of -1 is being used in the calculation. | 947-1049 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | Deployed 19/01/2019 | 15th February 2019 | 15th February 2019 | Yes |  | All data upto 10th November 2018 has been fixed. AQs will be recalculated mid February & issued in the NRL files at the end of February. The revised AQs will be effective from 1st March. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1045 | Following read replacement prior to a shipper transfer the reconciliation is missing any read between the replaced read and the shipper transfer read. The replaced read should reconcile back to the next subsequent read, instead it is reconciling to the shipper transfer read. | 1260 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium (3) | Deployed on 18/09/2018 | 15th February 2019 | 15th February 2019 | Yes |  | AQs will be recalculated mid February & issued in the NRL files at the end of February. The revised AQs will be effective from 1st March. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
863 | Incorrect volume and energy calculated where a read is replaced via the UKLink SAP screens (by Xoserve users) | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low | Deployed 18/09/2018 | 15th March 2019 | 15th March 2019 | Yes |  | Profiling for this defect was sent on 11th February 2019 AQs will be recalculated mid March & issued in the NRL files at the end of March. The revised AQs will be effective from 1st April. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | No
XRN4740 | When a Site Visit read is submitted a Check to Check Reconciliation is carried out back to the previous Site Visit read. When the AQ calculation is triggered the energy between each cyclic read as well as the energy calculated between the Check to Check Read is being used by the AQ calculation process, resulting in increased energy and an incorrect AQ value. | Approx 17000 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | 15/02/2019 | 15th February 2019 | 15th February 2019 | No | Does not affect the creation of a reconciliation or the charges. | The AQ has been recalculated using the 'AQ calculation Tool' in January, the amended AQ is effective from 1st February 2019. The revised AQs were issued on the NRL files at the end of January. Once the enduring fix has been implemented the AQs will be recalculated again for 1st April effective date. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1122 | Incorrect consumption on RGMA removal MRO when there is an RGMA update for the removal date. | approx. 2,000 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low | 05/04/2019 | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | The enduring fix is on target. The AQs will be calculated for 1st April effective date. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1125 | Where a Site Visit for a Class 4 Sites with AMR fitted is received and accepted and a subsequent cyclic read has already been processed, the system is not recognising the site visit read (Check Read) and is not recalculating the volume/energy between the site visit read and the cyclic read. | 923 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Low | Deployed 31/01/2019 | Completed | 15th February 2019 | Yes | Does not affect the creation of a reconciliation or the charges. | AQs will be recalculated mid February & issued in the NRL files at the end of February. The revised AQs will be effective from 1st March. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1089 | On the final read (FINX) submitted on a meter update (RGMA) the system is using the round the clock count (TTZ) on the FINX read and for the transfer read where the asset update read is used as the transfer read. This creates an incorrect inflated volume between the asset update read (FINX) and the opening read (OPNT). | Approx. 350 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium | Deployed 11/01/2019 | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | AQs will be recalculated mid March & issued in the NRL files at the end of March. The revised AQs will be effective from 1st April. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
XRN4676 | Where a cyclic read is present for the same day as an final (FINT) read (outgoing shipper transfer read) the system is currently applying an incorrect/duplicate energy and creates reconciliation charges against the one day reconciliation between cyclic and Final read | 30k | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium | 2019-06-01 | 15th March 2019 | 15th March 2019 | Yes |  | On target to correct consumption and correct AQ AQs will be recalculated mid March & issued in the NRL files at the end of March. The revised AQs will be effective from 1st April. The Formula Year AQ (FYAQ) will also be updated, effective 1st April 2019. | Open | Yes | 2018-12-12
1073 | Where an asset exchange is received & accepted post a Class change from any class to class 3, volume/consumption is calculated incorrectly which results in an incorrect AQ. | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | 2019-02-20 | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | Analysis ongoing to see if the defect can be fixed in line with all other AQ defects before 1st April 2019 | Open | No
1266 | Where there has been a consumption adjustment applied for a period which includes the Final Transfer Read (FINT) the AQ calculation process is not taking the comsumption adjustment into consideration | 194 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | TBC | 15th March 2019 | 15th March 2019 | No | Does not affect the creation of a reconciliation or the charges. | Defect being assessed. | Open | No

## Closed AQ Issues
Defect No. | Description | Volume | Customer Impact | Priority | Expected Fix Date | Expected Consumption Correction Date | Expected AQ Correction Date | Tracked by AMS/AML Team? | Reason why no impact to Amendment Invoice | Update as of 14th February 2019 | Status | Issue Profiled | Date Affected Meter Points Issued
1043 | The AQ calculation process should only consider consumption history on or after the backstop date. Functionality prior to fix on 12th July 2018 was not considering any reads where the read date is equal to the backstop date. Therefore a revised monthly AQ will not be calculated. This scenario will apply in the following cases: 1. New meter points confirmed on or after 1st June 2017 where the confirmation effective date is the backstop date for AQ calculation process. 2. Following an AQ Correction, the effective date of the corrected AQ is the backstop date. | 9922 | Potential impacts: The consumption period is reduced for the purposes of the monthly AQ process. | Low | Deployed on 12/07/2018 | Completed | Completed | No | Does not have an impact on the energy used for Reconciliation process. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | 2018-07-11
937 | Where a consumption adjustment is received for a DM meter point (Class 1 and 2 only) during the period of an asset update, the consumption adjustment is rejected. Only affects Class 1 and 2 meter points. | TBC. Linked to defect 974. | For the AQ process the original consumption will be used, not the revised consumption. | Low | Deployed on 08/08/18 | N/A | N/A | No | Reconciliation is not created. | N/A | Closed | Yes | 2018-07-11
1067 | Where an estimated transfer read is replaced (via the Shipper Agreed read process) the consumption and energy calculated from the replaced read is incorrect. | 67474 | The incorrect energy will be used in the AQ process for calculating a revised AQ. | Medium (1) | Deployed | Completed | Completed | No | Does not have an impact on the energy used for Reconciliation process. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 30/07/2018 issued on 03/08/18
985 | Where an RGMA asset update is submitted and accepted between D & D+5 of the effective date of the transfer, the energy is calculated incorrectly. Volume & energy for asset read is being calculated, should be recorded as zero as the volume & energy is calculated from transfer read. | 11,855 as at 7th August | The incorrect energy will be used in the AQ process for calculating a revised AQ | Medium (2) | Deployed in R2.02 on 27/07/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 04/07/2018 issued on 06/07/18
1040 | Where a read is received for a Class 4 Prime & Sub site the read is not triggering an AQ calculation | 49 | No AQ for Class 4 P&S sites. | Low | Deployed as part of R2.05 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | Will be provided once the fix is deployed
XRN4742 | When a shipper carried out a reconfirmation the new UKLink system required a reading for the Final read (FINT) and the Opening read (OPNT). It was an agreed approach at the time of migration to load a consumption of zero for OPNT and FINT reads and leave all the consumption against the latest read. This was carried out for 175k NDM Supply Meter Points. This approach was taken as it was deemed too difficult to apportion in the Energy, however will/has caused incorrect AQ and possibly FYAQ calculations since Nexus Go Live | 156k | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | 2018-11-09 | Completed | Completed | No | Does not affect the creation of a reconciliation or the charges. | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | TBC
933 | Where an estimated transfer read is generated and loaded with a TTZ (Through the Zeros) count of one, on receipt of the next actual read the energy calculated is incorrect. Estimate loaded with TTZ of 1, when Shipper replaces the read the TTZ count is used to calculate the energy. A negative consumption should have been created. | 166 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | Deployed in R1.21 on 04/05/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | Yes | The MPRNs known as at 04/07/2018 issued on 06/07/18
947 | Where an incoming Shipper is supplying the Opening Read D-5 and D-1 of the actual shipper transfer date, the outgoing shipper is also submitting a cyclic read within this transfer window which is causing the volume/energy to be calculated incorrectly. This is affecting the AQ values calculated. | 4242 | The incorrect energy will be used in the AQ process for calculating a revised AQ | High | Deployed on 14/10/2018 | Completed | Completed | Yes |  | Defect fixed, consumption corrected & AQ's re-calculated & issued end of November 2018 in the .NRL files. Revised, corrected AQs will be effective 1st December 2018. | Closed | No | TBC
| For AQ Corrections submitted & accepted in December 2018 with an effective date of 1st January 2019, UKLink did not update the AQ correctly. | 1122 | Incorrect values submitted to Shippers and used in gas allocations | Medium | 2019-01-09 | N/A | N/A | No | Does not affect the creation of a reconciliation or the charges. | AQs corrected in Gemini for the 1st to 4th January within GFD+5 correcting gas allocations. Uklink updated with correct AQ & FYAQ and affected shippers notified on 10th january 2019 of the correct values. DEs updated from 11th january 2019. | Closed | Yes | 2019-01-10
1137 | Where an estimated transfer reading has been created with a round the clock of 1 and the subsequent actual read confirms the meter/convertor has not clocked a negative consumption should be created, instead we are seeing large consumptions. | N/A | The incorrect energy will be used in the AQ process for calculating a revised AQ | N/A | N/A | N/A | N/A | Yes |  | This is a duplicate of defect 1052. Closed 07/02/2019. | Closed | No | N/A