## Slide 1: DSC Delivery Sub-Group
18th March 2019

## Slide 2: Agenda (1)
Item | Title | Document Ref | Lead | Action Required From DSG
1. | Welcome and Introductions | Verbal | Chair | Introduce yourself
2. | Meeting Minutes | Verbal | Chair | Approval of the meeting minutes for the previous meeting
3. | Defects Update |  |  | 
3a. | AQ defects | Spreadsheet published on Xoserve.com | Michele Downes/Eamonn Darcy | Standing agenda item – for information (if there is an update)
3b. | Defect Summary | Slides Only | Mark Tullett | None – For Information and Discussion
4. | Portfolio Delivery Overview POAP | Slides only | Richard Hadfield/Julie Bretherton | Standing agenda item – for information (if there is an update)
5. | Major Release Update |  |  | 
5a. | Release 3 | Slides Only | Tom Lineham | Standing agenda item – for information (if there is an update)
5b. | February 19 | Slides Only | Matt Rider | Standing agenda item – for information (if there is an update)
5c. | June 19 | Slides Only | Matt Rider | Standing agenda item – for information (if there is an update)
5d. | End User Categories 19 | Slides Only | Matt Rider | Standing agenda item – for information (if there is an update)
5e. | November 19 | Slides Only | Tom Lineham | Standing agenda item – for information (if there is an update)

## Slide 3: Agenda (2)
Item | Title | Document Ref | Lead | Action Required From DSG | 
6. | New Change Proposals For Ratification of the Prioritisation Scores |  |  |  | 
6a. | XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | CP published on Xoserve.com | Simon Harris |  | Ratification of the Prioritisation Score
6b. | XRN4866 - UIG Recommendation – removal of validation on uncorrected read | CP published on Xoserve.com | Simon Harris |  | Ratification of the Prioritisation Score
6c. | XRN4869 - DC Exit Programme |  |  |  | Removed
6d. | XRN4871 - Modification 0665 – Changes to Ratchet Regime | CP published on Xoserve.com and Slides | David Addison |  | Ratification of the Prioritisation Score
6e. | XRN4876 - Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | CP published on Xoserve.com |  |  | Removed
6f. | XRN4850 - Notification of Customer contact details to Transporters | CP published on Xoserve.com | Ellie Rogers |  | Ratification of the Prioritisation Score
7. | Change Proposal Initial View Representations |  |  |  | 
7a. | XRN4645 - The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) |  |  |  | Removed
8. | Undergoing Solution Options Impact Assessment Review |  |  |  | 
8a. | XRN4713 - Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) |  |  |  | Removed
8b. | XRN4803 - Removal of validation for AQ Correction Reason 4 | Slides Only | Simon Harris |  | DSG to validate the preferred solution option
9. | Solution Options Impact Assessment Review Completed None for this meeting |  |  |  | 

## Slide 4: Agenda (3)
Item | Title | Document Ref | Lead | Action Required From DSG
10. | Miscellaneous |  |  | 
10a. | IX Update | Slides Only | John Woodward | None – For Information and Discussion
10b. | XRN4864 - Supply of Meter Point data as part of the PARR Reports |  |  | Removed
11. | Change Management Committee Update | Slides Only | Richard Johnson | None – For Information and Discussion
12. | UIG Update (post ChMC) | Slides Only | Leanne Jackson | None – For Information and Discussion
13. | JMDG Update | Slides Only | Simon Harris | None – For Information Only as no change
14. | Action Updates | Action log published on Xoserve.com | All | Updates required on DSG owned actions (see below)
15. | AOB | Slides only | Various | TBC
15a. | XRN4857 – Report Review | Verbal | Jane Goodes | None – For Information and Discussion
15b. | XRN4686 – Smart Metering report | Slides only | Richard Johnson | None – For Information and Discussion
15c. | XRN4853 - Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | Verbal | Richard Johnson | None – For Information and Discussion

## Slide 5: 3. Defects
3a. AQ Defects
3b. Defect Summary and Dashboard

## Slide 6: 3a. AQ Defects
The AQ Defects spreadsheet to be saved in the DSG pages on xoserve.com listed as 3a. AQ defects.

## Slide 7
3b. DSG Defect Summary

## Slide 8: Defect Summary Stats
Stats as per HPQC extract taken on Wednesday 13th March 2019.
Defect Landscape (Open/Closed vrs PGL/New) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | PGL Defects |  |  |  |  |  | Newly Discovered Defects |  |  |  |  |  |  | GRAND RELEASE TOTALS
 | D1 | D2 | D3 | D4 | D5 | TOTAL | D1 | D2 | D3 | D4 | D5 | Not Set | TOTAL | 
Urgent Fix (D1/D2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1
Amendment Invoice Task Force | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 10 | 2 | 0 | 23 | 23
R3.08 - 8th March | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 7 | 0 | 1 | 18 | 18
On Hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2
Requires CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 4 | 4
Release Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 5 | 5
Future Release Dependent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Currently Unallocated | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 21 | 29 | 0 | 0 | 50 | 52
TOTAL OPEN | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 51 | 49 | 2 | 1 | 103 | 105
Closed as Rejected | 0 | 0 | 3 | 14 | 6 | 23 | 0 | 11 | 39 | 37 | 1 | 3 | 91 | 114
Closed as CR | 0 | 0 | 3 | 8 | 0 | 11 | 0 | 0 | 6 | 4 | 0 | 0 | 10 | 21
Closed - Deployed to Production | 0 | 7 | 28 | 58 | 9 | 102 | 9 | 212 | 443 | 200 | 13 | 10 | 887 | 989
TOTAL CLOSED | 0 | 7 | 34 | 80 | 15 | 136 | 9 | 223 | 488 | 241 | 14 | 13 | 988 | 1124
GRAND TOTAL | 0 | 7 | 31 | 73 | 16 | 138 | 9 | 223 | 533 | 286 | 16 | 14 | 1091 | 1229

## Slide 9: R3.08
The below fixes were all deployed to production between the 1st and 8th March.
Release 3.09 is scheduled for 22nd March 2019.
The below fixes were deployed as urgent.
Defect ID | Status | Description | Release
1120 | Closed - Deployed to Production | SAP - AQs at the EUC level is not equal to the CSEP Connection | R3.08
1129 | Closed - Deployed to Production | SAP- Incident MBG/MBO | R3.08
1144 | Closed - Deployed to Production | SAP-Principle Street Not Populating in TSI File | R3.08
1192 | Closed - Deployed to Production | SAP - AQ values in METER_EUC_AQ_CLASS | R3.08
1197 | Closed - Deployed to Production | SAP: CAP and COM billing job | R3.08
1221 | Closed - Deployed to Production | SAPBW: Data issue in Switch DSO | R3.08
1231 | Closed - Deployed to Production | Linked to 1233 :SAP ISU (SPA)- Issue with Objection processing | R3.08
1233 | Closed - Deployed to Production | Linked 1231 : SAP-US work items - Exception is currently raised on D-2 for Greenfield and Single to Shared scenario, this is required to be raised only on D day | R3.08
1244 | Closed - Deployed to Production | SAP ISU : Issue with CFR file. Two S75 details are getting generated. | R3.08
1256 | Closed - Deployed to Production | Non opening read from old shipper on new shipper effective date accepted incorrectly through UBR process (Class 3) | R3.08
1260 | Closed - Deployed to Production | GSR - Incorrect contact type is getting created if the device install and removal is on the same day | R3.08
1265 | Closed - Deployed to Production | SAP AQ- Winter Consumption validation process does not capture the NDMSOQ change made as part of the EUC update | R3.08
1271 | Closed - Deployed to Production | AQ Correction Issue: AQR file processed incorrectly | R3.08
Defect ID | Status | Description | Release
1292 | Closed - Deployed to Production | Incorrect AQ information sent to gemini in monthly AQ file | 27th Feb
1209 | Closed - Deployed to Production | SAP - Meter Assets Invoice Oct 2018 missing charges | 8th March
1312 | Closed - Deployed to Production | Code fix for DUK_MPUS | 8th March

## Slide 10: Amendment Invoice Impacting Defects
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
Defect ID | Status | Primary Business Process | Description
1122 | Clarification Required | READS | Multiple RGMA reads (Final Exchange and Report read) present in the system for the same day leading to incorrect one day rec.
1173 | DRS completed | INV | Mismatch in ASP file & not captured in mismatch report where legacy data used for Rec
1178 | Ready For Assurance | RGMA | ASP/AML mismatches when Class 4 read is received for the same read date as RGMA read.(creates MR07 exception)
1199 | Ready For Assurance | READS | Volume and energy calculated wrong where Read insert between actual and estimated shipper transfer with TTZ of 1 (inseted using manual read screen). Affects AQ & charge calculation for Amendment invoice
1207 | Ready For Assurance | RGMA | SAP - Incorrect volume being calculated for Class change scenario for Class 1 site
1218 | Clarification Required | READS | Incorrect energy calculated: Treatment of Check to Check Reconciliation spanning across Classes
1219 | Clarification Required | READS | SAP: Issue with DM Estimation following RGMA update for CA/CL site: Potential charge issue.
1247 | Awaiting CAB | READS | Linked with 1105 WC calculation process incorrectly rejecting & resulting in incorrect volume & energy calculated. Charges Excluded from invoice.
1249 | Awaiting CAB | INV | SAP - Incorrect values in Supporting Info (ASP & AML) for CSEPs, not showing FYAQ
1252 | Awaiting CAB | INV | Missing reconciliation data missing in ASP file for record type K89
1262 | Ready for Internal Testing | INV | SAP-SSMP presentation issue in the ASP file.
1278 | Failed assurance | READS | Better Estimate on Twin stream sites does not seem to be allocated aggregate energy correctly
1308 | Assigned | INV | SAP- where a reconciliation covers pre go live period the original vairances are created manually causing mismatch issues.
1314 | New | INV | SAP - Incorrect Netting off seen within ASP files when there are multiple re-recs within same month for the same REC period
1315 | New | INV | SAP- Amendment Invoice to prevent Pre LIS
1318 | New | INV | Revised energy issue

## Slide 11: Amendment Invoice Impacting Defects - Closed
The below defects were deployed / closed since the last slides were issued.
Key: | 
 | Amendment Invoice Task Force Defects
 | Standard Defect
* Rejected as it was a duplicate of an already logged defect.
Defect ID | Status | Description | Dep/ Close Date
1153 | Closed - Deployed to Production | SAP-CMS reference number for a 'GSR' contact is not populating in ASP file | 27th Feb
1276 | Closed - Deployed to Production | SAP BW- Amount of net off is not applied correctly in the AML file | 1st Mar
1277 | Closed - Deployed to Production | Reconciliation charges not getting created where there is a consumption adjustment over the period of the replacement read | 1st Mar
1288 | Closed as Rejected | SAP ISU Metering - Net-off volume not calculated for prime sites when sub sites have volume. | 4th Mar
1298 | Closed as Rejected | SAP BW: Mandatory data items missing from AML file: RECONCILIATION START DATE and RECONCILIATION_END_DATE | 4th Mar
1138 | Closed - Deployed to Production | SAP- ASP/AML Presentation Mismatch Issue where the is a Class 4 read followed by a RGMA read. (Linked to defect 1216) | 8th Mar
1214 | Closed as Rejected | Re-rec documents spanning across 2 reversed bill periods causing net-off issues and mismatches in ASP file. | 8th Mar
1216 | Closed - Deployed to Production | ASP mismatches due to one of the manual documents not getting considered in the net-off. (Linked to defect 1138) | 8th Mar
1220 | Closed - Deployed to Production | SAP - Class 3: sites only. For capped or clamped sites the read used for Rec is using the wrong date. Found as a result of defect 906 | 8th Mar
1253 | Closed - Deployed to Production | SAP-Duplicate ASP File for Nov 18 Billing Period | 8th Mar
1294 | Closed as Rejected | Allocated energy updated outside closeout through reads process (UDR) for Class 2 sites where convertor is installed. | 8th Mar

## Slide 12: 4. Portfolio Delivery Overview POAP
The Portfolio POAP to be saved in the DSG pages on xoserve.com listed as 4. Portfolio Overview POAP
Changes to the POAP are:
EUC – minor changes to Implementation A & B
A was 06/06 – Now 03/08
B was 09/09 – Now 31/08

## Slide 13: R&N Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
June-19
Sept-19 (EUC)
Nov-19
CSS CC
RETRO
UIG
Mod 621 – GB Charging
Feb-20
June-20
Nov-20
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Minor Release D4

## Slide 14: 2019 / 2020 R&N Delivery Timeline
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
Build
Testing
Imp
PIS
EUC
Build
Testing
Imp #1
PIS
Imp #2
PIS
Nov-19
Capture
Initiation
Design
Build & UT
ST
SIT
UAT
Reg / Pen Test
Imp
PIS
MT
MR
Potential Activity
CSS CC
HLD
Detailed Design
System / Internal Acceptance / Pen Testing
SIT / Reg Test
MT
IMP
Retro
Nov-2020
UIG
2020
ST
SIT
SUPT
UKL PT
UKL ST
UKL AT & RT
UT
UKL RT
UAT
IDR
IMP
PIS
Mod621 – Uk Link Impacts
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
J | F | M | A | M | J | J | A | S | O | N | D

## Slide 15: 2019 / 2020 R&N Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes February Release continue to be documentation only release
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this is all potential activity within UK Link over the next 24 months
Jun-19
BER Approval 09/01/19
Sep-19 / EUC
BER Approval 09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
Change Pack Issue
08/05/19
MR
Potential Activity
ChMC Scope Approval
10/04/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
Potential Activity
Governance Approval dates tbc
BER Approval
10/04/19

## Slide 16: Change Index – R&N Allocated Change
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Proposed R&N Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In Delivery | 27% | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In Delivery | 37% | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In Delivery | 67% | June 2019 | Medium | Xoserve
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | 31% | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories | In Delivery | 52% | June/Sep-2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP high level solution approved at ChMC | 41% | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | CP high level solution approved at ChMC | 28% | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | CP high level solution approved at ChMC | 29% | November 2019 | Tbc | Shipper

## Slide 17: Change Index – R&N Unallocated External Impacting Changes
Proposed Release | XRN | Change Title | Current Status | Xos Proposed Prioritsation Score | Indicative R&N Release | Complexity | Finance
Unallocated | 4777 | Acceptance of Contact Details Updates | A7 - CP awaiting ChMC solution approval | 32% | Minor Release Drop 4 | Tbc | Shippers
 | 4795 | Amendments to the PARR (520a) reporting |  | 44% | Minor Release Drop 4 | Tbc | PAC
 | 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | A7 - CP awaiting ChMC solution approval | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4803 | Removal of validation for AQ Correction Reason 4 | A7 - CP awaiting ChMC solution approval | 71% | Minor Release Drop 4 | Tbc | Shippers
 | 4871 | Modification 0665 – Changes to Ratchet Regime | A2 - CP proposed for ChMC | 27% | Minor Release Drop 4 | Tbc | Tbc
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | A2 - CP proposed for ChMC | 28% | Nov-19 | Tbc | Tbc
 | 4474 | Delivery of Retro | A9 - Internal change progressing through capture | 48% | 2020 | Tbc | DN
 | 4584 | Central Switching Services | A9 - Internal change progressing through capture | 20% | 2020 | Tbc | Shippers
 | 4627 | Consequential Central Switching Services | B1 - Start Up In Progress (Awaiting PAT/RACI) | 51% | 2020 | Tbc | Shippers
 | 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | A5 - CP in capture with DSG | 47% | Unallocated | Tbc | Tbc
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | A5a - Solution Development | 44% | Unallocated | Tbc | Shippers/DN
 | 4772 | Composite Weather Variable (CWV) Improvements | A7 - CP awaiting ChMC solution approval | 44% | Unallocated | Tbc | Shippers / DN
 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | A2 - CP proposed for ChMC | 41% | Unallocated | Tbc | Tbc
 | 4876 | Changes to PARR reporting – provide further data to PAFA to aid analysis of reporting performance | A2 - CP proposed for ChMC | 34% | Unallocated | Tbc | Tbc
 | 4850 | Notification of Customer Contact Details to Transporters | A2 - CP proposed for ChMC | 33% | Unallocated | Tbc | Tbc
 | 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | A5b - Undergoing Solution Impact Assessment | 32% | Unallocated | Tbc | Shippers
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | A2 - CP proposed for ChMC | 32% | Unallocated | tbc | tbc
 | 4801 | Additional information to be made viewable on DES | A5 - CP in capture with DSG | 29% | Unallocated | Tbc | Tbc
 | 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | A5 - CP in capture with DSG | 29% | Unallocated | Tbc | Tbc

## Slide 18: 5. Major Release Update
5a. Release 3
5b. February 2019
5c. June 2019
5d. EUC 2019
5e. November 19

## Slide 19: 5a. Release 3 - Update

## Slide 20: XRN4572 UK Link Release 3
27th February 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Track 1 (13 Changes) – Implemented. PIS Complete. Track 2 (XRN 4454 Cadent/ NG) – Implemented. PIS concluded on 08/03 Project Closure Report to be issued to ChMC in April |  |  | 
Risks and Issues | Issue against XRN 4534 RGMA Validation Rules (Unable to Implement in Track 1) Implemented on 01/03 PIS to conclude on 15/03 |  |  | 
Cost | Full Delivery costs approved at ChMC in April 2018. Revision to accommodate XRN4454 (Cadent) delivery approved at December ChMC. |  |  | 
Resources | Delivery and PIS completed. No further resource requirements to support R3 with exception of PM to document closure report |  |  | 

## Slide 21: UK Link Release 3 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build & System Test | Acceptance Test | Performance Test | Market Trials | Regression Test | Imp. | PIS
Track 1 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 04/06/18 | 13/08/18 | 07/09/18 | 19/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 1 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 04/06/18* | 13/08/18 | 07/09/18 | 25/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 2 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 30/06/18* | 24/09/18 | 05/11/18 | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
Track 2 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 30/06/18* | Build Complete ST synergised with AT | 14/12/18** | N/A | 14/12/18* | 18/01/18 | 04/02/19 | 08/03/19
RAG Key – Milestones are end dates;
*Closedown expected to finish this week ** Synergised ST and AT date
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed

## Slide 22: 5b. February 2019 - Update

## Slide 23: XRN4802 – MiR Drop 3 - Status Update
18/03/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS – Ongoing. No issues identified and first usage is tracking to plan. Closedown – Project on track to complete PIS and Handover to Xoserve Operate |  |  | 
department on 22/03Risks and Issues | No current risks or issues around MiR Drop 3 |  |  | 
Cost | All costs tracking to budget |  |  | 
Resources | All required SME resource to support first usage identified and available when required |  |  | 

## Slide 24: XRN4802 – MiR Drop 3 & Feb 19 Document Release Timeline
Minor Release Key Milestone Dates:
22nd March – PIS completion and Handover on track as per plan
2019
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Jan
Feb
Mar
2018
Testing
Build
UT
Imp
Apr
Feb-19 Minor Release Timeline
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Document Release Implementation
Document Release Key Milestone Dates:
1st March - Implementation
Feb-19 Minor Release Timeline
Feb-19 Document Release Timeline

## Slide 25: 5c. June 2019 - Update

## Slide 26: XRN4732 - June 19 Release - Status Update
18th March 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build: Activities have commenced and are continuing to plan to be completed by 15th March Plan: Tracking to plan, detailed testing phases have been drilled down and the timeline has been baselined based on this assessment Funding: The BER was approved by ChMC at the 09th January 19 meeting |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met Environments– There is a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging) a detailed assessment of co-existence in pre-production is in progress |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 27: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Traceability of Detailed Design to Requirements is complete
Agreement of June 19 Implementation Date to be agreed with ChMC

## Slide 28: 5d. EUC 2019 - Update

## Slide 29: XRN4665 – EUC Release
18/03/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build & UT : Build & UT activities continue to track to plan Testing : Test Approach approved on 08/03. Preparation of Test Cases based on approved Test Scenarios ongoing and tracking to plan Implementation : Two part implementation proposed Part A on 03/08 to make new EUC bands allowable in ISU to enable sharing of new EUC bands with Industry via the T67 file Part B on 31/08 (with a contingency date of 07/09 if required) to implement all code changes to processes affected by new EUC bands |  |  | 
Risks and Issues | Environments– There continues to be a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging). A detailed assessment of co-existence in Pre-production is currently in progress with relevant project teams. However the current view is that this will not impact the EUC release. Awaiting internal conformation. |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 30: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Build & UT activities tracking to plan. Contingency week planned for if required. However, no downstream impacts if this is required
ST activities on track to commence as per the plan
Awaiting confirmation of an acceptable PIS timeline

## Slide 31: 5e. November 19 - Update

## Slide 32: XRN4828 - Nov 19 Release - Status Update
6th February 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phase in progress and due to complete in April Planning for Design phase in progress Internal Business Case approved at internal financial governance meeting Market Trials phase discussed at ChMC and agreement reached in principle that this is not required for November 19 release. Alternative options to MT to be presented at next DSG Funding: BER for full delivery to be presented to ChMC in April 2019 |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs will be presented to ChMC in April 2019. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 33: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Supplier contract approval – 22/03/19
Approve and issue EQR – 04/02/19
Gain Business Case approval at IRC - 13/03/19
PID approval 28/03/19
Detailed Delivery Plan approved – 01/04/19
BER Approval – 10/04/19
Design Change Packs Submitted to Industry –08/05/19
Test Plan approval – 05/04/19
2020
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
2019
J
u
n
e
1
9
–
C
h
M
C
A
g
r
e
e
d
S
c
o
p
e
Testing
Build
UT
Imp
Mobilisation
Jan
Design
Build & UT
System Test
SIT
UAT
RT & PT
Market Trials
IMP (Inc IDR)
PIS
Closedown
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Submission
Nov-19 Timeline

## Slide 34: 6. New Change Proposals For Ratification of the Prioritisation Scores
6a. XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
6b. XRN4866 - UIG Recommendation – removal of validation on uncorrected read
6c. XRN4869 - DC Exit Programme - REMOVED
6d. XRN4871 - Modification 0665 – Changes to Ratchet Regime
6e. XRN4876 - Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting - REMOVED
6f. XRN4850 - Notification of Customer contact details to Transporters

## Slide 35: 6a. XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
Change Proposal can be found in the Change pages on xoserve.com

## Slide 36: 6b. XRN4866 - UIG Recommendation – removal of validation on uncorrected read
Change Proposal can be found in the Change pages on xoserve.com

## Slide 37: 6d. XRN4871 - Modification 0665 – Changes to Ratchet Regime
Change Proposal can be found in the Change pages on xoserve.com

## Slide 38: XRN4871 - Modification 0665 – Changes to Ratchet Regime

## Slide 39: Background
Modification 0665 has been raised and seeks to amend the current Class 2 Ratchet Charging Arrangement and it allows Transporters to designate Supply Points (Network Designated) that should, in addition to existing mandatory Class 1 Supply Points, be subject to the existing Class 1 Ratchet Charging Arrangement.
This Change Proposal has been raised to deliver the system requirements set out within this modification.
Due to the proposed timescales and the requirement to implement the changes by 01 October 2019, the Change Proposal has been raised ahead of the modification being officially approved (Panel approval expected March and Ofgem decision April).
Potential implementation has been proposed as the July Minor Release

## Slide 40: Summary of change
In summary the requirements for the CDSP are:
  Implementation of an amended Ratchet Charging Arrangement applicable for Daily Metered Supply Meter Points that are not Network Designated. [Class 2 Ratchet Charge].
  A mechanism is required to flag in UK Link where a Network has designated a Supply Meter Point which should be subject to the existing [Class 1] Ratchet Charge. These will then be subject to the ‘Class 1 Requirement’ in UNC.
  When a Supply Meter Point has been Network Designated the CDSP shall notify the registered Shipper, and the relevant Supply Point will as soon as reasonably practicable be required to be a Class 1 Supply Point
  If a Shipper does not reclassify the Supply Point as Class 1 within 20 Supply Point Systems Business Days of the notice of Designation, then the CDSP will reclassify the site as Class 1 after so notifying the relevant Shipper and providing not less than 20 Supply Point Systems Business Days’ notice of the revised classification effective date unless the CDSP has been informed that the Supply Meter Point is unable to be Daily Read in accordance with current code requirements.
Please note – due to the tight timescales for implementation, we are not proposing any changes to external interfaces including file formats and the all associated notifications will be offline

## Slide 41: Views sought from DSG – Visibility of ND Flag
  As part of application of Network Designation the Registered User will receive a notification to the DSC Contract Manager from the CDSP
  Visibility of Network Designation to Prospective Users
    As we are seeking to limit the scale of impacts to Users, and in particular Users who do not operate DM Supply Points, we are NOT proposing to make this data item available to Shipper Users in SPA files – e.g. Nomination Response (incl Enquiry); Confirmation; etc.
      We would suggest that IF this is required that this is considered within the CSS Consequential interface changes – schedule 2021
    Changes to DES
      May be precluded by timescales
    Addition to API
      If needed, seems like best available option?
    Other options for HLSO?

## Slide 42: Views sought from DSG - SPA
  Rejection of a Nomination / Confirmation (incl Reconfirmation) / Class Change
    If a site is Network Designated it must be Class 1, any relevant transactions will need to be rejected, such as:
      Nomination
      Confirmation
      Class Change
    We would propose that we use the existing Rejection Code CLS00002 – “Supply meter point should be Class 1”. This code is used for the above processes already.
    Other options for HLSO?

## Slide 43: Views sought from DSG – Inflight
  Outstanding Offers and Inflight Change of Shipper
    Assessing options around this where a Supply Meter Point gets set to Network Designated but it has:
    Outstanding Offer <> Class 1 – valid for 6 months
      Lapse Offer (as per Ratchet logic)
      Allow Offer to continue, but oblige Shipper to reconfirm
    Accepted Confirmation <> Class 1 – valid for 30 SPSBDs
      Cancel Confirmation
      Allow Confirmation to progress, but oblige Shipper to reconfirm
    Do not believe that there is any basis in 0665 for cancelling offer / confirmations – but to be verified
    Other options for HLSO?

## Slide 44: Views sought from DSG – Invoicing
  New Ratchet Charging Arrangement
    The current Ratchet Charge includes the ZRA – Customer Ratchet Charge and the SRA – SOQ Ratchet Charge
    The new Ratchet Charge for Class 2 sites will also include the ECN – Exit Capacity LDZ Charge. This is planned to be incorporated into the ZRA Charge for Class 2 Ratchets only
      Appears on CAZ Invoice and ZCS Supporting information
      RT_I09_CAP_RATCHET_CHARGE_DETAIL record has the RATCHET_PREMIUM value – which we expect will be populated differently between Class 1 and Class 2 Ratchets

## Slide 45: Next Steps…
We are asking DSG to consider our initial thoughts on this change and come back with views
  Seeking to remove any format changes so that this can be implemented within timescales requested
  However, likely to require process amendment by Shippers
We are requesting that DSG agree to an extraordinary Change Pack to be issued regarding this to get views from the wider industry

## Slide 46: 6f. XRN4850 - Notification of Customer contact details to Transporters
Change Proposal can be found in the Change pages on xoserve.com

## Slide 47: 7. Change Proposal Initial View Representations
7a. XRN4645 – The Rejection of Incrementing Reads Submitted for an Isolated Supply Meter Point (RGMA Flows) - Removed

## Slide 48: 8. Undergoing Solution Options Impact Assessment Review
8a. XRN4713 – Actual Read following transfer read calculating AQ of 1
8b. XRN4803 – Removal of Validation for AQ Correction Reason 4

## Slide 49: 8a. XRN4713 – Actual Read following transfer read calculating AQ of 1
HLSO to be completed on 15th March. Slides to be added before the DSG meeting.

## Slide 50: 8b. XRN4803– Removal of validation for AQ Correction Reason 4
High Level System Solution Impact Assessment

## Slide 51: Change Overview
XRN 4803 – Removal of validation for AQ Correction Reason 4
There have been instances where a users read is being rejected as it breaks the outer tolerance, and AQ correction is being rejected as the AQ has not been re-calculated in the UK Link system. Therefore there is no option to correct the incorrect AQ; hence the user can’t submit reads. Therefore we will never be able to reconcile or get a correct AQ calculated.
Solution Options
Remove the ‘calculated’ validation check when a site is/was unregistered or shipperless prior to current registration
1

## Slide 52: Option 1 - High Level Impact Assessment
1- Remove the ‘calculated’ validation check when a site is/was unregistered or shipperless prior to current registration
Currently if AQI is received with reason code 4 and AQ Roll has been recalculated; then only AQI will be accepted if all other validations are successful. After this change the above mentioned validation will be removed. Irrespective of the AQ Roll calculation has taken place or not; AQI will be accepted if all other validations are successful.
Impacted Systems
Assumptions
Market Trials costs are not considered. This change is applicable only for Reason Code 4 in AQI. Reason code 1,2,3 and 5 are out of scope of this change. All the other AQI validations will continue As Is.
Overall Impact | Release Type | High Level Cost Estimate
Low | Minor | 15,000 - 25,000 GBP
Marketflow
SAP PO
SAP ISU
Gemini
SAP BW
CMS
DES
API
Impact
1

## Slide 53: Option 1 - System Impact Assessment
System Component:
Development Type:
Impacted User(s):
Build Type:
Change Description:
Requirement Clarity:
Change Complexity:
Integration Complexity:
Test Data Prep Complexity:
Test Execution:
Regression Testing Impact:
Performance Impact:
SAP ISU |  |  |  |  | 
Process Code |  |  |  |  | 
Code Change |  |  |  |  | 
Shippers |  |  |  |  | 
Existing |  |  |  |  | 
System will be amended to remove the “previously calculated” validation on AQ Correction process for reason code 4 |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
G |  |  |  |  | 
1
Notes: System Component: File Format / Batch Job / Process Code / Report
Development Type: Interface / Online / Report / Workflow / Configuration
End User Impacted: Shipper / DN / NTS / Xoserve / Other
Build Type: New / Existing

## Slide 54: Option 1 - Process Impact Assessment
Process Area | Complexity | File Formats | Exceptions | External Screens | Batch Jobs | Performance Test?
SPA | L | N | N | N | N | N
Metering (Reads) | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Reconciliation | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Capacity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Commodity | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Amendment | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Invoicing – Other | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Rolling AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Formula Year AQ | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
RGMA | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
DSC Service | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
Other (Specify) | n/a / H / M / L | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N | n/a / Y / N
1

## Slide 55: 9. Solution Options Impact Assessment Review Completed
No agenda items for this section

## Slide 56: 10. Miscellaneous
10a. IX Update
10b. XRN4864 - Supply of Meter Point data as part of the PARR Reports - Removed

## Slide 57: 10a. Xoserve IX Refresh
Customer Update
05/03/2019

## Slide 58: IX Refresh Customer Update
Welcome to the February update of the IX Refresh Project
We’ve made good progress over the last month, achieving our major program milestones of Proof of Concept testing and the completion of the pilot site on February 19th. Our work on the pilot site has identified a number of potential improvements to our approach which will lead to a more seamless migration and will improve your experience of the process.
As part of the service transition to the new IX platform, alongside our continued line installation activities, we will be working with our suppliers over the next few weeks to make the improvements that we’ve identified and we will test the perfected migration approach on a second site ahead of the rollout. This will be our priority focus this month, however we will continue line and router installations as planned.
Whilst we acknowledge the improvements outlined above will have an impact on the timelines set out in last month’s update, we will look to identify efficiencies during the delivery phases of the program where possible and we will provide further information in future updates.
Our aim is to make this process as seamless as possible to ensure that the installation experience meets your expectations. If you’d like more detailed information about dates relevant to your migration, please email box.xoserve.IXEnquiries@xoserve.com
Finally, thank you for your ongoing support and I look forward to updating you again in March.
Michelle Callaghan
People Platform Director

## Slide 59: Look Forward: IX Program Quarterly Activity
Three Month Timeline
March
Migration approach to be perfected and tested at another site.
Initial line installations to continue across all phases
Router installations to take place at some phase one sites
Prepare April migrations
Continue to engage customers with Disaster Recovery equipment about testing approach
Continue to engage relevant customers requesting additional IP range / addresses for IX End User equipment
April
Rollout begins with Phase One
Relevant sites contacted to have servers installed
Prepare May migrations
Phone line installations to continue
May
Rollout continues for line, router and server installations
Customers contacted to have servers installed
Prepare June migrations
Phone line installations to continue
Please be assured that you will be contacted by Gamma before either your Network survey or phone line installation takes place (dependant on the complexity and IX option required).
If you have any queries answers to the most commonly asked questions can be found on our website in the Q&A section here.

## Slide 60
June
August
February
March
April
May
Pilot Site
Phase One
Network and Router Installation
Server Installation
Phase Two
Phase Three
Phase Four
Remaining Sites
(Where surveys are outstanding)
High level migration plan – Current & future view
Phase Five
July
Migration Amendments
Second Pilot Site

## Slide 61: 11. DSC Change Committee Summary – 13th March ‘19
7 New change proposals raised – 4 approved, 2 deferred for an initial review, 1 for information
XRN4865 Amendment to Treatment and Reporting of CYCL Reads – Approved to proceed to the Delivery Sub Group (DSG).
XRN4866 – Removal of Validation on Uncorrected Read (UIG Recommendation) – Approved to proceed to DSG.
XRN4869 – DC (Date Centre) Exit Programme – Progress updates to be presented to ChMC frequently. This agenda item was for information only.
XRN4871 – Modification 0665 – Changes to Ratchet Regime - Approved to proceed to DSG.
XRN4876 - Changes to PARR Reporting – providing further data to PAFA to aid analysis of performance reporting – Deferred for a 10 working day initial review consultation within the March Change Pack.
XRN4867 Service Description Table - Approved to proceed to be passed to CoMC. This is only a documentation change to the DSC Service Description Table.
XRN4888 – Removing duplicate address update validation for IGT Supply Meter Points via Contact Management Service (CMS) - Deferred for a 10 working day initial review consultation within the March Change Pack.

## Slide 62: DSC Change Committee Summary – 13th March ‘19
4 New change proposal post initial review:
XRN4850 Notification of Customer Contact Details to Transporters –proceed to DSG for solution development, but return to April’s ChMC for approval of the funding arrangements. DN’s have a view iGT should part fund the change.
XRN4851 Moving Market Participant Ownership from SPAA to UNC/DSC –This change was presented to ChMC only to give an update on the progress of the consultation period. Change to be presented for approval to proceed to DSG in April.
XRN4853 UIG Recommendation 3.1 Option 5 (Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only) – Approved to go into delivery, action on Xoserve to liaise with customers as not all want reads to be loaded on their behalf
XRN4860 National Temporary UIG Monitoring (Projection of National UiG from Allocation through to reconciliation (Code Cut-off Date)) - This change was presented to ChMC only to give an update on the progress of the consultation period. Change to be presented for approval to proceed to DSG in April.

## Slide 63: DSC Change Committee Summary – 13th March ‘19
2 Solution/Delivery option approvals, and one deferral
  XRN4772 – Composite Weather Variables
    Approved to proceed with the recommended solution option and for implementation in the June 2020 release
  XRN4790 – Introduction of Winter Read Consumption Reports and Associated Obligation
    The preferred solution option and Xoserve’s intention to implement this change at some point in April 2019 were approved
  XRN4686 – Smart Metering Report
    Approval decision deferred to the ChMC meeting in April due to questions around the value of the report, awaiting recommendation from DSG and the Change Proposer.
Implementation plan – approved
Change Documents – 3 approvals and one deferral
  BER for XRN4686 Smart Metering Report - deferred
  BER for XRN4790 - Introduction of winter read consumption reports and associated obligation (Mod 0652) – approved
  CCR for XRN4542 - Changes to the Shipper Portfolio Summary Report – approved
  CCR for XRN3667a Formula Year AQSOQ to proposing Users via API - approved

## Slide 64: DSC Change Committee Summary – 13th March‘19
Release Updates:
  Release 3 (due to be delivered 2nd November 2018)
    Track 2 – Successfully Implemented on 1st/2nd February 2019
    XRN4534 (RGMA Validation Updates) implemented on 1st March
  February 2019 release
    Documentation Release implemented on 1st March
    Minor Release Drop 3 implemented on 16th February
  June 2019 release
    Currently tracking Amber – greatest risk is centred around resource
  XRN4665 – Creation of new end user categories (2 stage release Jul & Sept)
    Currently tracking Amber – re-planning activities undertaken, risk on resources, also used sharing environment with GB Charging MOD
  Minor Release Drop 4 (Scope and Delivery Plan)
    Presented for information
  November 2019 Release – Delivery Plan – MT Required for 4621 (Suspension of the validation between Meter Index and Unconverted Convertor Index) ChMC agreed that DSG can look at the implications of carrying out MT just for XRN4621 and provide a recommendation to ChMC in April.
Change Assurance update for June and EUC provided
https://gasgov-mst-files.s3.eu-west-1.amazonaws.com/s3fs-public/ggf/2019-03/7.7%20Change%20Assurance%20Update%20-%20June%202019%20and%20EUC.pptx

## Slide 65: DSC Change Committee Summary – 13th March ‘19
Standard agenda item updates:
  CSS consequential change update
  XRN4695 UIG Taskforce update
  Amendment invoice update
  Finance and Budget update
  Bubbling under report (MODs)
  Plan on a page:
    Gemini
    UK link changes
    Prioritisation of Data Office changes (new standing agenda item, which ChMC welcomed)

## Slide 66: DSC Change Committee Summary – 13th March ‘19
AOB items:
IX Refresh Update
  Link to Document
Published Change Proposals – from 1st April all new Change Proposals will be published on Xoserve.com, not the JO website
DSC Change Management Governance Group (verbal)
XRN4795 Amendment to PARR Reports (PAC approved change for delivery)
  Link to Document
Change Pack process on Xoserve.com (verbal)
Strategy on the future of MIS
  Link to Document

## Slide 67: 12. UIG Task Force Progress Report
Change Management Committee 13/03/19

## Slide 68: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a task force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Task force next steps

## Slide 69: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Workstream | Date | Status
Attend UIG working group | IA & AA | 22/01/19 | C
Run UIG Recommendation day under UIG work group banner | IA & AA | 28/01/19 | C
Attend CoMC | Task force | 20/02/19 | C
Attend UIG working group | Task force | 26/02/19 | C
Raise CRs & CPs to support recommendations allocated to Xoserve | Task force | 29/01/19 - completed | C
Create and publish UIG Investigation Guide | Taskforce | 15/02/19 | C
Publish post sprint executive summary | Taskforce | 15/02/19 | C
Priorities for next month – key milestones | Workstream | Date | Status
Draft Mod/support Eon – 12.1 & 12.3 - Site specific Conversion factors |  | W/c 4/03/19 | G
Draft Mod – 12.2 - Standard conversion factors |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 - Automatically change meter read frequency to monthly where AQ increases above 293,000 |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 – Reduce qualifying period for Class 1 |  | W/c 4/03/19 | G
Draft Mod – 3.2.1 – Automatically convert site to Class 1 and install DM equipment. |  | W/c 4/03/19 | G
Attend UIG working group |  | 25/03/19 | G
Attend March Change Management Committee |  | 13/03/19 | G
Attend March Contract Management Committee |  | 20/03/19 | G
Overall RAG status:*

## Slide 70: Plan on Page
Delivery team milestone
Advanced Analytics
I
DSC ChMC governance
C
Completed activity
 | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | 
 | 05/11 | 12/11 | 19/11 | 26/11 | 03/12 | 10/12 | 17/12 | 24/12 | 31/12 | 07/01 | 14/01 | 21/01 | 28/01 | 04/02 | 11/02 | 18/02 | 25/02 | 04/03 | 11/03 | 18/03 | 25/03 | 01/04
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop and manage shipper action plans (linked to Investigation Log)
22/10 Action plan template developed
Sprint 5
Sprint 6
I
07/11 DCS ChMC
I
12/12 DSC ChMC
C
Sprints 4-6 to continue at the same pace and follow directly after the initial sprints to maintain momentum and ensure existing team resources are fully utilised. A 14-day stand-down period applies at any time.
08/11 Sprint 4 Exec Summary
22/11 Sprint 5 Exec Summary
05/12 Sprint 6 Exec Summary
C
C
Develop Findings template and Recommendation Packs
I
09/01 DSC ChMC
28/01 CUSTOMER RECOMMENDATION DAY
C
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
I
13/02 DSC ChMC
15/2 Post Sprint Exec Summary
C
15/2 Published Investigation Guide
C
I
13/03 DSC ChMC
Draft Mods to support recommendations
Support Mod development

## Slide 71: 13 Findings – 85 Recommendation lines - where we are
1 CR4868 in progress
1 CR4867 in progress
1 CP4853 in progress
2 ongoing engagement using existing MI
85 recommendation lines
3 lines – Xoserve (3.2.1) = 3 MODS
7 review April
19 lines Future review
2 review May
3 review July
3 review November
4 review December
8 lines - PAC /Xoserve
3 lines – EON & Xoserve = 1 MOD
37 lines CLOSED
As at 04/3/19
9 lines – Xoserve (12.2) = 1 MOD
6 lines In progress
1 CP4866 in progress
All future reviews include non task force related changes that are pending, defects with planned resolution dates, other options which may be considered if engagement/PAC reporting does not deliver results. (PAC can look to deliver these when PAC reporting is updated).
Notes: 85 lines in recommendation tracker
37 lines closed = 3.2.1 option 1, 5, 8 & 9. 3.2.2 option 1, 2, 3, 4, 5, 7a, 8. 1 option 1,5 &8. 12.1&12.3 options 1, 5, 7, 8 & 9b. 12.2 option 1. 3.2.8 option 1, 6, 10 & 11. 3.1 option 1, 3, 4, 8 & 9. 2 option 1, 2 & 3. 13.2.2 option 1 & 2. 13.2.5 option 1, 2 & 3.
8 lines PAC/Xoserve action = 3.2.1 option 3 & 4. 3.2.2 option 10. 1 option 4 & 7. 12.1&12.3 option 3 & 6. 3.2.8 option 5.
3 lines EON/Xoserve MOD = 12.1&12.3 option 9a, 10, & 11.
9 lines Xoserve draft mod – 12.2 options 2,3,4,5,6,7,8,9&10.
3 lines Xoserve draft mod 3.2.1 options 6,7 & 10.
6 lines in progress =
2 ongoing engagement 12.1&12.3 option 2, 3.2.8 option 2 – using current MI shipper performance packs
1 CP in progress - 3.1 option 5 – 3.2.1 option 7 - CP4853 manual workaround
1 CP in progress – CP4866 removal of validation on uncorrected read
1 CR in progress – 3.2.1 option 2 - CR4867 sites over 58.6m kWh that need reconfirming
1 CR in progress – 1 option 2 - CR4868 class 1&2 read rejections
18 lines for future review =
7 review April 3.2.2 option6, 7b & 9. 1 option 3, 6 & 9. 12.1&12.3 option 4.
2 review May 2 option 5 & 6.
3 review July 3.2.1 option 11. 3.2.8 option 3 & 4.
3 review November 3.1 option 6&7, 2 option 7,
4 review December 3.2.8 option 7, 8 & 9. 2 option 4.

## Slide 72: Overview Of Taskforce Funding

## Slide 73: Taskforce Next Steps
Use the UIG working group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UIG Working Group timescales.
Continue analysis on investigation lines & publish investigation tracker updates bi-weekly.
Publish any new findings/recommendations drawn from investigation lines which are currently “work in progress” when completed.
Continue the customer engagement, progress the CPs & CRs raised to support the recommendation options agreed at 28th January UIG-Recommendation session.
Drafting MODs to progress agreed recommendation options.
Lead the creation of new PAC reports as per the agreed recommendation options.

## Slide 74: 13. JMDG Update

## Slide 75: 42 Supplier API [Twin]
Overview
Use case overview
Access to an API service would allow Suppliers to significantly improve the reliability of the switching process for consumers
JMDG progression
Assessed, prioritised, requested project team to deliver an API service with an extended data set to that of the original PCW service.
A Twin fuel service was launched on the 30th November 2018.
42
Twin Fuel
Go-live
Tech Spec
Pricing
Electricity API
MOD Approval
JMDG Decision

## Slide 76: 27 Domestic M-Number Helpline [Gas]
Solution overview
Use case overview
Replace the existing method of providing this service with an online solution
500k calls per year, used by domestic consumers
JMDG progression
Assessed, prioritised and requested project team to provide solution.
Phase 1 – Web Portal to be developed for gas consumers. Will be able to obtain MPRN, Gas Supplier and Transporter name
Phase 2 – Migration of helpline to an enhanced Web Portal
Plan
Phase 1 was delivered in September 2018. Phase 2 has commenced and is on track to launch in June
Testing
Phase 1
Phase 2
Requirements
Gathering
27

## Slide 77: 06 MAPs - Meter Asset Details [Gas]
Solution overview
Use case overview
Meter asset data on UK Link is not correctly maintained by industry participants
A reporting service will be provided to compare the MAM / MAP meter point reference number and meter serial number to that held on UK Link
JMDG progression
Assessed, prioritised, requested project team to analyse requirements with MAPs
06
Engage Maps
Portfolio
Analysis
Phase 1 – MAPs to UKLink meter asset comparison service (Dec ’18) - Completed
Phase 2 – MAP to MAP meter asset comparison service (May ‘19) – In Progress
Phase 3 – Introduction of MAP ID into UKLink (CSSC) – Enduring solution (TBC – would be linked to a UKLink Release schedule)
MAP
Engagement
Process
Modelling
Service
Set-up
JMDG
Phase 1
Phase 2
Design /
Procurement
Development

## Slide 78: 33 Third Party Services [Twin]
Overview
Use case overview
Provide data services to Third Parties
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
23
Permissions
Workshop
Raise MOD 649
A gas data permissions matrix has been created detailing current industry participants permissions to data
  This has been included as part of MOD 649 which aims to move the approval decision making powers from UNC to DSC Contract Management Committee.
The data permissions matrix will help highlight potential API services. MOD 649 will help expedite the governance process to provision data new data services to industry participants while still providing a robust approval process
MRASCo Board has been establishing precedents for third party access approach, which can supplement the gas matrix
A Third Party industry engagement approach will then be created to seek requirements for services
workshop
Engagement Plan
Start Engagement
MOD 649 Approval
JMDG

## Slide 79: 47 & 09 ASC and CT / VT Ratio (Electricity)
Solution overview
Use case overview
Two linked cases involving DNO data:
047: The MIS could also facilitate access to Current/Voltage Transformer (CT/VT) ratio. The ratios would be populated initially by the distribution network operator and can be queried by Parties should discrepancies be identified as part of meter installation, or commissioning and proving tests.
009: Proposed making EAC available to quoting suppliers, and mentioned inclusion of ASC
Initial discussions suggest data will be available but DNOs not keen on multiple access to their databases.
Possibility of ASC access via aggregator model with one authorised API gaining access. This also means less development time.
Timescales: Specification work 3 months. Solution development (subject to BSC for CT/VT) 3 months. Testing I month. Go live May to August 2019.
JMDG progression
Indicative costs received from ECOES service provider. JMDG decided to progress to full solution design. MIS project team prioritised EAC use case for February meeting. Will refocus on this for March’s meeting.
47
Progress to Full Solution

## Slide 80: 01 & 57 Central industry contact database and Industry Escalation Process
Overview
Use case overview
Central repository for industry contact details to underpin industry processes
JMDG progression
Assessed, prioritised, requested project team to conduct initial analysis
09
Both cases can use the same information contained within current code processes. Initial discussions suggest data available but code administrators generally not willing to co-operate so may need changes to code to enforce compliance.
Timescales: Specification 3 months. Possible modification processes 3-9 months. Solution development 3 months. Testing I month. Go live may be incremental Feb 2019 to November 2019.
JMDG and MPB
decision making
Governance changes
and development

## Slide 81: 09 Estimated Annual Consumption (EAC)
Overview
Use case overview
Make EAC available to quoting supplier
JMDG progression
Indicative costs received from ECOES service provider. JMDG to decide on progression to full solution design based on outcomes of EAC workshop held 28/01/2019 – report provided to JMDG in enclosures for February meeting.
09
Workshop held 28th January to explore potential sources, formats, frequency of the data
Options assessment being presented to February 2019 JMDG
Followed by impact assessment of preferred option and JMDG progress/don’t progress decision
JMDG options
assessment
Second order analysis and
impact assessment
JMDG and MPB
decision making
Implementation
Options assessment
workshop

## Slide 82: 56 FiT Licensee Notifications – Smart meter installs
Options Overview
Use case overview
FiT Licensees would be better able to meet their Supply Licence obligation to administer export payments on metered data whenever possible if a mechanism existed to inform them that a smart meter (which by definition has export metering capability) has been installed on the premises of a FiT Generator
JMDG progression
JMDG agreed high priority progression. Ofgem attending December meeting to participate in discussion on solutions. Gemserv are impact assessing options for delivering the requirements JMDG wanted to progress with their service providers. We will report back in March.
56
ECOES contains meter information (meter serial number, meter type) which would allow FiT Licensees to identify if import MPAN associated with a FiT Generator had a smart meter installed
Either make relevant ECOES data through the Central FiT Registry or combine the two data sets and make available to FiT Licensees elsewhere
Another example of “Trusted Third Party API” requirement which could be handled in aggregate.
An example of where ‘push’ functionality on the API might be of benefit.
JMDG and MPB
Assessment and decision

## Slide 83: 58 MAP API [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a supply meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
58
Change Proposal has been raised and sponsored by Colin Blair (MPB Member)
Project team to provide ChMC feedback to MAPs post meeting to highlight any considerations
Dependency: Change is dependant on MOD and Data Permission Matrix (DPM) Amendment approval
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 84: 59 UKRPA Access to Gas data [Gas]
Overview
Use case overview
There is an opportunity to create a service where MAPs can query the current and historic Supplier ID for assets installed on a meter point
JMDG progression
Assessed, prioritised, requested project team to move to delivery
59
Change Proposal has been raised
ChMC
Review
Submit MOD
CoMC DPM
Amendment

## Slide 86: 14. Action Updates
The DSG Actions Log can be found on the DSG pages of Xoserve.com under Action log

## Slide 87: 15 AOB
15a. XRN4857 – Report Review
15b. XRN4686 – Smart Metering report
15c. XRN4853 - UIG Recommendation 3.1 option 5 - Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only.

## Slide 88: 15a. XRN4857 – Report Review
Verbal update to be presented by Jane Goodes

## Slide 89: 15b. XRN4686 SMART metering report Recommendation needed

## Slide 90: XRN4686 – SMART Metering report
XRN4686 raised by CNG requesting a monthly report to show the churn of Smart Meters throughout the industry.
This was as a follow up to MOD632S Shipper asset details reconciliation where the CDSP (Xoserve) issued a single report on Smart meters and Advance meters 3 months following implementation.
Requested reported anonymously at an aggregate level reflecting NS, SMET1 and SMET 2 installations broken down by Domestic and I&C.
Change Proposal previously presented at DSG:
  9 April 2018 - no concerns or objections were raised
  20 August 2018 - DSG were requested to review CP and feedback any further requirements
  3 September 2018 - DSG confirmed no additional requirements
  17 December 2018 – DSG feedback requested on Report design and location for publishing

## Slide 91: XRN4686 – Recommendation required from DSG
Approval requested at Change Management Committee for delivery in March but deferred until April meeting.
Recommendation sought from DSG for how useful report will be if approved for monthly publication.
Does DSG see any value in this report?

## Slide 92: XRN4853 - UIG Recommendation 3.1 option 5 - Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only.
Verbal update to be presented by Richard Johnson