## Sheet1
Scenario No. | Defect No | Number of MPRNS | Impact to AQ? | Process Area | Actions | Billed and Excluded profile dates | Defect fix Build date | Testing completion date | Script implementation date | Correction Completion date | Charge Release date
49 | 720 | 46 | No | Prime and Sub reads | 1. Reverse the rec. 2. Adjust volume 3. Perform Rec | N/A | N/A | N/A | N/A | N/A | TBD
A12 | 914 | 17345 | Yes | Transfer Read | 1. Reverse the read. 2. rec between previous actual and transfer read | 2018-10-02 | 2018-10-03 | 2018-10-08 | 2018-10-12 | 2018-10-20 | November Invoice
A21 | 945 | 36 | Yes | Exception Resolution | 1. Reverse the rec. 2. Adjust volume . 3. Perform Rec | 2018-10-02 | NA | NA | NA | 2018-10-27 | November Invoice
A22 | 1045 | 1661 | Yes | Replacement Reads | 1. Reverse the rec. 2. Adjust the volume for impacted reads (Up to 3 for each MPRN) 3. Perform Rec | 2018-10-03 | 2018-10-12 | 2018-10-19 | 2018-10-26 | 2018-11-16 | December Invoice
A15 | 1052 | 5813 | Yes | Class 4 read processing | 1. Reverse the rec. 2. Adjust volume 3. Perform Rec | 2018-10-03 | 2018-10-11 | 2018-10-17 | 2018-10-26 | 2018-11-09 | November Invoice
72/73 | 947 | 2483 | Yes | Read processing | 1. Reverse the rec. 2. Perform Rec | 2018-10-04 | NA | NA | NA | 2018-10-05 | October Invoice
67 | 837 | 5270 | No | Class change read | 1. Reset the rec flag 2. Peform class 3 rec. | 2018-10-08 | 2018-10-26 | 2018-11-09 | 2018-11-16 | 2018-11-30 | December Invoice
61 | 881 | 61 | No | Replacement Reads | 1. Reset the rec flag 2. Peform class 4 rec. | 2018-10-04 | 2018-10-03 | 2018-10-08 | 2018-10-12 | 2018-10-20 | November Invoice
23/51 | 727 | 3037 | No | Consumption Adjustment | 1. Re apply the Consumption Adjustment | 2018-10-02 | 2018-10-26 | 2018-11-09 | 2018-11-16 | 2018-11-30 | December Invoice
45 | 747 | 1039 | Yes | Site visit Reads | 1. Reverse the rec. 2. Inactivate Read. 3. Adjust volume 4. Perform Rec | 2018-10-05 | 2018-10-03 | 2018-10-08 | 2018-10-12 | 2018-10-20 | November Invoice
74 | 933 | 95 | Yes | Normal Read | Pending with Business | 2018-10-03 | 2018-10-26 | 2018-11-09 | 2018-11-16 | 2018-11-30 | December Invoice
16 | 881 | 12407 | No | Replacement Reads | 1. Reverse the rec. 2. Adjust volume . 3. Perform Rec | 2018-10-05 | 2018-10-11 | 2018-10-17 | 2018-10-26 | 2018-11-09 | November Invoice
39 | 631 | 1048 | No | RGMA Reads | 1. Insert the read in table 2. Perform the rec Class4 rec | 2018-10-05 | 2018-10-26 | 2018-11-09 | 2018-11-23 | 2018-11-30 | December Invoice
A32 | 1122 | 1508 | Yes | RGMA Reads | 1. Reverse the rec. 2. Inactivate Read. 3. Adjust volume . 4. Perform Rec | TBD | TBD | TBD | TBD | TBD | TBD
8 | 838 | 121 | Yes | Transfer Read | Pending Business discussion | TBD | TBD | TBD | TBD | TBD | TBD
68 | No Correction required | 2383 | TBC | TBC | Pending Business discussion | N/A | N/A | N/A | N/A | N/A | N/A
11 | No Defects mapped | 115 | TBC | TBC | Pending Business discussion | TBD | TBD | TBD | TBD | TBD | TBD
55 | No Defects mapped | 38 | TBC | TBC | Pending Business discussion | TBD | TBD | TBD | TBD | TBD | TBD
40 | Only one MPRN, hence can be done manually | 1 | TBC | TBC | Pending Business discussion | N/A | N/A | N/A | N/A | N/A | N/A