## Trident Query Log - LIVE
Project Trident query log |  |  |  |  | Last update: | 2025-12-08
ID2 | Date Raised2 | Source of Question2 | Theme | Topic | Question | Project workstream | Response owner | Response
QA001 | 09.09.24 | Project Trident Launch Day | Business Case & Scope | Critical Success Factors | What are your critical success factors for Project Trident? We can’t see references to net-zero, consumer, agility and flexibility. | Project Delivery | Nick Partridge | The purpose of the critical success factors within the Strategic Outline Case (SOC) is to assess the long list of options for Project Trident. They are grouped into the following five themes which will be available in full within the SOC, once this is published at the end of September 2024. 1. Strategic Fit and Business Need, including “allow flexibility, innovation and increased ease of change.” 2. Potential Value for Money, including “be long-lived, with support until at least 2040”. 3. Affordability, including “provide predictability of cost to customers”. 4. Achievability, including “minimise impact on customer as a general rule” and “limit customer change impact to improvements” 5. Capacity and Capability, including “capable of scaling to increased data processing needs which are driven by market and business changes including decarbonisation”. These critical success factors will help develop the next stage of specific and measurable criteria which we will use to assess the shortlist of options in the next phase (Outline Business Case). We expect these to include further references net-zero, consumer, agility, and flexibility.
QA002 | 09.09.2024 | Project Trident Launch Day | Business Case & Scope | Readiness | Unidentified Gas (UIG) has not been mentioned in the project approach. How much of the initial business case will be based on reducing UIG volatility? Would a UNC freeze not be a blocker to potential reductions to this volatility? | Project Delivery | Steve Brittan | Thank you for raising this. Our business case for Project Trident at this stage (Strategic Outline Case) does not reference UIG. From our Project Trident Launch event, we have logged UIG as an element to consider within the Outline Business Case alongside the impacts of our recommendations for elements of UNC freeze.
QA003 | 09.09.2024 | Project Trident Launch Day | Costs | Funding | Do the costs within BP25 cover all the steps within pre-procurement? Will the costs operate like other change initiatives (for example decarbonisation with a call off and rebate) and will there be more detail on what activities are being funded? | Finance | James Spicer | The FY25/26 costs presented at the Project Trident Launch event will be inclusive of the all the steps within pre-procurement referenced in our presentation. These will be presented in the first draft of BP25, which will contain further detail on the activities being funded. We expect the costs to operate like the other change initiatives with a call off and rebate option.
QA004 | 09.09.2024 | Project Trident Launch Day | Governance | Decision-making | Who will be the decision makers within Project Trident throughout the course of the project and activities, such as requirements gathering? | Project Delivery | Nick Partridge / Steve Brittan | Project Trident has a governance framework that describes the decision making forums. In addition to these forums, the ultimate decision-makers for Project Trident will be the Xoserve Board, including the customer nominated directors. Further details can be found on this page: https://www.xoserve.com/about-us/about-xoserve/our-role-and-customers/funding-governance-and-ownership/
QA020 | 2024-11-19 | BP25 Confidential Briefings | Business Case & Scope | Business Case | Who will make the decisions on the OBC and chosen supplier? | Project Delivery | Clive Nicholas | Ultimately the decision as to what to include in the Outline Business Case will be made by the Xoserve Board but it will be produced in collaboration with customers and other stakeholders. Supplier(s) selection will be subject to a commercial process and therefore have an associated level of confidentiality. We are currently considering how we can include customer representation in the governance of the project and we expect to come forward with a proposal in the coming weeks.
QA022 | 2024-11-19 | BP25 Confidential Briefings | Delivery Approach | Design & Requirements | Will we be asking users for their requirements within this process? | Stakeholder Engagement | Emma Johnson | Project Trident will provide like-for-like (or better) functional requirements for the UK Link system, with very limited ability to introduce new requirements to the process. However it is vital that we engage with users to understand how we can minimise impacts of the new solution to deliver against these requirements. Our next step is to understand, compared to our as-is solution, what the to-be requirements will be to maintain like for like (or better) functional requirements. We’ll be using customer feedback within our research to inform scoring against the criteria presenting in the SOC (including minimising customer impact and maintaining like-for-like or better functional requirements). This took place in a series of workshops focusing on UK Link Pain Points in H1 2025.
QA024 | 2024-11-19 | BP25 Confidential Briefings | Delivery Approach | Architecture | Our biggest interfaces are Gemini; are you saying that there will be no changes to our interfaces at all? | Project Delivery | Dave Turpin | The extent of any consequential change to Gemini will only be known once the programme is fully scoped following the Full Business Case. It is a project objective to keep these to as low a level as possible.
QA025 | 2024-11-19 | BP25 Confidential Briefings | Costs | Costs | If there is a consequential change to Gemini as a result, who picks up the cost? | Project Delivery | Dave Turpin | Consequential changes to CDSP systems are usually funded by the programme requiring the changes, in this case Project Trident.
QA026 | 2024-11-19 | BP25 Confidential Briefings | Governance | Governance & Assurance | 3rd party assurance, is this some assuring on costs? | Assurance | Clive Nicholas | Project Trident has solicited independent 3rd party assurance from PWC. This will include assurance against project costs, by comparing Project Trident against comparable industry projects on various aspects such as testing timelines.
QA027 | 2024-11-19 | BP25 Confidential Briefings | Governance | Governance & Assurance | 3rd party assurance - Would they report back to the board and customers? | Assurance | Clive Nicholas | We recognise the value that third party assurance can provide to the successful delivery of the project. We appointed PWC in Q1 2025 to provide this. We believe it appropriate that the audience for the assurers' assessments and recommendations to not be isolated to the project team but extended to the Xoserve Executive, Board, customers and other stakeholders. The organisation appointed will be expected to provide assurance for the project itself and also for the industry participants.
QA028 | 2024-11-18 | Email to Business Planning account | Delivery Approach | Architecture | Will the change to UK link require any change to the current file flow format? | Project Delivery | Nick Partridge | We are at the start of a consultative process to select our preferred option for Project Trident. One of our key principles within this selection process is to minimise impact to customers, however it is likely that customers should anticipate some degree of change to their traditional file flows when we come to implement Project Trident (currently anticipated before 2030). We expect there to be benefits to reviewing file flow processes throughout the course of Project Trident and considering if there are benefits to customers for us doing so whilst reimplementing the UK Link solution and benefitting from the adoption of new technology and processes throughout the course of the programme.
QA029 | 2024-11-18 | Email to Business Planning account | Costs | Funding | How do you anticipate the project cost to be smeared to shippers? Will this be via volume, MPRN count or some other calculation? | Finance | James Spicer | Project Trident costs are shared across customers of the data services contract (DSC). Organisations share of these costs is based on their portfolio size (the count of meter points, applicable for Shippers, DNOs and IGTs) and is detailed in our Business Planning documentation available on the BP25 minisite.
QA030 | 2024-11-20 | BP25 Confidential Briefings - Follow up | Stakeholder Engagement | Customer updates & input | How can customers access project materials that are version controlled, easily accessible and reduce confusion? | Stakeholder Engagement | Emma Johnson | For Stakeholder Engagement, we will ensure all Project Trident focused material is available on the dedicate webpage - https://www.xoserve.com/products-services/data-products/uk-link-system/project-trident/ To date, mainly finalised documentation has been shared, so there is no requirement for external version control, however, some active documents, like the Project Trident query log are labelled with a Latest Review date and notifications will be issued to all Project Trident subscribers.
QA034 | 2025-02-05 | Stakeholder Engagement call - 05/02/25 | Governance | Governance & Assurance | How will ARB and the EA tool ensure that no processes will be overlooked to avoid future black holes in the processes occurring? | Architecture | Andy Morrey | The Enterprise Architecture (EA) tooling and Architecture Review Board (ARB) are essential in the compilation, update and governance of the 67 TOGAF* artefacts used to describe the Xoserve architectural landscape. One of these 67 artefacts is the Process Catalogue which will hold details on every process within the Xoserve business (including UK Link). This artefact will reside within the EA tool along with the process maps for each process documented. The EA tool will allow the Enterprise Architecture function and wider Xoserve teams to visualise a process, its owner, the teams involved, the data processed, which applications support the process and even the infrastructure that all of the above runs/resides on. One role of the ARB is to ensure that the Process Catalogue and the many other TOGAF artefacts are kept upto date as and when changes are in the pipeline or implemented, keeping the holistic view of the Xoserve architectural landscape relevant. This is done by having all internal change (business and technical) come through the ARB for guidance and approval, providing a consistent steer in line with our Architecture Principles. By aligning our CDSP estate documentation to TOGAF now, we ensure a framework is in place to avoid the suggested black holes consistently across all change projects, most notably Project Trident. *The Open Group Architectural Framework
QA036 | 2025-02-05 | Stakeholder Engagement call - 05/02/25 | Delivery Approach | Planning | There were some high level timelines published with the SOC, appreciate these were early and subject to change, but has the thinking around timescales or timelines been affected by the market engagement exercise? | Project Delivery | Nick Partridge | The Market Engagement exercise helped us better estimate timelines for implementation post-contract award to a Delivery Partner. These timelines for the implementation for Project Trident will vary depending on the option for the new UK Link Solution and the Delivery Partner chosen. As of August 2025, we have shared a preferred hypothesis and begun a customer consultation which will inform the preferred option within the Outline Business Case.
QA037 | 2025-02-05 | Stakeholder Engagement call - 05/02/25 | Delivery Approach | Procurement | There is a suggestion to minimise the numbers of vendors involved, but how are we making sure that those procured 'play well' together so that industry doesn't suffer because of the (potentially) complex relations? | Procurement | Lorraine Owen | It is recognised that complexity and risk increases the higher the number of vendors involved in the project. Appropriate contractual provisions, ways of working and governance will be put in place to manage the risks associated with appointing more than one vendor.
QA038 | 2025-02-05 | Stakeholder Engagement call - 05/02/25 | Delivery Approach | Resources | If a future vendor is not performing, how will Xoserve ensure it is managed swiftly, effectively and with penalties if needed? | Procurement | Lorraine Owen | Xoserve’s contract with the awarded vendor(s) will include the appropriate provisions and remedies as well as the governance arrangements to enable us to manage the performance of the selected vendor(s).
QA043 | 30/04/2025 | Customer call | Stakeholder Engagement | Customer updates & input | How will customers be consulted on the existing experience of the UK Link services? | Stakeholder Engagement | Emma Johnson | Moorhouse Consulting has been engaged to work with customers to identify and validate key customer pain points with UK Link, as part of Project Trident. They will run a series of workshops during June & July 2025. The purposes of these workshops are: 1. To validate known customer pain points around UK Link and to understand the frequency and severity of these from a user perspective. 2. To identify any new or previously undocumented pain points, and/or any existing workarounds being adopted by users to navigate UK Link issues or limitations, highlighting any discrepancies between our internal understanding and user experiences. 3. To clarify what customers can expect from Project Trident and how customer feedback will be used to influence future changes.
QA044 | 2025-05-06 | Email from customer | Stakeholder Engagement | Customer Advisors | It was our understanding that customer representation would be independent of Xoserve, with the representative appointed by us (Shipper representative appointed by Shippers) as completed within other major transformation projects e.g. MHHS. Will the customer representative be appointed by Xoserve and paid for by Xoserve? | Governance | Nick Partridge | Project Trident would be funding the costs of the role, via BP25 funding if required (in case, there are individuals who could take on these responsibilities as part of their existing roles in the industry). The roles will be appointed by Xoserve's Project Trident Steering Committee. A requirement of this role would be to represent the voice of the customer in Steering Group decision-making, for which an essential part would be for the individual to take a view independent from Xoserve Management. Our proposal for this isn’t the same as the nominated roles within MHHS or the Xoserve Board at this stage. It was our intention for the role to be interviewed and for shipper/GTs/iGTs to be part of the interview panel. Due to not finding an available candidate after engaging with the market from February 2025, we intend to speed up the process by appointing two representatives (one for Shippers / and one for GTs/iGTs) in on an interim basis (likely 6 months) before decision-making around the Outline Business Case (OBC) takes place. We continue to look for a longer-term solution. We think the assurance we need is different to MHHS and Nexus as Project Trident focuses primarily on providing like-for-like (or better) functional requirements to the current UK Link and on technology re-platforming/modernisation. To adapt this, we have also adopted an additional Independent Assurance Partner in PWC, who will provide an independent view on how the project is progressing, particularly on the tech & procurement processes, and can report their findings directly to customers where required within existing forums (eg CoMC).
QA045 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, what is your definition of large shipper, a shipper with large amounts of sites or a shipper that ships large amounts of gas? | Industry Customer Engagement | Emma Johnson / Nicola Garland | We have defined Large Shippers based on the number of meter points rather than AQ. This segmentation is because we expect that several shippers with large AQs will fall into the I&C Shipper category. A large shipper is one that has over 1 million supply points, an I&C shipper is one whose business is to supply predominantly non-domestic customers and other shippers and service provider are those not covered under the large or I&C Shipper definition. If you have a question about which category your organisation falls into, please contact us at communications@xoserve.co.uk
QA046 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, 1 week for pre-read material is not enough time for us to generate conversations internally. Can this be sent out sooner? | Industry Customer Engagement | Emma Johnson / Nicola Garland | We have committed to sharing pre-reading material at least one week before each workshop. Where possible, we will share pre-reading material earlier than this to allow more time for internal conversations.
QA047 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, what's the justification for IGTs only having one workshop? | Industry Customer Engagement | Emma Johnson / Nicola Garland | Each organisation is invited to a total of four hours of workshops. Through the validation of the existing pain points that we’ve captured, we have noticed that there are a larger number of UK Link pain points that exist within the Shipper community in comparison to the GT and IGT community. We have made the GT and IGT sessions longer (they are three hours, rather than two), and this decision was made based on not taking huge amounts of time out of people’s calendars whilst also capturing all relevant pain points. The number of and length of sessions directly reflects the amount of time we have estimated we will need to have conversations with the different cohorts. If the need for an additional session is identified we will schedule a subsequent workshop with the cohort.
QA048 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, are there any caps on attendance for organisations? Some businesses have multiple areas who have different focus areas so a single attendee might not be enough. | Industry Customer Engagement | Emma Johnson / Nicola Garland | No, we are not applying any organisational caps on the number of attendees. We recognise that different organisations will have different structures of roles and therefore would want to send experts from certain processes to the workshops. We track sign-ups for the workshops and where an individual organisation has multiple sign-ups, we may have a discussion with the contract manager to confirm the value of all the attendees.
QA049 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, why are shippers being split between sessions? Isn't it better for issues to be discussed between all shippers together? | Industry Customer Engagement | Emma Johnson / Nicola Garland | We decided that the best way to have conversations with the shipper cohort was to break it down so that we can really get into the detail and have detailed technical conversations. We want to ensure all attendees have the opportunity to input and contribute. The shippers have therefore been broken down into smaller groups to aid the facilitation of smaller, workshop-style conversations that we hope to have, particularly as the sessions are being run virtually.
QA050 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, will you be providing the view of the Shipper community? | Industry Customer Engagement | Emma Johnson / Nicola Garland | In the workshops we will be collating the customers’ view of the pain points that they have with the current UK Link system. The view will be from a Shipper, IGT and Transporter view and these will be shared with all cohorts. The impact of the current pain points and the benefits of resolving them will be captured which will feed into the business case assessment for Project Trident.
QA052 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshops, who are the decision makers on what goes forward and what doesn’t from the information gathered? | Industry Customer Engagement | Emma Johnson / Nicola Garland | Project Trident and the decision-making governance structure will inform the way that decisions are made throughout the project with the Xoserve board being the ultimate decision maker for Project Trident. Moorhouse is not a decision maker within the project. Moorhouse’s role is to facilitate engagement with industry and ensure we understand customers’ pain points, prepare a detailed report, and provide it as input to the business case for project.
QA053 | 2025-05-15 | Workshop Launch Webinar | Business Case & Scope | Business Case | Is there a clear direction on how much effort should be allocated to enhancements compared to just delivering a like for like system? | Industry Customer Engagement | Emma Johnson / Nicola Garland | Project Trident will provide like-for-like (or better) functional requirements for the UK Link system, with very limited ability to introduce new requirements to the process. The business case will determine which option is most optimal for the replacement of the current UK Link system. Moorhouse is fundamentally interested in hearing about pain points, and the impacts and benefits that each of these have on your organisations. Our pain point workshop report, which we will launch in open sessions at the end of July, will summarise the discussions that we've held with the industry and will feed into the business case, allowing the Xoserve board to make an informed decision on the future system requirements.
QA054 | 2025-05-15 | Workshop Launch Webinar | Delivery Approach | UK Link Pain Point Workshops | For the H1 2025 UK Link Pain Point workshop outputs, what overlapping reviews are being completed so things are not siloed? | Industry Customer Engagement | Emma Johnson / Nicola Garland | The UK Link Pain Point report captures several areas in each individual workshop that will be needed for further exploration following the sessions. As part of our final report we have collated all the individual workshop feedback, grouping together individual feedback into themes. We’ll validate how these areas interact with other initiatives currently undertaken by the Xoserve team to ensure that the work is not carried out in silo from other initiatives.
QA055 | 2025-05-15 | Workshop Launch Webinar | Stakeholder Engagement | UK Link Pain Point Workshops | For the H1 UK Link Pain Point workshops, are you using the insight from CRM tickets to provide insight? Or are issues only being obtained from the workshops? | Industry Customer Engagement | Emma Johnson / Nicola Garland | Yes, we have several sources of information on existing pain points which include insight from CRM tickets, insight from ICS surveys and information from workshops within Xoserve that we have worked through ahead of the workshops and that will form part of the pre-reading materials that we will share.
QA056 | 2025-05-27 | Project Trident Introductory Webinar | Delivery Approach | Industry change | Will there have to be any industry code / regulatory changes raised? | Governance | Nick Partridge | We are currently unsure if there are any industry code or regulatory changes that will be required by Project Trident for the UK Link modernisation. Project Trident aims to provide like-for-like functional requirements as the current UK Link solution and will continue to evaluate if there are changes that might be required. Industry or regulatory change if required will be shared through BAU change processes and the Project Trident change control process will help us identify the impacts for Project Trident and customers.
QA058 | 2025-05-27 | Project Trident Introductory Webinar | Delivery Approach | Planning | What is the plan to provide test data to support industry testing? is it already factored into the plans? | Testing | Nick Partridge | It is an upcoming Project Trident deliverable to write a Testing Strategy. This will be helped by our Delivery Partner to shape the level of customer testing required and will vary on the nature of the solution. Customers will be informed and involved with the shaping of go-live, including testing, as we get closer to confirming the solution and Delivery Partner at the Full Business Case stage.
QA059 | 2025-05-27 | Project Trident Introductory Webinar | Delivery Approach | Industry change | How will the transition to Code Managers be accommodated within the Trident program? | Governance | Nick Partridge | We don't yet know how code reform and any code managers will impact Project Trident and eagerly await the outcomes of the Ofgem consultation. Code Reform is important to Project Trident as Code management gives a more structured approach to UNC changes. For Project Trident, a Code Manager will: 1. Provide more clarity in the code change roadmap in the lead up to implementation. This allows us to maximise the change periods before limitations on code changes during the build phases are applied. 2. Provide more clarity on the changes expected after implementation, so that the solution can be built to better match future requirements. 3. The timing of the allocation of a code manager is important to Project Trident as it is likely that this will occur between 2025 and 2030 and could bring uncertainty to project planning if they do not closely communicate.
QA061 | 2025-06-02 | 121 Customer Call | Stakeholder Engagement | Customer Advisors | How will the Customer Advisors represent all customer groups knowing that not all customers operate the same? | Stakeholder Engagement / Governance | Emma Johnson | In May 2025, we advertised our intention to appoint two advisors on a 6-month trial basis, in the form of two roles: • Customer Advisor – Shippers who provides the voice of the gas shippers. • Customer Advisor – Transporters who provides the voice of the Gas Transporters and Independent Gas Transporters (IGTs). We have appointed on an interim basis as a trial of the role being split into two. Towards the end of their 6-month term, we will be reviewing the success of the roles and whether the candidates would be suitable/available to stay on a longer term basis. At this point, we will share our plans to handover information if required.
QA063 | 2025-06-02 | 121 Customer Call | Stakeholder Engagement | UK Link Pain Point Workshops | For the upcoming Customer Workshops, we believe that it would be beneficial for Project Trident to have joint constituency forums where discussions are held collectively and collaboratively, to ensure full transparency. Is this possible? | Stakeholder Engagement / Governance | Emma Johnson | We have split the UK Link pain point workshops by customer type due to the different kinds of pain points and customer journeys that different groups experience. We recognise the benefits of bringing together cross-customer group discussion. We held a collaborative customer session on 24th July 2025 where we shared the findings from all workshops collectively.
QA064 | 2025-06-06 | Customer email | Governance | Customer Advisors | How are you continuing to look for a longer-term solution to Customer Advisors? Can you provide me some information on what that looks like please? Is it still your intention to find a permanent position with Shipper/GT/iGTs being a part of the interview panel – noting that the interim could be a candidate for selection. | Stakeholder Engagement / Governance | Emma Johnson | Our long-term solution is still to be determined based on the success of the new Customer Advisor roles. Our priority with the Customer Advisors is to improve the trust in, credibility of and quality of the decision-making process for Project Trident and we’ll need to review against this before knowing what the longer-term solution looks like. For the new Customer Advisors, we have appointed on an interim basis as a trial of the role being split into two. Towards the end of their 6-month term, we will be reviewing the success of the roles and whether the candidates would be suitable/available to stay on a longer-term basis. This will determine the next steps in terms of whether the roles remain split, are combined or reworked to better suit requirements –this decision will determine the appointment/selection process.
QA068 | 2025-06-17 | Customer Advisor Launch webinar | Governance | Customer Advisors | As this is an add on to their day jobs, how are we ensuring that this representative roles get the adequate / required dedication? | Stakeholder Engagement | Emma Johnson | These roles will be managed in alignment to the agreements that we have in place with our Customer Advisors which specifies that these roles will be on a part time basis. We trust our Customer Advisors to share where they are unable to fulfil their commitments to Project Trident in line with their agreements.
QA069 | 2025-06-17 | Customer Advisor Launch webinar | Governance | Customer Advisors | For the Customer Advisor update sessions, will there be a dedicated page to share the advisor information for those who cannot attend the sessions mentioned? | Stakeholder Engagement | Emma Johnson | Thank you for raising this. Following the Customer Advisor sessions with customers, we will provide meeting summaries for those who are unable to attend. Questions and their responses will be captured and shared within this rolling Q&A log.
QA070 | 2025-06-17 | Customer Advisor Launch webinar | Stakeholder Engagement | Customer updates & input | For the comms which go into the mailbox how are we going to ensure that consistent information on those responses are cascaded to all? | Stakeholder Engagement | Emma Johnson | We care about making sure that our diverse customer group can stay up to date with all updates on Project Trident. To provide summaries of recent questions, we will use the rolling FAQ log and will continue to be published on the Project Trident homepage. To provide bigger updates, we will use our monthly newsletter, The Tide, to ensure important topics are proactively brought to stakeholders attention.
QA072 | 30/07/25 | Preferred Hypothesis Customer Briefing | Business Case & Scope | Preferred Hypothesis | Are we being asked to sign off the hypothesis without knowing the costs? We need to ensure value for money. | Business Case | Amy O'Connor | Within the HMT Green Book approach, we work to reduce the ambiguity at each stage and we'll consult with customers for their thoughts at each stage. The cost analysis gets more detailed as we follow the process. In the Strategic Outline Case, published in September 2025, we presented a cost range for Project Trident as an indicative cost guideline based on delivering a project the size and scale of Trident. In the Outline Business Case we will be providing indicative costs against the options, and a range for the preferred option. The Full Business Case will have more detailed costs against the preferred solution, in advance of this option being procured and design & building taking place.
QA073 | 30/07/25 | Preferred Hypothesis Customer Briefing | Business Case & Scope | Preferred Hypothesis | Have we got an understanding as to what / how the hybrid option will address the 'pain points' raised? i.e. are there pain points that this option will not be able to address? | Business Case | Amy O'Connor | Our Preferred Hypothesis considers how UK Link pain points could be addressed and we expect that, if selected, this could largely take place in Step 2. All pain points will be subject to a feasibility assessment and some may be addressed within BAU CDSP delivery, outside of Project Trident.
QA074 | 30/07/25 | Preferred Hypothesis Customer Briefing | Stakeholder Engagement | Regulator | As a "Qualifying Central System" what role, if any, do Ofgem have in the decision to proceed with this replatforming? | Stakeholder Engagement / Governance | Emma Johnson | We have engaged Ofgem with Project Trident, including on our preferred hypothesis. To date [August 2025], they have asked to be an informed observer on Project Trident. We see Project Trident as a Technology refresh programme, different to industry programmes such as MHHS, and are therefore not currently expecting the same level of involvement.
QA075 | 30/07/25 | Preferred Hypothesis Customer Briefing | Delivery Approach | Delivery | Is the intent to also look at organisational and delivery / support methodology change here? 'Agile' was mentioned briefly but do you see software dev lifecycle change naturally coming out of the technical lift-and-shift? Is there a perception that that org change is even required? | Project Delivery | Nick Partridge | We are looking at both Agile and DevOpps approaches for Project Trident. This will be confirmed within the Outline Business Case.
QA076 | 30/07/25 | Preferred Hypothesis Customer Briefing | Business Case & Scope | Preferred Hypothesis | Will you look to leverage embedded AI and Automation features? Was that covered in the consultation? | Business Case | Amy O'Connor | As the scope of Project Trident is to provide 'like for like' functional requirements for UK Link of the future, this is not something that would be automatically included in the scope of Project Trident. Xoserve however is exploring opportunities for AI & Automation, and Project Trident could benefit from this work.
QA077 | 30/07/25 | Preferred Hypothesis Customer Briefing | Business Case & Scope | Preferred Hypothesis | Is there more detailed information on how you assessed the preferred Hypothesis? Particularly around complexity of delivery due to high level of integrations. | Business Case | Amy O'Connor | Within the Outline Business Case, we will use the Critical Success Factors to establish the most crucial assessment points for the options considered for future UK Link. One of the critical success factors is centred around delivery risk and reducing delivery risk of Project Trident to ensure delivery of the UK Link solution of the future does not compromise existing CDSP responsibilities and guarantees. The options are assessed on how complex the delivery of the solution will be with a view to ensure a low-risk approach for Trident.
QA078 | 30/07/25 | Preferred Hypothesis Customer Briefing | Delivery Approach | Planning | If I have understood the hypothesis correctly, Step 1 re-platforms UK Link (as is) to an updated version of SAP, and Step 2 is designed to address the pain points? If so, do you have approx timelines for the completion of each step? | Business Case | Amy O'Connor | As part of the OBC we are currently assessing the options and we continue to validate the preferred hypothesis. This means we are building knowledge through case studies of similar SAP upgrade and clean core approaches, feasibility assessment and cost/benefit analysis. To provide the evidence we need to validate the preferred hypothesis we have invested an partnership with Resulting IT and Esyasoft, experts in SAP upgrades to S/4 HANA, to inform us of feasibility and the approach we need to take for the UK Link we intend to deliver through Project Trident. Once we have validated this, our partners will support us with informing the timelines for delivery of steps 1 and 2 based on experience and the case studies we are using to validate. Once we have this validation we will shared this through the customer engagement channels set up to engage customers with Project Trident.
QA079 | 30/07/25 | Preferred Hypothesis Customer Briefing | Business Case & Scope | Preferred Hypothesis | Does the Preferred Hypothesis consider S/4 HANA hosting to be Cloud / Ground or Hybrid? | Business Case | Andy Morrey | The hosting strategy for Project Trident will be published within the RFP.
QA080 | 30/07/25 | Preferred Hypothesis Customer Briefing | Costs | Costs | Do we have a view on the cost impact of each option? | Business Case | Amy O'Connor | The indicative cost impact of each option will be presented at the Outline Business Case stage. This is part of the Solution Definition workstream where we have solicited indicative costs from some suppliers.
QA081 | 30/07/25 | Preferred Hypothesis Customer Briefing | Delivery Approach | Planning | Why have we chosen the 6 week holiday period for the consultation period? surely this isn't the best timing for people? | Stakeholder Engagement | Emma Johnson | We have chosen this time period carefully to launch the Preferred Hypothesis as: - It follows the conclusion of the UK Link Pain Point workshops on 07 July and enables us to consider these outputs within our Hypothesis. - It occurs in advance of BP26 Draft 1 and the publication of the Outline Business Case for Project Trident, and allows for us to feed in customer feedback into these responses. To acknowledge that this is taking place over a summer holiday period, we have extended the consultation length to 6 weeks until 12 September. If your organisation will have an issue in responding to the consultation within this time period, please contact communications@xoserve.com who will reach out to offer support.
QA083 | 24/07/25 | UK Link Pain Point Playback | Stakeholder Engagement | UK Link Pain Point Workshops | Some of the pain points raised at workshops that I attended potentially strayed into wider CDSP activities and were arguably outside the scope of a UK Link project. Does the report include all pain points if there was enough support for them, or does it filter out issues that perhaps fall outside the scope of UK Link? As an example, access to greater volumes of I&C supply point data may be a code and not a system issue. | Stakeholder Engagement / Governance | Emma Johnson | The UK Link Pain Point workshops include some aspects of the customer edge and service that are outside of the scope of Project Trident, however the full report will detail all pain points captured on UK Link. Moorhouse have included pain points that touch on the 'Customer Edge' systems e.g. DDP etc and feedback on broader service experience. We have not included issues on systems deemed to be out of scope (e.g. GES) but where raised we have passed these on internally to the relevant people in Xoserve. We have included issues where no current code modification has been raised (even if it may require one in the future), but not included one if there is already a code modification has been raised.
QA084 | 24/07/25 | UK Link Pain Point Playback | Business Case & Scope | Preferred Hypothesis | Design for Flexibility does seem to have elevated the scope away from SAP technical obsolescence to a wider ranging impact on associated systems. Has that objective been ratified now or are we still saying that is up for grabs as we drive to a fully defined requirements catalogue? | Business Case | Amy O'Connor | The Strategic Outline Case, published in September 2024, describes the flexibility that we are looking for from the future UK Link Solution and how this is in scope for Project Trident. As of August 2025, our assessments are looking at how much flexibility our preferred hypothesis can provide and whether additional investment are required to deliver the ambitions set out in the Strategic Outline Case.
QA085 | 24/07/25 | UK Link Pain Point Playback | Delivery Approach | Architecture | Do we have a slide on the architectural principles and strategies? | Architecture | Andy Morrey | We introduced our Enterprise Architecture function In November 2024 and these principles provided at our mid-year strategy event - you can see those principles in this summary report - mid-year-stakeholder-update-deck-v7.pdf
QA086 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Resources | How does Project Trident bring in 3rd party service providers? How do you balance the messaging between customers and 3rd party providers? | Commercial | Lorraine Owen | Project Trident has brought in 3rd party service providers following fair and robust procurement processes to support with the procurement phase. These providers have signed agreements and their involvement has been advertised within the Tide newsletter. Project Trident tries to broadcast as much information transparently as possible to help both customers and potential participants within future procurement processes. However, DSC customers are privy to commercially sensitive that 3rd Party Service providers who are not under agreement will be able to see. This is shared within DSC Governance Forums and within Business Plan briefings.
QA092 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Industry change | Are we liaising to make sure we don’t have multiple major industry changes happening at the same time? | Stakeholder Engagement | Emma Johnson | It is not clear what implementation timelines for Project Trident look like yet - this will be clearer at the point of the Full Business Case. In advance of this, Xoserve are liaising with Ofgem and other central bodies to avoid clashes where possible. We refer to Ofgem's strategic direction statement within the project.
QA093 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Business Case & Scope | Critical Success Factors | How are you defining the Future Agility metric? | Business Case | Amy O'Connor | As part of the case for change and scope of Project Trident, the requirement for UK Link to be "agile is based on an acknowledgement of the need to incorporate future industry change into the Trident solution to ensure UK Link can process facilitate this change in a more simple, streamline and cost effective way". Our critical success factors cover a wide range of 'must haves' as part of the project solution and delivery and within that we have noted adaptability and flexibility which reflects the agility requirement.
QA094 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Stakeholder Engagement | UK Link Pain Point Workshops | Will the customer pain point workshops inform a decision around Trident? How are these being used to inform project requirements? | Stakeholder Engagement / Governance | Emma Johnson | The UK Link Pain Point workshops that took place in H1 2025 will be used as a data point in the Solution Definition of Project Trident and as research within the Outline Business Case which will present a preferred option for Project Trident. The outputs from the workshops help us understand the constraints of the current system against the critical success factors within the Strategic Outline Case for Project Trident. Further detail on how the outputs have been used can be found within the Preferred Hypothesis briefing.
QA096 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Measures | Keen to know more about the whole Trident lifecycle - what about post-build? What metrics are we using beyond the build? | Business Case | Amy O'Connor | Beyond build we will be moving into the testing phase of Project Trident, delivering system integration testing, non functional requirements testing and user testing. This will be in line with industry regulatory requirements and customer system integration testing. The readiness phase will lead us into service run which will include standard and industry specific SLAs, and quality measures that will be agreed as part of the service integration process
QA097 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Planning | Why is the PQQ is starting before the OBC? We need to make sure we’re not wasting people’s time. How does the PQQ and OBC align/interact? | Project Delivery | Nick Partridge | The PQQ and RFP will be launched after the OBC is published and approved. The timelines show overlap as the development of the PQQ and RFP materials will begin before the OBC is published internally.
QA098 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Stakeholder Engagement | Customer updates & input | How many personas are you going to have? How are you going to get a set of personas to cover all users? | Stakeholder Engagement / Governance | Emma Johnson | User personas for the future UK Link won't be available until after the Full Business Case for Project Trident is published. Project Trident is following the HMT Green Book Business Case approach. This approach involves a clear set of critical success factors (including minimising customer impact) and a requirement to meaningfully engage customers throughout the scoping and procurement phases. As of August 2025, we are currently developing our Outline Business Case. Details on the user personas that we will be using will be available after the Full Business Case and the selection of the solution for the future UK Link have taken place.
QA099 | 2025-08-04 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Business Case & Scope | Business Case | Where is the scope of Project Trident defined? What is in and out of scope? | Business Case | Amy O'Connor | For the scope of Project Trident, please see our Strategic Outline Case as on the Project Trident homepage. In the Strategic Outline Case (SOC) we introduced the scope of Project Trident and discussed UK Link infrastructure within the Strategic Case and economic Case. This informed that all of UK Link was in scope of Project Trident with the core scope being delivery of a like for like solution for UK Link with any identified improvement opportunities to be included in scope which deliver future flexibility or agility in line with future industry requirements.
QA101 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Business Case & Scope | Critical Success Factors | Are the criterial success factors weighted? What do they mean in practice? | Business Case | Amy O'Connor | Our Critical Success Factors (CSFs) are published in the Strategic Outline Case for Project Trident. They outline attributes essential for successful delivery of Project Trident. The purpose of the CSFs is to provide assessment of the options for the solution and delivery of the project. We use the CSFs alongside the architectural principles for the solution, benefit vs cost analysis and feasibility assessment. They are not weighted against each other.
QA102 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Readiness | How would we manage the transition? Change freeze, direction from Ofgem etc.? How do we do a systems wide view on this? How will you assess high priority implementation into the old system? | Project Delivery | Nick Partridge | As of August 2025, it is unclear what the transition will be to the future UK Link Solution. This will be clearer upon the selection of the solution for Project Trident within the Full Business Case. In advance of this we have shared our Change Impact Assessment and Control Approach for how we will assess changes on both the BAU and future solution in the near future. This can be found here: https://www.gasgovernance.co.uk/sites/default/files/related-files/2025-06/5.1%20Project%20Trident%20Change%20Impact%20Assessment%20%26%20Control%20Approach_0.pdf
QA104 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Delivery Approach | Readiness | How much work will suppliers and all customers need to do to adjust to the implementation of any future UK Link solution? | Project Delivery | Nick Partridge | As of August 2025, it is unclear what suppliers and customers will need to do to adapt to the future UK Link Solution. This will be clearer upon the selection of the solution for Project Trident within the Full Business Case. Please be assured that one of our key principles and assessment criteria against the options is aiming to minimise customer impact within Project Trident.
QA105 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Stakeholder Engagement | Customer updates & input | What consideration has been made in the communication timelines that factors in lead times for customers and users to make any necessary changes (e.g. training, system updates, internal communications) as a result of Project Trident delivery? | Stakeholder Engagement / Governance | Emma Johnson | Communication timelines and any necessary changes won't be available until after the Full Business Case for Project Trident is published. Project Trident is following the HMT Green Book Business Case approach. This approach involves a clear set of critical success factors (including minimising customer impact) and a requirement to meaningfully engage customers throughout the scoping and procurement phases. As of August 2025, we are currently developing our Outline Business Case. Details on requirements for any potential changes for customers will not be clear until after the Full Business Case and the selection of the solution for the future UK Link.
QA106 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Business Case & Scope | Business Case | Has Xoserve got the capability and experience to assess and identify problems with the solution options and take the chosen solution option forward? And if not, how will it mitigate any knowledge/skills gaps? | Business Case | Amy O'Connor | We have developed partnerships with 3rd party experts in SAP products (such as the current UK Link solution), project & programme delivery and industry engagement. Our research is being assured by Independent 3rd Parties to mitigate risks.
QA107 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Stakeholder Engagement | Customer updates & input | How are you considering engagement when you reach your final solution choice? Will key users be involved in this process and can you be sure that all users’ needs are considered and assessed? What level of involvement are you looking for from customers? | Stakeholder Engagement / Governance | Emma Johnson | We continue to be grateful to our customers for their interest and involvement in Project Trident. Project Trident is following the HMT Green Book Business Case approach. This approach involves a clear set of critical success factors (including minimising customer impact) and a requirement to meaningfully engage customers throughout the scoping and procurement phases. To gather user feedback, we will use workshops (such as the H1 2025 UK Link Pain Point workshops), customer consultations (such as the preferred hypothesis customer consultation) and surveys. These will be promoted within existing DSC governance forums, within the Project Trident newsletter and directly to DSC Contract Managers and nominated engagement representatives.
QA109 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Costs | Costs | What are the key areas of cost (now and in the future)? | Project Delivery | Nick Partridge | Project Trident costs are presented at CoMC on a quarterly basis. If the Preferred Hypothesis progresses to the preferred solution within the Outline Business Case, the immediate costs will focus on the design, build and test phase. Our future costs will include hosting costs and license costs for the future UK Link.
QA111 | 2025-07-07 | Xoserve Customer Strategy Day - Project Trident Break out sessions | Costs | Costs | At what point will the costs become more accurate than they currently are? | Project Delivery | Nick Partridge | Project Trident is following the HMT Green Book Business Case approach. Our Outline Business Case will include indicative costs, however detailed costs will be included in the final Full Business Case.
QA112 | 2025-08-04 | Xoserve Customer Strategy Day, Customer Advisor Launch, Customer Emails | Stakeholder Engagement | Customer Advisors | What is the role of the Project Trident Steering Committee Customer Advisors? | Stakeholder Engagement | Emma Johnson | These roles are part of the Project Trident Steering Group, including the Xoserve Executive Team, and reports to the Xoserve Board. Their purpose is to bring a customer perspective to the highest level of Project Trident governance, building greater transparency, credibility and stakeholder trust within Project Trident decisions. They will provide the “Voice of the Customer” within the fortnightly Steering Committee and contribute to formal decision-making as part of the wider committee. They will solicit feedback from customers and can be called upon to provide relevant updates within Project Trident forums. These roles supplement, not replace, the existing governance, assurance and customer engagement structure for Project Trident. In this structure, customers can get involved by staying up to date with the Project through our newsletter, to make their voices heard within the existing Xoserve forums and constituency meetings or by contacting one of the Project Trident team.
QA113 | 2025-08-04 | Xoserve Customer Strategy Day, Customer Advisor Launch, Customer Emails | Stakeholder Engagement | Customer Advisors | How will the Project Trident Steering Committee Customer Advisors interact with customers? | Stakeholder Engagement | Emma Johnson | Our Customer Advisors Launch event presentation that took place on 18.06.2025 presents how the Customer Advisors will interact with customers and how customers can get in touch: https://xoserve.com/media/tmfbykmm/customer-advisor-launch-webinar-062025-v1_0.pdf
QA114 | 2025-08-04 | Xoserve Customer Strategy Day, Customer Advisor Launch, Customer Emails | Governance | Customer Advisors | Are Customer Advisors required under Steering Committee quoracy rules? How will they input into decision-making? | Stakeholder Engagement | Emma Johnson | The Customer Advisors are a core part of Steering Committee, and included in quoracy for decision-making. Decision-making is not made on a voting basis and the Committee works towards getting to a mutual consensus. Where this is not possible, a decision is made by the Steering Committee chair. The following document shares more on our Governance framework: https://xoserve.com/media/4ysd4ywh/project-trident-governance-overview-v2_1.pdf