## MT L2 Processes
|  |  |  | UK Link Secondary Interface Files |  | CSS Interface
Process Ref | Process Name | CSSC Impact | Process Ref | Files In | Files Out | API | Webhooks
1.01 | Manage Stakeholder Entry | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of creation. Shipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included. |  |  |  | RECM_SN_CSS00200 Supplier Arranged Appointment synchronisation RECM_SN_CSS00250 Market Participant Role Alliance
1.02 | Maintain Stakeholder Information | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of updates being madeShipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included |  |  |  | RECM_SN_CSS00200 Supplier Arranged Appointment synchronisation RECM_SN_CSS00250 Market Participant Role Alliance
1.03 | Manage Voluntary Discontinuance | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a Voluntary Discontinuance |  |  |  | RECM_SN_CSS00200 Supplier Arranged Appointment synchronisation RECM_SN_CSS00250 Market Participant Role Alliance
1.04 | Maintain Stakeholder | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of updates being madeShipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included |  |  |  | RECM_SN_CSS00200 Supplier Arranged Appointment synchronisation RECM_SN_CSS00250 Market Participant Role Alliance
1.05 | Manage Sanctions | Will need to include new feed into the CSS process for shipper sanctions |  |  |  | RECM_SN_CSS00250 Market Participant Role Alliance
1.07 | Manage Stakeholder Termination | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a termination |  |  |  | RECM_SN_CSS00200 Supplier Arranged Appointment synchronisation RECM_SN_CSS00250 Market Participant Role Alliance
1.09 | Manage Other Stakeholder Withdrawal | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a stakeholder withdrawal
2.02 | Create Supply Meter Point | Needs to be updated to include the CSS supply meter point synchronisation notification sent to the CSS following the successful creation of a meter point (assumed that this is only for in-scope meter type types, i.e. not NTS sites) |  | IMC, CIC | IMR,CCN, CGI | RECM_SN_CSS01100, Supply Meter Point Synchronisation RECM_SN_CSS00250 Supply Meter Point Synchronisation RECM_SN_CSS01200 Supply Meter Point RMP Event Synchronisation
2.04 | Amend Supply Meter Point | Needs to include the CSS supply meter point sync message (for CSS managed sites) following the update/change to an address, meter point status or network (GT or iGT) ownership |  | RFR | RFA, GCC | RECM_SN_CSS01100, Supply Meter Point Synchronisation RECM_SN_CSS00250 Supply Meter Point Synchronisation RECM_SN_CSS01200 Supply Meter Point RMP Event Synchronisation
2.05 | Amend CSEP Information | Where this is a change to the CSEP LDZ where there is a change in network ownership this needs to be reflected in the meter point update process models |  | IMA, CAI | DES, CIR, STN, AES, CAO, IME
2.06 | Manage Contract Enquiry | Process needs to be changed to reflect the provision of ad hoc queries. |  |  | NMR
2.07 | Manage Contract Nomination | Make the submission of a NOM request optional (for non NTS sites) as may only be needed where a network referral is required for capacity changes / distance requests and for any other referral reasons for CSS sites |  | NOM, BRN, BID, RSP, SBF | NMR, BRR, EPD, EPS, ESP, RFS, BIS, RSR
2.08 | Manage Contract Nomination Cancellation | No changes required, process expected to remain as-is |  | NOM
2.09 | Manage Contract Confirmation | Needs to support the inbound notification from the CSS for the shipper / supplier registration, and linking to a transportation offer (where required) and/or where settlement data (shell record) has been received and validated. Also needs to provide the Ceased Responsibility notification to the incumbent shipperThe existing nomination and confirmation process will only be used for sites out of scope of the CSS switching process.Changes may be required to support the submission of EMR and consumer detailsBulk Transfer (from 1.4.2) will be managed by CSS and will follow a similar process to a switch notification.SoLR will again be manged by the CSS following a notification from Xoserve.Process needs to include transporter forced registrations (following GSR, iGT auto confirmation, Mod 410A/431, etc.) which will be notified to the CSS (which we could receive a rejection from the CSS based on an invalid request) May need to include new outbound notification to the incoming shipper following a CSS triggered registration updateNeeds to be updated to included CSS change of shipper registration event updates (change of shipper where no change of supplier) |  | CNF, WAO | CFR, ASN, WOR, SWN, CID, CFR, TRF, TMC, MRI, SSR, DCF | RECM_SN_CSS01700 Initial Registration Request RECM_SN_CSS02100 Withdrawal Request | RECM_SN_CSS02800 RegistrationPendingSynchronisation RECM_SN_CSS02860 RegistrationSecuredActiveSynchronisation RECM_SN_CSS02860 RegistrationSecuredInactiveSynchronisation RECM_SN_CSS02860 RegistrationCancelledSynchronisation RECM_SN_CSS02850 RegistrationEventSynchronisation RECM_SN_CSS02600 RetailEnergyLocationSynchronisation RECM_SN_CSS02300 RegistrationPendingNotification RECM_SN_CSS02350 RegistrationEventNotification
2.10 | Manage Asset Change | Where the asset is isolated a combination of the isolation flag and meter point status will change the RMP status. Will need to include a change to the validation rules - Mapping rules from existing RQ, CO, LI confirmation status to Validated, Confirmed, Secured, Completed (CSS Statuses).UK Link will ignore market sector code when provided May need to be updated to capture the MAP ID of the installed asset |  | JOB, UPD, JOB, CDN | JRS, UNR, CDR, CDJ, PAC
2.11 | Manage Contract Change | Needs to remove supplier updates for in scope CSS sites as this will be managed as a switch by CSS and feed into 2.09 Site takeover will trigger an update to the CSS to change the network owner details Shipper Withdrawals will be notified by the CSS as registration status updates – De-activated (for CSS sites) Where there is a change to the Market Sector Code outside of the switching process then an outbound file will be issued to the registered shipper when the new Market Sector Code become effective (based on the effective date provided by on the CSS registration event sync message. SoLR updates will be received from the CSSMAP ID updates may need to be added into the process – depending on the chosen update method/route |  | GEA, SPC, MAM | GEO, SPR, MAS
2.12 | Manage Cancellation of Contract Change | Need to consider what impact a CSS switch will have on this process and if this would trigger anything to be cancelled (should be no impact)
2.13 | Manage Supply Meter Point Change | Updates will be issued to the CSS when various items change – e.g. address and meter point status changes. |  | IMA, SPC, CNC, EMC, MSI, AQI | NAC, CNR, CTR, EXZ, SPR, MSO, EXZ, MPE, LAC, NMS, SCR, AQR
2.15 | Generate Portfolio | Sending of portfolio data to DCC needs to be removed as this will transfer to the CSS. All changes to the Meter Point Status needs to feed into the CSS process – Site take over process needs to issue sync message to the CSS |  |  | EQL, EDL, EWS, IDL, IQL, DDS, DDU, IIL, PPN, TAP, SDM, CIN
2.20 | Manage Network Referrals |  |  | NOM | NRF, CRF, IGR
3.04 | Calculate Energy Consumption Predictions
3.05 | Calculate Energy Allocations
3.06 | Calculate Energy Balancing Positions
4.01 | Calculate Read Supply Meter Point Energy |  |  | UMR, UDR, UBR, DLC,RD1, SFN | URS, RPA, URN, SFR, MBR, MDR, PRN, PMN, RAT
DES | Manage DES Enquireis | Not currently modelled in the RRCLogical model but new REL and RMP data to be displayed and will need testings |  |  |  | RECM_SN_CSS02600 RetailEnergyLocationSynchronisation

## MT L3 Processes
CSSC to-be process | Process Ref | L2 Process Name | CSSC Impact | Process Ref | L3 Process Name | Primary Text/EL Comment | Test Category | Industry Process Name | Test Scenarios | File Out | Files In | UK Link Files In | UK Link Files Out | Comments (Files) | CSS Interfaces Inbound | CSS Interfaces Inbound
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 | Manage Stakeholder Entry | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of creation. Changes may be required to include the new user accreditation process under REC (details of this are still to be defined)Shipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included | 1.01.01 | 1.01.01 Validate Application | Internal tests for regression. Process isn't changing we do need to test the update to CSS. Not sure any external Shipper would want to test | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.02 | 1.01.02 Process Confidentiality Agreement |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.03 | 1.01.03 Process Accession Agreement |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.04 | 1.01.04 Process Supplier Deed of Undertaking |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.05 | 1.01.05 Confirm Stakeholder Agreement to Relevant Obligations |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.06 | 1.01.06 Manage Contact Details for Financial Security |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  | New screens for setting up Shipper - Network relationships | 1.01.07 | 1.01.07 Manage Stakeholder Activation | Shipper or Network may want to test | Consequential Change | Gas Industry Stakeholder Amendment | Accepted, Rejected Class 1,2,3,4 GT, iGT | N/A | N/A |  |  | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.01 |  |  | 1.01.08 | 1.01.08 Process Data Services Contract or UKLink User Agreement |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.02 | Maintain Stakeholder Information | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of updates being madeShipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included | 1.02.01 | 1.02.01 Monitor Stakeholder Company Registration | Internal tests for regression. Process isn't changing we do need to test the update to CSS. Not sure any external Shipper would want to test | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.02 |  |  | 1.02.02 | 1.02.02 Monitor Stakeholder VAT Number |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.02 |  |  | 1.02.03 | 1.02.03 Monitor Stakeholder Licence Status |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.02 |  |  | 1.02.04 | 1.02.04 Monitor Stakeholder Contact Details |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.02 |  |  | 1.02.05 | 1.02.05 Monitor Industry Scheme Registration |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.03 | Manage Voluntary Discontinuance | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a Voluntary Discontinuance | 1.03.01 | 1.03.01 Process Voluntary Discontinuance Notice | Internal tests for regression. Process isn't changing we do need to test the update to CSS. Not sure any external Shipper would want to test | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.03 |  |  | 1.03.02 | 1.03.02 Manage Authorisation of Voluntary Discontinuance Notice |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.03 |  |  | 1.03.03 | 1.03.03 Finalise Stakeholder Exit |  | Internal Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 08: Manage Gas Industry Stakeholders (To-be) | 1.04 | Maintain Stakeholder | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of updates being madeShipper to Supplier mapping and Shipper to network mapping needs to be enhanced and a feed into CSS included | 1.04.01 | 1.04.01 Process Stakeholder Amendments | External regression as process isn't changing | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.04 |  |  | 1.04.02 | 1.04.02 Process Merger and Acquisition Amendments |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.04 |  |  | 1.04.03 | 1.04.03 Process Shipper to Trader Amendments |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.04 |  |  | 1.04.04 | 1.04.04 Process Trader to Shipper Amendments |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.04 |  |  | 1.04.05 | 1.04.05 Manage Disclosure of Information |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.05 | Manage Sanctions | Will need to include new feed into the CSS process for shipper sanctions | 1.05.01 | 1.05.01 Apply Sanctions | External regression as process isn't changing | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.05 |  |  | 1.05.02 | 1.05.02 Monitor Sanctions |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.05 |  |  | 1.05.03 | 1.05.03 Remove Sanctions |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.07 | Manage Stakeholder Termination | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a termination | 1.07.01 | 1.07.01 Process Termination Instruction | External regression as process isn't changing | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.07 |  |  | 1.07.02 | 1.07.02 Invoke Supplier Deed of Undertaking |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.07 |  |  | 1.07.03 | 1.07.03 Appoint Supplier of Last Resort |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.07 |  |  | 1.07.04 | 1.07.04 Monitor Stakeholder Termination Status |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.07 |  |  | 1.07.05 | 1.07.05 Finalise Stakeholder Termination Exit |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 | Manage Other Stakeholder Withdrawal | Stakeholder process needs to be updated to reflect data feeds into the CSS/ REC code body on the back of a stakeholder withdrawal | 1.09.01.01 | 1.09.01.01 Validate Stakeholder Withdrawal | External regression as process isn't changing | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.03 | 1.09.01.03 Establish Portfolio Details |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.07 | 1.09.01.07 Finalise Stakeholder Role |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.08 | 1.09.01.08 Notify Stakeholder of Withdrawal |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.06 | 1.09.01.06 Establish if Communications Equipment to be Decommissioned |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.04 | 1.09.01.04 Notify Shipper of Outstanding Portfolio Details |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.02 | 1.09.01.02 Notify of Withdrawal Rejection |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
| 1.09 |  |  | 1.09.01.09 | 1.09.01.09 Notify Relevant Stakeholders of Withdrawal |  | External Regression | [6 empty] | No known files for this process - Need to ask customer lifecycle team. I don't believe CSSC impacts this process
CSSCC 01: Create Supply Meter Point (To-be) | 2.02 | Create Supply Meter Point | Needs to be updated to include the CSS supply meter point synchronisation notification sent to the CSS following the successful creation of a meter point (assumed that this is only for in-scope meter type types, i.e. not NTS sites) | 2.02.01 | 2.02.01 Validate Supply Meter Point Creation Request | Shipper, GT and IGT test for GT sites need CMS linked | Consequential Change | Meter Point Creation Creation of new Meter points via CMS and mapping of class. | Accepted, Rejected Class 1,2,3,4 GT, iGT | FOM MNC QMP IMC IMA | AES QMR IMR IME | IMC, CIC | IMR
CSSCC 01: Create Supply Meter Point (To-be) | 2.02 |  |  | 2.02.02 | 2.02.02 Create Supply Meter Point | Shipper, GT and IGT test | Consequential Change | [5 empty] | CCN, CGI
CSSCC 02: Pre-Registration SMP Updates (To-be), CSSCC 06: Manage Supply Meter Point Updates (To-be) | 2.04 | Amend Supply Meter Point | Needs to include the CSS supply meter point sync message (for CSS managed sites) following the update/change to an address, meter point status or network (GT or iGT) ownership | 2.04.01 | 2.04.01 Validate Supply Meter Point Changes | Post code changes, different LDZ, Address amendments. Need CMS linked for all site types. | Consequential Change | Supply Meter Point updates | Accepted, Rejected Class 1,2,3,4 GT, iGT | SPC, CNC, MAM, EMC, GEA, MAI, MID, RFA, MSI, CMS | MSO, SCR, CNR, CTR, MIO, MIR, LAC, NAC, STN, EXZ, GEO, RFR, MAS | RFR |  | This is an amendment to the creation of a meter point and not the data items associated with the SMP
| 2.02 |  |  | 2.04.02 | 2.04.02 Amend Supply Meter Point Details |  | Consequential Change | [5 empty] | RFA, GCC
| 2.05 | Amend CSEP Information | Where this is a change to the CSEP LDZ where there is a change in network ownership this needs to be reflected in the meter point update process models | 2.05.01 | 2.05.01 Validate CSEP Change | Not affected by changes, would you want to regression test internally? Consider if you wanted to do a full IGT end to end. | Consequential Change |  |  |  |  | IMA, CAI
| 2.05 |  |  | 2.05.02 | 2.05.02 Amend CSEP Details |  | Consequential Change | [5 empty] | DES, CIR, STN, AES, CAO, IME
CSSCC 05: Switching Sites (Enquiry and Nomination) (To-be) | 2.06 | Manage Contract Enquiry | Process needs to be changed to reflect the provision of ad hoc queries. | 2.06.01 | 2.06.01 Respond to Contract Enquiry Request | Shipper test and new test for API enquiry | Consequential Change | Supply point enquiry | Accepted, Rejected Class 1,2,3,4 GT, iGT | NOM | NMR |  | NMR
CSSCC 05: Switching Sites (Enquiry and Nomination) (To-be) | 2.07 | Manage Contract Nomination | Make the submission of a NOM request optional (for non NTS sites) as may only be needed where a network referral is required for capacity changes / distance requests and for any other referral reasons for CSS sites | 2.07.01 | 2.07.01 Validate Contract Nomination Request | Process changing slightly but only to change optionality into option rather than mandatory. Validation changes. Shipper input test | Consequential Change | Registration - Gain Registration - Loss Registration - Gain - Objection Received - Objection Upheld Registration - Gain - Objection Received - Objection Removed Registration - Loss - Objection Raised - Objection Upheld Registration - Loss - Objection Raised - Objection Withdrawn Registration - Forced Registration Registration - Nomination Request - accepted Registration - Nomination Request - rejected Registration - Supply Meter Point updates for a pending registration | Accepted, Rejected Class 1,2,3,4 GT, iGT | NRF, NMR, CFR, BRR, SNR, CRS, ASN, TRF, TMC, TRS | BRN, NOM, CNF, BRN, SNO, CSS | NOM, BRN, BID, RSP, SBF | NMR, BRR, EPD, EPS, ESP, RFS, BIS, RSR
| 2.07 |  |  | 2.07.03 | 2.07.03 Generate Offer Response | Regression for all sites | Consequential Change
| 2.08 | Manage Contract Nomination Cancellation | No changes required, process expected to remain as-is | 2.08.01 | 2.08.01 Cancel Nomination Request | Regression | Consequential Change |  |  |  |  | NOM
CSSCC 04: Supplier Switching and Change of Shipper (To-be) CSSCC 03: Forced Registrations (To-be) | 2.09 | Manage Contract Confirmation | Needs to support the inbound notification from the CSS for the shipper / supplier registration, and linking to a transportation offer (where required) and/or where settlement data (shell record) has been received and validated. Also needs to provide the Ceased Responsibility notification to the incumbent shipperThe existing nomination and confirmation process will only be used for sites out of scope of the CSS switching process.Changes may be required to support the submission of EMR and consumer detailsBulk Transfer (from 1.4.2) will be managed by CSS and will follow a similar process to a switch notification.SoLR will again be manged by the CSS following a notification from Xoserve.Process needs to include transporter forced registrations (following GSR, iGT auto confirmation, Mod 410A/431, etc.) which will be notified to the CSS (which we could receive a rejection from the CSS based on an invalid request) May need to include new outbound notification to the incoming shipper following a CSS triggered registration updateNeeds to be updated to included CSS change of shipper registration event updates (change of shipper where no change of supplier) | 2.09.01 | 2.09.01 Validate Contract Confirmation Request | Regression tests for sites out of scope only | Consequential Change | Registration - Gain Registration - Loss Registration - Gain - Objection Received - Objection Upheld Registration - Gain - Objection Received - Objection Removed Registration - Loss - Objection Raised - Objection Upheld Registration - Loss - Objection Raised - Objection Withdrawn Registration - Forced Registration Registration - Nomination Request - accepted Registration - Nomination Request - rejected Registration - Supply Meter Point updates for a pending registration | Accepted, Rejected Class 1,2,3,4 GT, iGT | NRF, NMR, CFR, BRR, SNR, CRS, ASN, TRF, TMC, TRS | BRN, NOM, CNF, BRN, SNO, CSS | CNF, WAO | CFR, ASN, WOR, SWN
| 2.09 |  |  | 2.09.02 | 2.09.02 Monitor Contract Confirmation Progress |  | Consequential Change
| 2.09 |  |  | 2.09.03 | 2.09.03 Finalise Contract Confirmation |  | Consequential Change | [5 empty] | CID, CFR, TRF, MRI, TMC, SSR
| 2.09 |  |  | 2.09.04 | 2.09.04 Cancel Contract Confirmation |  | Consequential Change | [5 empty] | DCF
CSSCC 07: Manage Meter Assets (To-be) | 2.10 | Manage Asset Change | Where the asset is isolated a combination of the isolation flag and meter point status will change the RMP status. Will need to include a change to the validation rules - Mapping rules from existing RQ, CO, LI confirmation status to Validated, Confirmed, Secured, Completed (CSS Statuses).UK Link will ignore market sector code when provided May need to be updated to capture the MAP ID of the installed asset | 2.10.01 | 2.10.01 Validate Asset Update | Regression | Regression | Meter Install, Meter Removal, Meter Exchange, Meter Details Update | Accepted, Rejected Class 1,2,3,4 GT, iGT | JRS, UPR, DRS, PAC | JOB, UPD | JOB, UPD | JRS, UNR
| 2.10 |  |  | 2.10.02 | 2.10.02 Update Connection and Disconnection Store | Regression not touched by process changes | Regression | Meter Install, Meter Removal, Meter Exchange, Meter Details Update | Accepted, Rejected Class 1,2,3,4 GT, iGT | CDJ, CDR | CDN | JOB, CDN | CDR, CDJ
CSSCC 07: Manage Meter Assets (To-be) | 2.10 |  |  | 2.10.03 | 2.10.03 Apply Asset Update | Shipper timing tests in conjunction with a switch plus regression test | Consequential Change | [5 empty] | PAC
CSSCC 10: Deactivation (To-be) | 2.11 | Manage Contract Change | Needs to remove supplier updates for in scope CSS sites as this will be managed as a switch by CSS and feed into 2.09 Site takeover will trigger an update to the CSS to change the network owner details Shipper Withdrawals will be notified by the CSS as registration status updates – De-activated (for CSS sites) Where there is a change to the Market Sector Code outside of the switching process then an outbound file will be issued to the registered shipper when the new Market Sector Code become effective (based on the effective date provided by on the CSS registration event sync message. SoLR updates will be received from the CSSMAP ID updates may need to be added into the process – depending on the chosen update method/route | 2.11.01 | 2.11.01 Validate Contract Change | Regression tests and to ensure updates flow to CSS and to ensure activities no longer allowed are not flowing to UK Link or flowing for out of scope sites only | Consequential Change | Withdrawal | Accepted, Rejected Class 1,2,3,4 GT, iGT | WAO | MPE, MPD, WOR | GEA, SPC, MAM
UK Link Existing Processes | 2.11 |  |  | 2.11.02 | 2.11.02 Update Contract Details | Regression | Regression | [5 empty] | GEO, SPR, MAS
UK Link Existing Processes | 2.12 | Manage Cancellation of Contract Change | Need to consider what impact a CSS switch will have on this process and if this would trigger anything to be cancelled (should be no impact) | 2.12.01 | 2.12.01 Cancel Request to Change Contract | Regression | Regression
UK Link Existing Processes | 2.13 | Manage Supply Meter Point Change | Updates will be issued to the CSS when various items change – e.g. address and meter point status changes. | 2.13.01 | 2.13.01 Validate Supply Meter Point Information Update | Regression tests and to ensure updates flow to CSS and to ensure activities no longer allowed are not flowing to UK Link or flowing for out of scope sites only | Regression |  |  |  |  | IMA, SPC, CNC, EMC, MSI, AQI |  | Address is updated via CMS so no file listed for this
UK Link Existing Processes | 2.13 |  | Market sector code updates needs to be changed as this will come from CSS. | 2.13.02 | 2.13.02 Apply Supply Meter Point Updates | Regression | Regression | [5 empty] | NAC, CNR, CTR, EXZ, SPR, MSO, EXZ, MPE, LAC, NMS, SCR, AQR | NAC is for address change
UK Link Existing Processes | 2.15 | Generate Portfolio | Sending of portfolio data to DCC needs to be removed as this will transfer to the CSS. All changes to the Meter Point Status needs to feed into the CSS process – Site take over process needs to issue sync message to the CSS | 2.15.01 | 2.15.01 Generate Portfolio | Regression | Regression | [5 empty] | EQL, EDL, EWS, IDL, IQL, DDS, DDU, IIL, PPN, TAP, SDM, CIN
|  |  | Business rules for the data feed to Gemini (MDS/AAQ) will need to change to align with new switching timeframes |  |  |  | N/A
CSSCC 05: Switching Sites (Enquiry and Nomination) (To-be) | 2.20 | Manage Network Referrals |  | 2.20.01 | 2.20.01 Facilitate Network Referral | Test with Shipper input and referral to GT and IGT's and their response | Consequential Change | GAIN | Accepted, Rejected Class 1,2,3,4 GT, iGT | NOM |  | NOM | NRF, CRF, IGR
? | 3.04 | Calculate Energy Consumption Predictions |  | 3.04.01 | 3.04.01 Calculate Non Daily Metered Output Nominations | Not affected by changes, would you want to regression test internally? Consider if you wanted to do a full end to end | N/A
| 3.04 |  |  | 3.04.02 | 3.04.02 Validate Daily Metered Output Nominations / Renominations |  | N/A
| 3.04 |  |  | 3.04.03 | 3.04.03 Calculate Output Nominations |  | N/A
| 3.04 |  |  | 3.04.04 | 3.04.04 Calculate LDZ Nominations Scaling Adjustment |  | N/A
CSSCC 11: Opening Meter Reads (To-be) | 4.01 | Calculate Read Supply Meter Point Energy |  | 4.01.01 | 4.01.01 Validate Read | Regression | Regression | Submit Meter Read, Submit Replacement Read | Accepted, Rejected Class 1,2,3,4 GT, iGT | JRS, URS, URN, MBR, MDR | UDR, UMR | UMR, UDR, UBR, DLC,RD1, SFN | URS, RPA, URN, SFR
| 4.01 |  |  | 4.01.02 | 4.01.02 Unsuspend Reads |  | Regression
| 4.01 |  |  | 4.01.03 | 4.01.03 Calculate Better Estimated DM Meter Reads |  | Regression
CSSCC 11: Opening Meter Reads (To-be) | 4.01 |  |  | 4.01.04 | 4.01.04 Estimate Read |  | Consequential Change | Submit Meter Read, Submit Replacement Read | Accepted, Rejected Class 1,2,3,4 GT, iGT | JRS, URS, URN, MBR, MDR | UDR, UMR
CSSCC 11: Opening Meter Reads (To-be) | 4.01 |  |  | 4.01.05 | 4.01.05 Report Meter Reads |  | Regression | Submit Meter Read, Submit Replacement Read | Accepted, Rejected Class 1,2,3,4 GT, iGT | JRS, URS, URN, MBR, MDR | UDR, UMR |  | MBR, MDR
| 4.01 |  |  | 4.01.06 | 4.01.06 Check Increase on Current Year Minimum |  | Regression
| 4.01 |  |  | 4.01.07 | 4.01.07 Assess Impact On Ratchets |  | Regression
| 4.01 |  |  | 4.01.08 | 4.01.08 Pre-Notify Ratchet |  | Regression | [5 empty] | PRN
| 4.01 |  |  | 4.01.09 | 4.01.09 Notify Finalised Ratchet |  | Regression | [5 empty] | PMN, RAT
| 4.01 |  |  | 4.01.10 | 4.01.10 Validate CV |  | Regression
| 4.01 |  |  | 4.01.11 | 4.01.11 Apply CV Changes |  | Regression
| 4.01 |  |  | 4.01.12 | 4.01.12 Calculate Shipper Share |  | Regression
CSSCC 09: Update Retail Energy Location (To-be) | NEW | [5 empty] | Consequential Change
Manage DES Enquireis | DES | Manage DES Enquireis | Not currently modelled in the RRCLogical model but new REL and RMP data to be displayed and will need testings |  |  | Tests following CSS input and regression for Shipper/Network inputs | Consequential Change

## Gemini Shipper
Ref | Functionality | Process | Participants
|  |  | Shippers | File | Online | API
1 | Portfolio Changes | Creation of a new LDZ site meter on D-1 with effective on D day |  |  | Y
2 |  | End-date an existing Meter id on D-1 with effective D day |  |  | Y
3 |  | Cancellation of approved gas nominations/renominations existing in Gemini for the end-dated meter id |  | Y | Y | Y
4 | Creation of activity number | Creation of activity number for new meter ids created |  |  | Y
5 |  | Generation of ACT File with new activity number & meter ids | ACT File | Y
6 | Daily Meter Nomination estimation | DM Nomination estimation run in the system |  |  | Y
7 |  | Display the estimated nominations for the new activity numbers created |  | Y | Y | Y
8 | Renomination | Place renomination all through the D day over-riding the system generated estimated nomination |  |  | Y | Y
9 | Energy Balancing | View the Balancing to check the Nomination position |  |  | Y | Y

## Gemini GT
Ref | Functionality | Process | GT | File | Online | API
1 | Portfolio Changes | Creation of a new LDZ site meter on D-1 with effective on D day | GMD File | Y
2 |  | End-date an existing Meter id on D-1 with effective D day | GMD File | Y
3 |  | Cancellation of approved gas nominations/renominations existing in Gemini for the end-dated meter id | NDN File | Y
4 | Creation of activity number | Creation of activity number for new meter ids created
5 |  | Generation of ACT File with new activity number & meter ids
6 | Daily Meter Nomination estimation | DM Nomination estimation run in the system
7 |  | Display the estimated nominations for the new activity numbers created | NDN File | Y
8 | Renomination | Place renomination all through the D day over-riding the system generated estimated nomination
9 | Energy Balancing | View the Balancing screen to check the Nomination position

## titles
Category
Internal Regression
External Regression
Gemini Regression
Regression
Consequential Change
N/A