## Sheet1
| CONSEQUENTIAL CHANGE MARKET TRIALS - INDUSTRY INTERACTION SCHEDULE | START DATE | END DATE | XOSERVE | SHIPPER | GT/iGT | Status | PRODUCT DESCRIPTION
1 | Industry engagement
1.01 | Draft organisation test schedules discussions agreed | 2021-02-15 | 2021-03-05 | Y | Y | Y |  | Test schedules to enable test step initiation to take place in line with each organisations test programme . This will be agreed btween Xoserve and the individual organisation
1.02 | Organisation Test schedules finalised | 2021-04-05 | 2021-04-09 | Y | Y | Y |  | Final test schedules in place prior to test execution
1.03 | Registration confirmation | 2020-11-23 | 2020-12-07 | Y | Y | Y |  | Registration template will be sent to all participants by Xoserve to confirm organisation, phase and code for testing
1.04 | contact information confirmation | 2020-11-01 | 2020-11-08 | Y | y | Y
2 | CCMT Re-launch
2.01 | webpage launch | 2020-06-30 |  | Y |  |  | complete | single point of contact for information regarding CCMT
2.02 | CCMT review & sign off schedule in place | 2020-05-01 | 2020-05-29 | Y | Y | Y | complete | list of all industry interactions to provide an understanding of forthcoming activities and requirement and enable resource management within Industry project teams
2.03 | CCMT document library established | 2020-06-30 |  | Y |  |  | complete | single point for all signed off and baselined documents for CCMT
3 | CCMT Approach approved
3.01 | CCMT Approach industry review (final ) | 2021-02-15 | 2021-03-05 | Y | Y | Y |  | All particpants to review the Approach document
3.02 | CCMT Approach industry sign off (final) | 2021-03-05 |  | Y | Y | Y |  | All participants to sign off the Approach document - this will be done through CCMTWG
4 | Test schedule principles agreed
4.01 | Test Schedule principles reviewed with industry | 2020-11-09 | 2020-12-04 | Y | Y | Y | with industry for review | Draft Test schedule pronciples will be issued to all particpants for review and comment
4.02 | Test schedule principles agreed | 2020-12-21 | 2021-01-15 | Y | Y | Y |  | All participants to sign off the principles
5 | DPIA in place
5.01 | DPIA - industry review | 2020-11-23 | 2020-12-11 | Y | Y | Y |  | DPIA to be provided by Xoserve for all participants to review
5.02 | DPIA - sign off | 2020-12-11 |  | Y | Y | Y |  | signed off DPIA
6 | Defect Management Plan agreed
6.01 | Industry contact information requested | 2021-02-01 | 2021-02-19 | Y | Y | Y |  | All participants to provide contact details for defect management
6.02 | Defect Management RQM user guide provided | 2020-12-14 | 2020-12-18 | Y | Y | Y |  | All particpants will have direct access to RQM to log & monitor defects
6.03 | Defect Management plan - Industry review | 2020-07-01 | 2020-07-31 | Y | Y | Y | with industry for review 03Jul20 | All participants to review and comment on the draft Defect management plan
6.04 | Defect Management plan - final industry review | 2020-12-21 | 2021-01-22 | Y | Y | Y |  | to provide final comments on the defect management plan
6.05 | Defect Management plan - industry walkthrough | 2020-12-21 | 2021-01-22 | y | y | y |  | Xoserve to arrange a walkthrough of the defect management plan
6.06 | Defect Management plan approved | 2021-02-26 |  | y | y | y |  | signed off defect management plan
7 | Release Management plan agreed
7.01 | Release Management plan - industry review | 2020-06-16 | 2020-07-15 | y | y | y | with industry for review 22Jun20 | All particpants to review and comment on Release Management
7.02 | Release management plan - final review | 2021-01-25 | 2021-02-12 | y | y | y |  | All particpants to review and comment on Release Management
7.03 | Release management plan industry sign off | 2021-02-15 | 2021-02-19 | y | y | y |  | signed off release management plan
8 | Entry and Exit criteria agreed
8.01 | entry & exit criteria - industry review | 2020-08-03 | 2020-08-31 | Y | Y | Y | with industry for review | Market Trial participants will need to have reviewed the Entry Criteria and feed back any comments. Participants will then have until 30Nov20 to ensure that the enty criteria is met
8.02 | entry & exit criteria - final industry review | 2020-12-21 | 2021-01-15 | Y | Y | Y |  | Market Trial participants will need to have reviewed the Entry Criteria and feed back any further comments. Participants will then have until 30Nov20 1 to ensure that the enty criteria is met
8.03 | entry & exit criteria - industry sign off | 2021-01-15 |  | Y | Y | Y
9 | RACI agreed
9.01 | RACI - industry review | 2020-07-16 | 2020-08-16 | Y | Y | Y | with industry for review | All participants to review and comment on the RACI
9.02 | RACI - final industry review | 2020-11-30 | 2020-12-11 | Y | Y | Y |  | All participants to review and provide final comment on the RACI
9.03 | RACI - industry sign off | 2020-12-11 |  | Y | Y | Y
10 | data provision to industry
10.01 | data provision to industry | 2021-02-22 |  | Y |  |  |  | All particpating organisation will receive their data portfolios in line with the agreed data requirements via SFTP
11 | SFTP in place
11.01 | SFTP information requested from industry | tbc | tbc | Y |  | Y |  | Xoserve to provide all particpants with a template for SFTP information and working with industry on queries
11.02 | SFTP information provided by the industry | tbc | tbc |  | Y | Y |  | all particopants to provide information to enable data transfer via SFTP
11.05 | SFTP tests with industry | 2020-12-14 | 2021-01-08 | Y | Y | Y |  | Market Trial participants will need to ensure that the SFTP process is set-up within their organisation prior to data provision ** note this can be a little later than 16th October data provision date if entering January 21
11.04 | SFTP in place | 2021-01-25 | 2021-01-25 | Y | Y | Y
12 | Industry system Access confirmed
12.01 | IX confirmed and in place | 2021-03-05 | 2021-03-05 | Y | Y | Y
12.02 | IX node structure shared with industry | 2020-11-30 | 2020-12-18 | Y |  |  |  | structure provided by Xoserve to particpants to ensure that technical teams can ensure IX is structured correctly to enable testing
12.03 | IX user guide sent to industry | 2020-10-30 | 2020-10-30 | Y |  |  |  | full user guide to support all particpants techniacl teams
12.04 | IX structure confirmed by industry | 2021-01-11 | 2021-01-29 | Y | Y | Y |  | all participants to confirm that all technical work has taken place
13 | API and Registration set up
13.01 | Registration Information requested from industry | 2021-01-04 | 2021-01-08 | Y |  |  |  | Xoserve provides an API registration template to collate the relevant information to enable techinal set up
13.02 | information provided by industry | 2021-01-08 | 2021-01-29 |  | Y | Y |  | all participants to provide Xoserve with API registration information to allow technical set up
13.03 | Registration contact information requested | 2020-11-30 | 2020-12-11 | Y |  |  |  | request to provide contact details during registration set up
13.04 | registration tested | 2021-03-22 | 2021-04-09 | Y | Y | Y |  | technical tests carried out to ensure that APIs can be tested effectively
14 | processes agreed with industry
14.01 | processes reviewed | 2020-10-05 | 2020-10-23 | Y | Y | Y | already reviewed, refresher to be sent | All participants to review and comment on baselined processes
14.02 | Final process review | 2020-11-30 | 2020-12-11 | Y | Y | Y |  | All participants to carry out final review and comment on baselined processes
14.03 | Final process industry sign off | 2020-12-11 |  | Y | Y | Y |  | processes signed off
15 | Reporting
15.01 | external reporting pack - industry review | 16Nov2- | 2020-12-04 | Y | Y | Y |  | All participants to review and comment on reporting pack
15.02 | External reporting pack - final industry review | 2021-02-08 | 2021-02-26 | Y | Y | Y |  | All participants to carry out final review and comment on reporting pack
15.03 | External reporting pack sign off | 2021-02-26 |  | Y | Y | Y |  | Approved reporting pack
16 | Partnering arrangements
16.01 | Draft partnering proposals | 2021-01-04 | 2021-01-15 | Y | Y | Y | with industry for review | xoserve to provide draft proposals for all participants to review and comment
16.02 | Final partnering review | 2021-01-04 | 2021-01-29 | Y | Y | Y |  | final review of all partnering arrangements by all participants
16.03 | provide relevant partnering information to industry | 2021-02-01 | 2021-02-12 | Y | Y | Y |  | Xoserve to provide any relevent reports following partnering definition . All parties to use the information to create test scripts with appropriate partners
16.04 | Partnering arrangements signed off | 2021-02-12 |  | Y | Y | Y |  | Partnering arrangements approved
17 | Query Management
17.01 | Query template provided | 2020-12-14 | 2020-12-18 | Y |  |  |  | Xoserve to provide the query template
17.02 | Query process review and comment | 2020-12-14 | 2020-12-18 | Y | Y | Y |  | All participants to review and comment on the query process
17.03 | Query management Email provided | 2021-01-11 | 2021-01-15 | Y |  |  |  | Xoserve to provide the Query mamagement email address to all participants
17.04 | Final process review and sign off | 2021-02-01 | 2021-02-19 | Y | Y | Y |  | Query managememt process approved
18 | GNG complete
18.01 | GNG decision made | 2021-03-12 |  | Y |  |  |  | Xoserve to confirm to all participants that CCMT will go ahead. This will be subject to entry criteria