## DSC Business Evaluation Report (BER)

| Change Title | Increase Frequency of FSG Payments |
| --- | --- |
| Xoserve reference number (XRN) | XRN5469 |
| Correla Project Manager | Richard Hadfield |
| Email address | DSC+ Change Development Manager |
| Contact number | +441212292559 |
| Target Change Management Committee date | July 2022 |
| Section 1: In Scope |  |
| This BER requests approval of funding of this change request for an additional 1.0 FTE, at a cost of £36,900 from September 2022 to March 2023 (and £63,300 from April 2023 to April 2024, and per annum thereafter but subject to any future DSC+ schedule changes that affect the daily FTE rate card) be added to the Business Operations Invoicing Team in order to provide a faster payment service for “Failure to Supply Gas” (FSG GSoP1) payments. XRN; Title; Type; Description; Link to Change Proposal; Impacts. 5469; Increase Frequency of FSG Payments; Xoserve change; To change the frequency of “Failure to Supply Gas” (FSG GSoP1) payments, from the current weekly/ad-hoc service, to a daily working day service.; XRN 5469 ¦ Xoserve; Business Operations Invoicing Team. |
| Section 2: Out of Scope |  |
| - This change will be delivered by the addition of FTE resource to the Business Operations Invoicing Team. System changes are not required and are therefore out of scope. - Process/System changes for Distribution Network Operators (DNOs), Shippers and Suppliers are not required and are out of scope. |  |
| Section 3: Funding required to deliver the change |  |
| BER Costs Key |  |
| Section 4: Estimated impact of the service change on service charges |  |
| XRN; Xoserve Service Area & Line; Impact; (+/-) Projected Change in Annual Cost. 5469; <<”Collective Service, amendment to Service Line” TBC by XOSERVE>>; Business Operations Team additional FTE resource to deliver an enhanced service.; £63,300 p.a.. Total; £63,300 p.a.. |
| Section 5: Project plan for delivery of the change |  |
| - July 2022 approval of BER - August 2022 recruitment and training - September 2022 start of new service (subject to successful recruitment and training) |  |
| Section 6: Additional information relevant to the proposed service change |  |
| Risk Margin XRN Ref; Risk Margin; Description. RISK; N/A; DNO/Shipper business/system processes are not able to support an enhanced/faster daily working day FSG payments process. Mitigation: Xoserve communicate to Shippers about the move to daily working day payments, ahead of the actual change.. ASSUMPTION; N/A; There will be no Business Operations system changes required to support faster FSG payments.. ASSUMPTION; N/A; There will be no changes to DNO/Shipper business/system processes to support faster FSG payments.. ASSUMPTION; N/A; There will be no changes to the Business Operations current system invoice creation runs (daily).. ASSUMPTION; N/A; There will be no change to the current Business Operations SLA for processing FSG payments (by next working day).. |

Please send completed form to: box.xoserve.portfoliooffice@xoserve.com

Document Version History

| Version | Status | Date | Author(s) | Summary of Changes |
| --- | --- | --- | --- | --- |
| 1.0 | For Review | 01.07.22 | Rajiv Patel | Finalise Review Version BER |

Template Version History

| Version | Status | Date | Author(s) | Summary of Changes |
| --- | --- | --- | --- | --- |
| 2.0 | Approved | 17/07/18 | Rebecca Perkins | Template approved at ChMC on 11th July |
| 3.0 |  | 23/06/2021 | James Rigby | Table added to section 1 More detailed table in section 3 More detailed table in section 4 Inserted a project plan example in section 5 Table added in section 6 |