## Slide 1: DSC Delivery Sub-Group
Monday 24th October 2022

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Capture

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
XRN 5564 - Gemini Sustain Plus
XRN 5565 - Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824)
XRN 5567 - Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067)
XRN 5569 - Contact Data Provision for IGT Customers
XRN5573 - Updates to the Priority Consumer process

## Slide 6: XRN 5564 - Gemini Sustain Plus
NGG wishes to modernise the Gemini platform in order to continue to provide required Capacity & Balancing Services as well as delivering system compliance against new UNC modifications.
NGG also wants to deliver change more efficiently whilst improving the customer experience.
The change will be known as the Gemini Sustain Plus programme. The scope of delivery will include:
Conversion of all the current Gemini functionality and code into modern (Java Microservices) code
Delivery of additional functional requirements
Delivery in line with non-functional requirements
Consolidation and re-design of Gemini screens
Implementation of Azure cloud infrastructure components (including replacing the current Oracle database)
Improvements to the support service arrangement to respond better to incidents and change (in line with new service levels and KPIs)
NGG require all of the programme scope to be delivered within a 2- year period, implementation to be specified in the Correla Delivery Plan.

## Slide 7: XRN 5565 - Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824)
The Government has proposed the EPG (Gas) Scheme, for domestic customers, to secure reductions in the energy bills of domestic customers within Great Britain. The intention is for the Central Data Service Provider (CDSP) to perform the function of the EPG (Gas) Scheme (the ‘Scheme’) Administrator and that the scheme to be implemented by 1st October 2022.
Modification 0824 confirms the role of the CDSP as the Scheme Administrator for the EPG (Gas) and gives them the relevant powers to make changes under the DSC in order to facilitate implementation and administration of this Scheme, from 1st October 2022, in line with the Government direction.
This change proposal seeks to design, build and implement the relevant functionality and processes in order for the CDSP to fulfil its role as the Scheme Administrator.

## Slide 8: XRN 5567 - Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067)
This change request proposes the ability to request a CSS message to be ‘resent’ if the Gas Retail Data agent (GRDA) has not received it. This ‘resend’ functionality is a key mitigation of impacts to UK Link system as a result of missing or ‘late’ Gate Closure messages. This resend message will NOT interface with DSC Core Customers, but these parties are listed as ‘impacted’ as the implementation of this change should reduce the risk of missing and ‘late’ Gate Closure messages.
Since CSS Implementation there have been a number of missing and ‘late’ gate closure messages (i.e. up to 19:00 hours – whereas at average volumes these should be received by 17:20hrs).
Introduction of a CSS refresh functionality would allow systems which interface with the CSS to request a re-send of out of sync messages, messages received after gate closure, or missing messages without the need of manual intervention.

## Slide 9: XRN 5569 - Contact Data Provision for IGT Customers
This Change Proposal has been raised at the request of IGT Customers and seeks to assess options that allow Contact Data that is not currently provisioned to IGTs available.
IGT Customers do not currently have full visibility of Contact Data that is held within UK Link systems against IGT Supply Meter Points that are within the relevant IGT organisations portfolio.
The lack of visibility of this data can inhibit IGTs in being able to conduct associated business activities, can present challenges in being able to address queries that may exist against associated properties, and reduce the completeness of data that IGTs require to have access to in their role as Gas Transporter.

## Slide 10: XRN5573 – Updates to the Priority Consumer Process
The current criteria in place to assign a Priority Consumer (who will be prioritised where there is a national gas emergency), has been updated at the direction of BEIS Secretary of State
Based on this, the relevant updates to the process are required to reflect the updated criteria and Priority Consumer Categories
There will be a need to replace the obsolete Category B, with one that permits the protection of sites of significance to national security or whose loss would pose a significant threat to welfare
Change Category C from a fixed financial threshold of damage to, damage costs calculated as a percentage of site value. This is relevant for sites over 2 million therms (58,600,000 kWhs) per annum.
The process for a site to apply to be a Priority Consumer must be updated to reflect these changes

## Slide 11: 2b. Change Proposal Initial View Representations

## Slide 12: 2b. Change Proposal Initial View Representations
None for this meeting

## Slide 13: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 14: 2c. Undergoing Solution Options Impact Assessment Review
None for this meeting

## Slide 15: 2d. Solution Options Impact Assessment Review Completed

## Slide 16: 2d. Solution Options Impact Assessment Review Completed
None for this meeting

## Slide 17: 3. Changes in Detailed Design

## Slide 18: 3a. Requirements Considerations
None for this meeting

## Slide 19: 3b. Design Clarification
XRN 5556.C - Contact Management Service (CMS) Rebuild – Version 1.2 – Detailed Design
XRN 5541 Amendment to the UIG Additional National Data Reporting​
XRN 5561 -Reform of Gas Demand Side Response (DSR) Arrangements (Modification 0822)
XRN 5379 - Class 1 Read Service Procurement Exercise - MOD 0710

## Slide 20
XRN5556.C - Contact Management Service (CMS) Rebuild – Version 1.2 – Detailed Design

## Slide 21: Contact Management Service (CMS) Rebuild
XRN5556.C - Contact Management Service (CMS) Rebuild – Version 1.2 – Detailed Design
Reason for Change:
There are two reasons to change the current bulk upload process. Firstly, the process to upload multiple CMS Contacts requires changes to resolve the current pain points causing high customer effort. Secondly, the re-engineering of the Contact business processes has created leaner business processes, resulting in two key differences:
Less information is needed to raise some contacts (due to process streamlining)
More processes can be raised via file upload (for example ISO)
Proposed Changes:
1. New File Type To Upload Multiple CMS Contacts to the new version of CMS
We propose that a new file is used to upload multiple contacts into the new version of CMS. This will also be similar to the current method in that it is a CSV file, with the ability to upload via the new CMS user interface or the IX with two differences:
New extension “.BCL” (Bulk Contact Logging), instead of “.QMP”, this will help reduce any potential confusion during dual running.
Different fields within the file, due to process streamlining and inclusion of more contact types (such as ISO, DTL), see attached fields
2. Tracking Contacts Submitted by File
We propose bulk Contact upload files are tracked within the new version of CMS. The new version of CMS will provide multiple tracking and search options, including File and CRN Search, File Tracking, Advanced Search and Dashboards (in future releases). Additionally, the new version of CMS will provide File Alert notifications. This means that files uploaded via IX will no longer get response files (QMR or QMJ), and instead use the new version of CMS to track the file response. Also, Contacts will be tracked within the new version of CMS, rather than creating QCL and QEX reports.

## Slide 22: Contact Management Service (CMS) Rebuild
Proposed
For full details please see change pack XRN5556.C - Contact Management Service (CMS) Rebuild – Version 1.2 – Detailed Design
XRN5556.C - Contact Management Service (CMS) Rebuild – Version 1.2 – Detailed Design
Current

## Slide 23: Contact Management Service (CMS) Rebuild
XRN5556.B - CMS Rebuild - v1.1 - Revised Detailed Design
The XRN5556.B Change pack is an update to the approved XRN556.B change pack, issued in September 2022. The original change description, which has been approved, remains unchanged. The proposed addition is to add the Set to Extinct (STE) contact type to CMS version 1.1, due to go live in December 2022.
Currently there is a manual process for Shippers, Disruption Network (DN) or Independent Gas Transporter (IGTs) organisations to request to change the status of a Meter Point Reference Number (MPRN) to extinct. The current process requires the Shipper, DN or IGT to email STE requests, which are then validated manually by a Central Data Service Provider (CDSP) agent and if they are found valid the meter point status is changed to extinct.
We propose to add this Contact Type to the new version of CMS to resolve pain points identified within the current process, including:
Customer Effort - Currently raising STE contacts is a lengthy manual process, which requires a lot of effort to confirm if a contact has been accepted and check the progress of a STE contact.
Cycle Time – Currently there can be delays in updating the status of an MPRN to extinct.
For the Set to Extinct business process and further detail please see Change Pack XRN5556.B - Contact Management Service (CMS) Rebuild – v1.1 - Revised Detailed Design.

## Slide 24: Contact Management Service (CMS) Rebuild
Contact Management Service (CMS) Rebuild – Query Management Standards of Service (SoS) Reporting
Currently there are two different views produced for the performance of Query Management:
Query Management (QM) Standard of Service (SoS) Reporting
Data Services Contract (DSC)+ Performance Indicators
The DSC+ Performance Indicators (PI’s) have superseded the Query Management SoS Reporting, and are now the primary, and more effective, method for analyzing and managing performance of the Query Management service.
Currently reporting of QM SoS is generated monthly, using data from the existing Contact Management Service (CMS) system, and are then manually emailed out to Shippers, however with rebuild of CMS additional work will be needed to create and distribute these legacy reports. The effort required to create QM SoS and associated reports may not deliver any business value, and instead take time which could be spent delivering valuable product features, such as customer dashboard reporting.
Information Required:
We would like to find out if the SoS QM reporting is being used by Shippers and Distribution Networks.
For more detail see the Contact Management Service (CMS) Rebuild – Query Management Standards of Service (SoS) Reporting Change Pack.

## Slide 25
XRN 5541 - Amendment to the UIG Additional National Data Reporting

## Slide 26: XRN5541- Overview Amendment to the UIG Additional National Data Reporting
Currently the UIG Additional National Data report does not provide a breakdown of energy by EUC Sub Band, which were introduced as part of Modification UNC 0644 and delivered under XRN4665 ‘Creation of New End User Categories’. The absence of this breakdown means that customers are not able to validate UIG allocations as effectively as is required, due to the aggregate nature at which the data is currently presented.
This change seeks to amend the existing version of the UIG Additional National Data report, to provide the requested aggregate energy values for each of the four respective End User Category Sub-Bands, as detailed below:
  Non-Prepayment/Domestic
  Prepayment/Domestic
  Non-Prepayment I&C
  Prepayment I&C
For clarity, the End User Category Sub-Bands are applicable to EUC01 and EUC02 only.

## Slide 27: XRN5541 - continued
New Tab All Energy by Class Breakdown
As additional tab/sheet will be added to both versions of the existing report, weekly and monthly. This tab will include 32 columns, 8 per Class, and this will ensure the format of the tab is consistent within each iteration.

## Slide 28: XRN5541 – continued
Implementation and Funding
Our aim is to deliver this change as soon as ready, post approval, and it will be present in both weekly and monthly iterations of the report from that point forwards. No further communication will be issued regards implementation however a closure document will be issued to Change Management post implementation.
Due to the size and nature of the proposed change, no additional funding is to be sought in order to complete the required work.

## Slide 29: XRN5561 – Reform of Gas Demand Side Response (DSR) Arrangements (Urgent Modification 0822)

## Slide 30: Background
Modification 0822 – Reform of Gas Demand Side Response Arrangements was raised to include provisions within the UNC for National Grid NTS to:
  Administer an invitation to offer process for Gas Demand Side Response (DSR),
  Introduce option payments to Users that arrange with consumers to provide DSR in advance of winter, and
  Extend the trigger for opening the DSR market from the issue of a Gas Balancing Notification to also include issue of a Margins Notice at the day ahead stage.
Modification 0822 has now been approved by Ofgem and has been implemented with effect from 17 October 2022.

## Slide 31: Key Impacts – Option Payments
XRN5561 has been raised to support the delivery of Urgent Modification 0822 – Reform of Gas Demand Side Response Arrangements and specifically introduce “Option” payment and penalty charges issued by the CDSP.
Option payments:
  NGG will provide the CDSP with a breakdown confirming the Shippers and Invoice values to be paid each month once the Invitation to Offer assessment has been completed.
  The CDSP will issue the Option Payment credit via the Request to Bill (RTB) process.
  This payment will be issued on the .INR (Generic Request to Bill Invoice) and the .INV file format utilising existing Charge Type ‘DSP – DSR COMPENSATION PAYMENT’.
  The Invoice will be issued on M+23 with the payment due date on D+12. Please note this aligns with the Energy Balancing Invoice (BAL).

## Slide 32: Key Impacts – Option Payments
Penalty charges:
  NGG will provide a breakdown to the CDSP confirming the Shippers and Penalty Charges to be invoiced as a result of Urgent Modification 0822.
  As per the Modification, Penalty Charges will be 110% of the Option Payment. However, this will be reduced proportionately based on the number of DSR Market Offers that were accurately posted during that Winter Period.
  The CDSP will issue the Penalty Charge payment via the Request to Bill (RTB) process.
  This Penalty Charge will be issued on the .INR (Generic Request to Bill Invoice) and the .INV file format utilising existing Charge Type ‘B96 – ADJUSTMENT TO DSR COMPENSATION PAYMENT CR DR’
  Where a Penalty Charge applies, as per the Modification 0822 business rules, this is expected to be charged after the relevant Winter Period. It is anticipated that this will be included within the May invoice and will be based on the current month’s throughput.
  The Invoice will be issued on M+23 with the payment due date on D+12. Please note this aligns with the Energy Balancing Invoice (BAL).

## Slide 33: Key Information
Urgent Modification 0822 has been approved by Ofgem and implemented on 17 October 2022.
3098.6 – RT – PO – XRN5561 – Urgent Modification 0822 – Detailed Design For Awareness has been issued within the October Change Pack.
This Change Pack is for awareness only as the Urgent Modification has been approved and implemented.

## Slide 34: XRN5379 – Class 1 Read Service Procurement Exercise (Modification 0710)

## Slide 35: XRN5379- Overview MOD0710S – Class 1 Read Service Procurement Exercise
Background
Modification 0710S and IGT Modification IGT148, were raised to obligate the CDSP to take on Class 1 Read Service provision on behalf of Shippers. This was to transfer the obligation to provide the Class 1 Supply Meter Point Read Service from the Transporters to the CDSP.
XRN5379 seeks to ensure:
The CDSP appoints a Service Provider on behalf of Shippers, to provide the Class 1 Daily Read Service from 01 April 2023 onwards, following the expiry of existing contracts in place for the service between the DNOs and the DMSPs on 31 March 2023.
Invoicing changes are delivered to cease charging Shippers for the Class 1 Read Service on behalf of Transporters (via IX) and commence charging Shippers directly by the CDSP (specific service).
The introduction of additional CDSP operational support for the Class 1 read service.

## Slide 36: XRN5379 – Key Impacts
Contractual arrangements
We do not anticipate material changes to the core Class 1 read service as a result of this change, however, the party responsible for contracting with the Service Provider will be different.
Class 1 Reads Charging Structure
As detailed within Modification 0710 (and IGT148), these Daily Metered (DM) asset and DM read charges will be removed from each DNOs Transporter Metering Charging statements.
Following the implementation of this XRN, going forwards, the charges for all the Class 1 read services will be published within the CDSP DSC Annual Charging Statement.
These charges will be shared in due course once all procurement activities have been completed.

## Slide 37: XRN5379 - Impacts
Invoicing for the Class 1 read service
Post-implementation of XRN5379, Shippers will no longer be charged for Class 1 read service through a UK Link invoice via the IX in an .INV Generic Invoice file
Instead, DSC Customers who utilise the Class 1 read services will be charged via the DSC Specific Services Invoice.
Invoicing through this mechanism will utilise the existing process, terms and timescales, no changes are being made to these as part of this change except for the addition of new specific services.
New Supporting Information has been proposed for Class 1 read services which will be emailed to relevant Shippers on the same day as the DSC Specific Service Invoice being issued.

## Slide 38: XRN5379 - Impacts
Additional Class 1 read services
The following additional services will be available on request via the CDSP:
Within-day service – provision of hourly or half-hourly consumption data. This is sent via the Information Exchange (IX) via the .BBR file (Shipper), or via the .DMV file (DNOs).
Retrospective Within-day service (Shipper only) – retrospective read data up to 18 months prior to the request date.
Annual data service (DNOs only) – provision of an annual view of specific Class 1 data as set out within the UNC TPD Section B Clause 11 – Supply Point Offtake Rate Review Process (SPOR Report).

## Slide 39: XRN5379 - Impacts
Class 1 read service incentives
Post-implementation of XRN5379, DSC Customers will no longer be credited (on an ongoing basis) for the Class 1 read services through a UK Link invoice via the .INV Generic Invoice file.
Instead, DSC Customers who utilise the Class 1 read services will be charged via the DSC Specific Services Invoice.
Under the new contract DSC parties could receive incentive payments for the following services:
  Class 1 DM read service incentive (existing)
  Within-day service incentive (new)
  Failed site visit incentive (new)
  Daily Read Equipment (DRE) installation incentive (new)
As incentive logic will not be detailed in UNC following Modification 0710 implementation, a [DSC Class 1 Supporting Document] will be created to detail key information relevant to parties utilising the service (including incentives).

## Slide 40: XRN5379 – Transitional Arrangements
The new approach for invoicing for charging for the service and crediting incentives will not commence until a full month of the service under the new contract has occurred. The first time the new charges will be issued via the DSC Specific Service Invoice will be May 2023.
  As a result, the last invoices issued under the current service (March 2023), for Reads, Assets and Within-day services via the existing UK Link Invoices will be in April 2023, and for liabilities, May 2023
  Charge Types that are no longer used moving forward post-implementation, will remain within the Xoserve_Comprehensive_Invoices_Charge_Types document as a minimum throughout the transitional period
To ensure a successful transition with a continuous service, once the procurement exercise and required analysis is finalised, we will propose the transitional arrangements following engagement with relevant parties.
.

## Slide 41: Key Information
3098.7 – RT – PO – XRN5379 – Class 1 Read Service Procurement Exercise – Mod0710 – Detailed Design has been issued within the October Change Pack.
This is out for industry Consultation until 31 October 2022.
Please review and provide a Consultation Response if you have any questions.

## Slide 42: 4. Release/Project Updates

## Slide 43: 4. Release/Project Updates
4a. FWACV
4b. February 23 Major Release

## Slide 44: 4a. FWACV Progress Update

## Slide 45: XRN5231 Flow Weighted Average CV
October 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is now tracking as GREEN. All implementation activities are complete. PIS activity is progressing to plan. 1st Usage monitoring and assurance taking place. Requirements traceability activities have completed. No major issues have been reported and the service is largely working as expected since 1st Sept. A number of PIS tickets have been raised; 10 key PIS activities are now closed and work is in progress for the remaining 5 issues. The resolution activities for these issues will conclude within the PIS phase. Regular calls are taking place with the DNs as appropriate, NG and key stakeholders. These will continue for the remainder of PIS. Next Steps: Conclude PIS phase. Commence Closedown activity | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | There are currently no key issues or risks. | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs are within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 46: 4b. February 23 Major Release

## Slide 47: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, Start up and Initiation phase completed on 23/09 as per plan Currently in build phase, with system testing in progress for XRNs where build completed from 03/10 Progress update: UK Link build in progress, delivery on track to complete by 30/09 DDP build for XRN4990 commenced on 12/09, delivery on track to complete by 23/12 System Testing preparation in progress, test case execution to commence 03/10 User Acceptance Testing (UAT) preparation to commence on 17/10 Decision in October ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update - SGN confirmed that Ofgem are due to provide an update on the status of the Modification w/c 26/09/22, which ultimately could result in this change being descoped from Feb-23 release. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 27th September 2023
Complete
On Track
At Risk
Overdue

## Slide 48: 5. Change Pipeline

## Slide 49: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 – Major Release
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992, XRN5298
July 22
February 23
June 23 – Major Release
XRN5091, XRN5186, XRN5482
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
XRN5472
XRN5143
No Major Release
XRN5379
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 30th September 2022
XRN5565
XRN5529
XRN5561

## Slide 50: Change Pipeline Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | Standalone | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | Standalone | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | Standalone | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | Standalone | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | Standalone | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | October 22 | Standalone | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Indicative
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm

## Slide 51: Change Pipeline April 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 23 | Standalone | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | N/A | 1st April 23 | Standalone | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | 1st April 23 | Standalone | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 | Major | Indicative

## Slide 52: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | Mod0651 – Retrospective Data Update Provisions | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5286 | Clarification Change to the AQ amendment process to be applied retrospectively (MO0746) | CDSP | Shipper DN | Shipper | Tbc | Tbc | Tbc | N/A
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A

## Slide 53
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5532 | Hydrogen Town Trial | WWU | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | DN IGT NGT Shipper | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued

## Slide 54: 6. AOB

## Slide 55: Annex – For Information

## Slide 56: 7. DSC Change Management Committee Update
ChMC 12.10.22 Meeting

## Slide 57: Change Management Committee Update –12.10.22 ChMC Meeting

## Slide 58
8. DSG Defect Summary

## Slide 59: DSG
Defect Summary

## Slide 60: Defect Summary Stats

## Slide 61: Closed Defects between 1st Sept & 30th Sept 2022
Closed Defects |  |  | 
Defect ID (RTC) | Deployed / Closed on: | Description | Amendment Invoice Impacting
67828 | 09/9/22 | ( Priority high) : For a class 3 mod 700 site, the oldest read in a batch file is getting processed instead of the latest one. | No
67281 | 27/9/22 | (Priority Medium) Nov 21 - BAU071 / When a cyclic read with reason 'N' is loaded within D to D+5 of the transfer date through UMR process, the read type is blank | No
67273 | 09/9/22 | (Priority Medium) When cyclic read is loaded within transfer window for a Meter-Corrector site, uncorrected read is blank and meter read is incorrect for estimated transfer read | No
67220 | 09/9/22 | (Priority Low) Replacement read of OPNX got stuck in pending status in UBR staging table ,ideally it should get rejected. | No
66894 | 9/09/22 | ( Priority Medium) Proactive / UK Link / Metering / Actual read uploaded through DLC/UDR process with a non-zero TTZ does not consider TTZ to derive better-estimated reads | No

## Slide 62: Closed Defects between 1st Sept & 30th Sept 2022
Closed Defects |  |  | 
Defect ID (RTC) | Deployed / Closed on: | Description | Amendment Invoice Impacting
66584 | 09/9/22 | (Priority Medium) MR15 exceptions are created incorrectly when class change estimated reads (loaded during class change from 3 to 4) are replaced, while the next read is already present in class 4 period | Yes
66429 | 09/9/22 | (Priority Medium) SAP- For class 4 sites two variances are getting generated on the end of the month after rec | Yes
66428 | 09/9/22 | (Priority High) Incorrect previous volume populated in UBR table when Replacement read is loaded on D+10 (Shipper transfer date) where Class change occurs from 4 to 3 on D date | Yes
66070 | 28/09/22 | (Priority Medium ) UKLINK/SPA/SLSP site confirmed to class 4 within contract period | No
65738 | 30/09/22 | (Priority Low) SAP:RGMA : Role code missing while RGMA exchange | No
65322 | 09/9/22 | (Priority High) Ratchet Process - PRN files are getting triggered to incorrect shipper for class 1 & 2 sites | No

## Slide 63: Amendment Invoice Impacting Defects - Open
Open Amendment Invoice Impacting Defects |  |  | 
Defect ID | Status | Primary Business Process | Description
66624 | UAT Assurance | READS - Reconciliation Process | (Priority Medium) When Shipper transfer is performed for a Prime site on D date and read is submitted by the outgoing shipper on D-1 day, the read is incorrectly loaded as an ACTIVE read
66623 | DRS completed | READS - Read upload (NDM) | (Priority Medium)In Class 4 Prime-sub sites, When Shipper transfer is performed for sub site on D date followed by loading an actual read through read submission(RD1) file ,within transfer window(D to D+5), the transfer read estimation is not getting triggered
66428 | Fix Deployed - Pending Data Correction | READS - Reconciliation Process | (Priority High) Incorrect previous volume populated in UBR table when Replacement read is loaded on D+10 (Shipper transfer date) where Class change occurs from 4 to 3 on D date
66429 | Fix Deployed - Pending Data Correction | READS - Reconciliation Process | (Priority Medium) SAP- For class 4 sites two variances are getting generated on the end of the month after rec
67938 | UAT Execution | READS - Read upload (NDM) | ( Priority High) Incorrect volume/energy is calculated for actual read loaded after estimated transfer read due to the last actual read on the site being an inserted actual read
68059 | DRS Completed | READS - Read upload (NDM) | ( Priority Medium ) Auto-resolution of LD01 exception fails for prime sites when Shipper transfer occurs on D date and LDZ change occurs on D-1 date

## Slide 64: Amendment Invoice Impacting Defects - Open
Open Amendment Invoice Impacting Defects |  |  | 
Defect ID | Status | Primary Business Process | Description
68376 | DRS In Progress | RGMA - READS - Read upload (NDM) | ( Priority High) UKLP: SAP: RGMA: Volume and energy populated incorrect for RGMA final read
68374 | DRS In Progress | READS - Read upload (NDM) | (Priority Medium)In Class 4 Prime-sub sites, When Shipper transfer is performed for sub site on D date followed by loading an actual read through read submission(RD1) file ,within transfer window(D to D+5), the transfer read estimation is not getting triggered
68370 | DRS In Progress | READS - Read upload (NDM) | ( Priority - High) CSSC defect 68141 - LD01 resolution process does not work when switch involves class change from 4 to 3
68344 | Ready for Internal Testing | READS - Read upload (NDM) | ( Priority High) REC flag is immediately updated after uploading a Replacement read on class 3 start date (class change from class 2 to class 3)
67274 | Ready for Internal Testing | READS - Consumption adjustment | ( Priority Low) In class 4 site CA is not getting applied from CMS end for one day and In class 2 site CA is not getting applied where adjustment end date is Shipper end date.

## Slide 65: Amendment Invoice Impacting Defects - Open
Open Amendment Invoice Impacting Defects |  |  | 
Defect ID | Status | Primary Business Process | Description
68343 | DRS Completed | RGMA - READS - Read upload (NDM) | (Priority - High) Effective TTZ is not getting calculated correctly for NDM prime sites as per XRN5072 logic.
68340 | DRS Completed | READS - Read upload (NDM) | (Priority - High) Incorrect volume/energy is populated for FINX read loaded after estimated transfer reads due to the last actual read being an inserted/replaced actual read
68266 | Ready for Internal Testing | READS - Read upload (NDM) | (Priority - High) \Duplicate site visit read is being accepted for same date in NDM sites causing the original site visit read with correct volume/energy to be set to inactive
68180 | DRS Completed | READS - Read upload (NDM) | ( Priority - High ) Incorrect volume calculation for class 3 sites between class change date and first cyclic read received post class change to class 3 for Meter-Corrector sites
68342 | DRS Completed | READS - Read upload (NDM) | (Priority High) Reads under EUC band are processed in incorrect manner for Class 3 prime sites
67319 | Ready for Internal Testing | RGMA - READS - Read upload (DM) | (Priority High) When a Site Visit read is inserted between 2 actual reads in DM sites, the Site Visit read insert is not populating next read date in SFN table
64731 | UAT Assurance | RGMA - Asset Updates | (High Priority) SAP - RGMA: Transfer reads created incorrectly as non-opening read instead of opening & closing read. Rec and billing impact for Class 4 sites.
63690 | Fix In Progress | READS - Read upload (DM) | (Medium priority) - Issue with the Class change re-estimation; whenever the previous Class is either Class 3 or 4, and the Read is received in the Class 2 period, the Class change estimated Read on the Class 2 start date does not get updated

## Slide 66: 9. Portfolio Delivery

## Slide 67: 9. Portfolio Delivery Overview POAP
The POAP is available here.