## Issues
Customer Issue ID | Status | Incident No. | Incident Priority (P1 or P2) | Defect No. | CR Ref. | Issue Title | Customer Impact | Issue Description | Primary Process Impacted | Customer Segments Impacted | Cause | Date Detected | Planned Issue Resolution Date | Resolution RAG Status | Resolution RAG Justification Commentary | Closed Issue Date
1 | Open | N/A | N/A | N/A | Mod 0658 / XRN4695 | Levels & volatility of Unidentified Gas (UIG) | Unpredictable UIG gas nominations & gas allocations | Levels & volatilty with UIG between D-5 of the gas day to GFD+5 and beyond D+5 close-out in extended reconciliation periods which create the need for Shippers to account for UIG until eventually reconciled. | UIG | All Shippers | Various: Incorrect DM reads used to calculate energy, estimated DM reads to calculate energy, issues with data that feeds UIG (CVs, weather data). | 2017-06-01 | 2019-10-01 | Green | Task Force recommendations = 1 Implemented. Modification, 5 sponsored Modifications, 2 drafted Modifications published on Xoserve website.
2 | Open | N/A | N/A | Multiple | N/A | Amendment Invoice supporting information (AML & ASP files) | Incorrect reconciliation charges and unable to validate the invoice due to mismatches on the supporting information files Cash flow for Distribution Networks | A number of functional defects and integration issues are causing presentation and charge calculation issues within the AMS invoice. | Invoice - Amendment | Shippers & Networks | Various: system functionality, manual workarounds. Defects raised. | 2017-07-01 | 2019-12-01 | Amber | The number of customers with a mismatch reduced to 17 in July (June billing period) with a total mismatch of 65, this is the lowest amount of mismatches since go live in 2017. Customer Workshop continue each month Progress update published on website - https://www.xoserve.com/services/issue-management/amendment-invoice/ SLA updates to be reported at CoMC
3 | Closed |  | N/A |  |  | Network Reports - providing aggregate AQ, SOQ & CSEP portfolio information (BOPRI & SCH606) |  | The BOPRI & SCH606 reports are issued to DNs monthly (BOPRI on 28th & SCH606 on the 1st). There have been issues with both reports including the December report which DNs use to set their transportation rates for the 12 months commencing 1st April. BOPRI shows all 'rolling' AQs, SCH606 all CSEP SOQs. Updated reports issued on the 11th January however, due to the difference in the reports Networks were not confident with the reports issued in January. | Reporting | DN's |  | 2017-12-11 |  | Blue
4 | Open | 807068 | N/A | 846 1379 1269 1380 1326 1362 1437 1439 | N/A | Data issues relating to transfer of ownership process | Incorrect data submitted to Shippers on the transfer of ownership notification / response files. Defect 846 & 1269: Does not prevent transfer of ownership however offers may be cancelled where there has been an update to the SOQ due to the ratchet. Workaround in place. Data corrections are being carried out upon of receipt of files from Shippers Defect 1380 affects a very small number of supply Points. No workaround required as impact is minimal. EUC not used for Class 1 & 2 sites Defect 1326: Customers will receive incorrect SOQ charges, and therefore will also charge their customers incorrectly Defect 1439: Workaround in place until fix is deployed | 846: When the capacity amendment effective date is the same as the ratchet SOQ effective date, the offered SOQ and provisional new SOQ values reported in the Provisional Ratchet Notification File (PRN) are incorrect and should reflect the values prevailing on the Gas Flow Day of the ratchet. The new values reported in the Ratchet Notification File (RAT) and Ratchet SOQ Breach File (PMN) will also need to be corrected in the case where the capacity amendment is valid 1379: When going through the Shared Supply Meter Point (SSMP) process, the incorrect Supply Offtake Quantity (SOQ) value is being provided within the S15 record of the Transfer of Ownership (TRF) response file 1269: Class change from Daily Metered (DM) to Non Daily Metered (NDM); Offers are being incorrectly cancelled where the Ratchet SOQ is greater than the requested SOQ within the Offer 1380: For Greenfield class 1 and 2 sites, where there is an EUC change following a confirmation, the incorrect EUC valuesare being populated in the Transfer of Ownership file (TRF). The previous EUC is being populated as opposed to the new EUC details. 1326: Incorrect Gas Nomination ID values are being sent out in the M15 record (Confirmation Notification File). The values being sent out in the field are incorrect for both incoming and outgoing Shippers. The outgoing Shipper can continue to receive their Gemini ID up until the proposing Shippers confirmation reaches confirmed status (CO). The incoming Shipper should have a blank Gemini ID whilst their confirmation is at request status (RQ). Once the Confirmation has changed to confirmed status, the incoming Shipper should only receive their relevant Gemini Meter ID and the outgoing Shipper should receive a blank Gemini ID. 1362: Where a Shipper submits Confirmation File (.CNF) or Customer Amendment File (.CNC) for a site including Priority Service Register Code 17 (unable to speak English), the file is incorrectly accepting, when the S83 record (End Consumer) is not accompanied with the S84 record (priority services) 1437: Confirmation of class 1 sites are being incorrectly accepted when the revised offer is below the class 1 threshold of 58.6 million 1439: Upon receipt of an address amendment which results in an LDZ / Gas Transporter update, the system is failing to complete the shipper transfer on the move in date | Registration Process | Shippers & Networks | TBC | 2018-01-05 | TBC | Amber | Defect 846: Deployment date TBC Defect 1379: Deployment date TBC Defect 1269: Deployed 7th June 2019 Defect 1380: : Deployed 28th May 2019 Defect 1326: Deployed 17th May 2019 Defect 1362: Deployed 10th May 2019 Defect 1437: Deployment date is 4th October 2019 Defect 1439: Deployment date TBC
5 | Closed | 950723 | P2 | N/A | N/A | Daily Read file (.MDR) not issued before 14:00 hrs. |  | Delay in submitting the daily reads file to Shippers (.MDR) file for Class 1 meter points. | Read process | All Shippers | Issue caused due to defect deployment performed affecting daily reads process. | 2018-01-19 |  | Blue |  | 2018-01-19
6 | Closed |  | N/A |  |  | Missing Read files where the meter exchange takes place on same date as transfer date |  | Transfer read files are not issued to the Shipper where there has been a meter exchange on the same day as a shipper transfer | Read process | All Shippers |  | 2018-02-12 |  | Blue
7 | Closed | N/A | N/A | N/A |  | The number of Must Reads has increased significantly |  | - DNs raised the issue that the value on the invoices that we produce on their behalf to the Shippers has reduced since Nexus. At the same time, the invoices from the MRAs for procuring reads on their behalf has not reduced. - Analysis identified that the technical elements of the process are working correctly. However, there are reasons for the reduced value of the invoice (not all reasons affect all DNs) | Read process | DN's |  | 2018-03-01 |  | Blue
8 | Closed |  | N/A | 945 | N/A | Incorrect functionality of a Meter Read validation routine affecting circa 3,000 meter reads |  | An issue was identified in March following a number of exceptions raised from UK Link. A validation routine in UK Link was creating exceptions in certain scenarios when processing the meter read. It was found that the validation job was incorrect. On the 9th March 2018 the validation was stopped. Analysis has identified that 3,652 MPRNs have been affected. | Read process | All Shippers |  | 2018-03-20 |  | Blue
9 | Closed |  | N/A | N/A | XRN4671 | Energy for Class 2 sites incorrect in Gemini where a read replacement is received or a consumption adjustment within GFD+5. |  | Energy mismatch in Gemini where a read is replaced with a read or a consumption adjustment for Class 2 sites as the energy calculated is not being sent to Gemini correctly. | Read process | All Shippers |  | 2018-04-01 |  | Blue
10 | Closed | 843169 (Problem ID 1636) | P2 | N/A | N/A | Issues with the Allocation run in Gemini affecting UIG |  | Issue encountered with the first run of Energy Allocation for Gas Day 2nd & 6th May 2018. NDM Allocation failed to calculate for this gas day, for all LDZs, This was corrected within the day. | Gas Allocation processes | All Shippers | The cause of this issue is due to a code fault | 2018-05-03 |  | Blue |  | 2018-05-03
11 | Closed |  | N/A | 969 | N/A | Incorrect AQ/SOQ values issued in transfer of ownership files |  | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including AQ and SOQ values. Due to a code change for a defect deployed on September 27th 2017, incorrect Rolling SOQ data has been sent for all Class 3 and 4 sites transferring ownership, equating to 1.75 million Meter Points with incorrect SMP rolling SOQ values. The rolling SOQ being issued is the value as at EUC effective date (either 1st October or 1st of the month if a rolling AQ change has taken place).The transportation rates sent in the same file are correct. | AQ process | All Shippers |  | 2018-05-15 |  | Blue
12 | Closed | 848559 | P2 | N/A | N/A | Gas Nominations batch job failure affecting UIG |  | Unidentified Gas nominations batch job failure within Gemini at approximately 11:00 on 17th May. Issue repeated on 21st May. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | Gas Nomination processes | All Shippers |  | 2018-05-17 |  | Blue |  | 2018-05-17
13 | Closed | 858471 979484 | N/A | 1313 1050 | N/A | Incorrect charges relating to Capacity |  | 1. Duplicate adjustments in UK Link are not crediting back all charge types to the Shipper correctly. In certain scenarios, Shippers are receiving multiple refunds for Capacity Charges only 3. In a number of instances, where there has been a ratchet SOQ charge applied, they have either been incorrectly billed or have missing bill documents | Invoice - Capacity | Shippers & Networks | TBC | 2018-06-01 | April 2019 | Blue | Defect 1050 deployed on 05/04/2019 Issue closed as Defect 1313 is now being monitored under the AML Taskforce. Please refer to https://www.xoserve.com/services/issue-management/amendment-invoice/ for updates | 2019-04-05
14 | Closed | 843903 | P2 | N/A | N/A | Workflow did not complete in SAP potentially resulting in incorrect data held in UKLink & Gemini |  | Workflow did not complete for 4,000 meter points resulting in potential incorrect data being held in UKLink & SAP affecting gas nominations, allocations, DEs & invoicing. May also impact read estimation & read processing. | Gas Nomination processes | All Shippers | Fix deployed at the weekend affected the process. | 2018-06-04 |  | Blue |  | 2018-06-04
15 | Closed |  | P2 |  |  | Incorrect file loaded into Gemini affecting Allocations in Gemini & UIG |  | Issued experienced on 5th & 6th June due to incorrect file loaded for 5th June, delay with processing the file caused issues with allocation run on the 6th June. This was corrected within the day. Delayed publication of the UIG data for the 5th of June has meant that customers would have seen their UIG screens showing a blank value until the UIG job (as part of the Allocation Suite) had completed. | Gas Nomination & Allocation processes | All Shippers | This was due to a system issue by Aggregator systems experiencing a technical issue when transferring the file between systems. | 2018-06-05 |  | Blue |  | 2018-06-05
16 | Closed | 856558 (Problem ID 1708) | P2 | N/A | N/A | Incorrect demand forecast received affecting Gas Nominations & UIG |  | Separate issue affecting UIG for Gas Nominations on 8th June due to incorrect demand forecast received. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | Gas Nomination processes | All Shippers | June issue caused by an incorrect demand forecast had been sent to Gemini . | 2018-06-08 |  | Blue |  | 2018-06-08
17 | Closed | 856162 (Problem ID 1713) | P2 | N/A | N/A | Issues with the Allocation run in Gemini affecting UIG |  | Issue identified on the 15th June. The UIG values are very high for LDZs NW, NO, WM for Gas Day 13/06/2018 | Gas Allocation processes | All Shippers | This is due to low Daily Metered (DM) values being used as part of the UIG calculation within the allocation suite job. | 2018-06-15 |  | Blue |  | 2018-06-15
19 | Closed |  | N/A | 1022 |  | Read issued in the Transfer of Ownership files (TRF) |  | At transfer of ownership the TRF file is issued on D-2 of the Confirmation effective date confirming the effective date of the Confirmation. The MRI file is also issued which contains asset information. The ‘Last Actual Read’ recorded on UKLink is submitted in both the TRF file (S15) and the MRI file however the read in the MRI is not the correct read. Defect 1022 raised. This has been since 01/06/2017. | SPA - Transfer of Ownership | All Shippers |  | 2018-06-28 |  | Blue
20 | Closed | 865213 | P2 | N/A | N/A | Line Pack not published |  | A Control Room User raised a ticket as Line Pack had not been published for 00:00 hour bar. | Gemini processes | GTs | Gemini Application Support began investigating and found that Gemini had received two Line Pack files at 23:00; this meant that the 23:00 hour bar loaded successfully with the first file but the second file got stuck in processing. The batch job was triggered and the 00:00 hour bar Line Pack file was published successfully. | 2018-07-02 |  | Blue |  | 2018-07-02
21 | Closed |  | P2 | N/A | N/A | Data Enquiry Service is at D-2 |  | There has been a delay in completing the daily data load for the Data Enquiry Service (DES). As a result the system is displaying data for 2nd July 2018 but data for 3rd July 2018 is not visible. The data for 3rd July 2018 is currently being loaded which means users may be experiencing slow performance on some of the screens | Data Enquiry | All Shippers | Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2018-07-04 |  | Blue |  | 2018-07-04
22 | Closed |  | P2 | N/A | N/A | Technical issue with Data Search telephone service |  | technical issue with our Data Search telephone service, 0121 713 4901 and Contact Management Helpline, 0121 713 4903 | Helpline | All Customers |  | 2018-07-12 |  | Blue |  | 2018-07-12
23 | Closed |  | N/A |  |  | DPS file sequencing |  | DPS files issued to Shippers have not followed the sequence of the last release (e.g. .PN002332.DPS’ to .PN002354.DPS’ ) | SPA - files | All Shippers |  | 2018-07-12 |  | Blue
24 | Closed | 873558 | P2 | N/A | N/A | UIG not visible in Gemini |  | Shippers and GNCC are unable to view the UIG Nominations balance for 15th and 16th Gas day & UIG allocations for 14th | UIG | All Shippers | A column in one of the table has size 8 digits which is causing the UIG job failures. Database have restructured the table column size from 8 to 10 in the production environment | 2018-07-16 |  | Blue |  | 2018-07-16
25 | Closed | 874837 | P2 | N/A | N/A | UIG mismatch in Gemini |  | Mismatch due to the UIG allocation job took time to complete for the gas day (11th ,12th,13th,14th,15th) which delayed the process. | UIG | All Shippers | Job overrun due to defect 873558 | 2018-07-20 |  | Blue |  | 2018-07-20
26 | Closed |  | N/A |  |  | DM Reports |  | DM reports issued to Shippers were incorrect for 30/06/2018 to 06/07/2018 | Reporting | All Shippers |  | 2018-07-20 |  | Blue
27 | Closed |  | N/A | 999 |  | Incorrect FYAQ values issued in transfer of ownership files (TRF). |  | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including FYAQ and FYSOQ values. Incorrect FYSOQ data has been sent for all Class 3 and 4 sites transferring ownership, | SPA - Transfer of Ownership | All Shippers |  | 2018-07-25 |  | Blue
28 | Closed |  | N/A |  |  | UIG Rec Invoice includes kWh for SSP pre go live |  | The kWh presented in the supporting information is not as expected as it includes the kWh associated to SSP reconciliation pre go-live (which has no financial value). However this does not impact the invoice value as the smear is based on the monetary value (GRE) and we do not re-value the reconciliation using SAP and kWh. | Invoice - Amendment | All Shippers |  | 2018-07-27 |  | Blue
29 | Closed | N/A | N/A | N/A |  | Delay is publishing the Performance Assurance Report Register (PARR) reporting |  | The publication of the Performance Assurance Report Register (PARR) reporting for August 2018 will be delayed and will not be published on Monday 30 July 2018 as expected. | Reporting | All Shippers |  | 2018-07-27 |  | Blue
30 | Closed | 884278 | P2 | N/A | N/A | Gemini-Demand Attribution not published for 10th hour bar |  | P2 raised at 10:30. Shippers unable to place gas nominations. | Gas Nomination processes | All Shippers | Scheduling team have identified that the demand attribution jobs were on hold | 2018-07-29 |  | Blue |  | 2018-07-29
31 | Closed | 886370 | P2 | N/A | N/A | IX - Unable to connect to multiple shipper sites |  | AML file delivery to 3 shippers impacted. | IX | All Shippers | IX team have updated that the connectivity issue is due to huge file transfer (400MB files); | 2018-08-05 |  | Blue |  | 2018-08-05
32 | Closed | 888227 | P2 | N/A | N/A | UIG Allocations |  | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 8th). This has affected the following: The UIG allocation values for Gas Days 3rd to 6th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 7th August were not calculated and appear as zero for all LDZs for all Shippers | UIG | All Shippers | This was due to the allocation suite overrunning on 8th August hitting the maintenance window. | 2018-08-09 |  | Blue |  | 2018-08-09
33 | Closed | 888227 | P2 | N/A | N/A | UIG Allocations |  | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 9th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 8th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | UIG | All Shippers | This was due to the allocation suite overrunning on 9th August hitting the maintenance window. | 2018-08-10 |  | Blue |  | 2018-08-10
34 | Closed | 888227 | P2 | N/A | N/A | UIG Allocations |  | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 12th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 11th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | UIG | All Shippers | This was due to the allocation suite overrunning on 11th August hitting the maintenance window. | 2018-08-13 |  | Blue |  | 2018-08-13
35 | Closed | 971341 | N/A | 1107 | N/A | MUR response not sent for Prime sites |  | For Prime sites (Class 2 & 3) Must Read responses are not being sent to Shippers in CMS | CMS | Shippers & Networks | TBC | 2018-08-24 | 2019-04-05 | Blue | Defect deployed on 05/04/2019 | 2019-04-05
36 | Closed | 893054 | P2 | N/A | N/A | Amendment Invoice |  | The UGR charge in the Amendment Invoice is incorrect. The total national Unidentified Gas reconciliation value is correct, but the allocation to individual Shippers is incorrect. | Invoice - Amendment | All Shippers | Manual error in the brought forward Shipper throughput values for market shares of UIG reconciliation allocation from the previous month | 2018-08-24 |  | Blue |  | 2018-08-24
37 | Open | 983387 | N/A | 1267 1122 1199 1305 1340 1341 1377 1411 1414 1415 1424 | XRN4676 | Incorrect AQ and / or Formula Year AQ (FYAQ) calculated | AQ's calculated incorrectly due to various data issues relating to specific scenarios. Where FYAQ is affected this will impact transportation rates applied. Impacts gas nominations, gas allocations & UIG in Gemini. XRN4676 & defects 1122, 1341 & 1377 are also Amendment invoice impacting. | 1267: Formula Year AQ not calculated correctly for greenfield sites where its changed from Daily Metered (DM) to Non Daily Metered (NDM) where the request was received in December with the D-2 date falling in December for confirmations due in January of the following year. 1122: Where there is multiple RGMA reads (Final Exchange and Report read) present in the system for the same day, the consumption being calculated is incorrect - affecting AQ & Reconciliation. XRN4676: Where a cyclic read is present for the same day as an final (FINT) read (outgoing shipper transfer read) the system is currently applying an incorrect/duplicate energy and creates reconciliation charges against the one day reconciliation between cyclic and Final read. Affects the AQ calculated. 1199: Volume and energy calculated wrong where Read insert between actual and estimated shipper transfer with TTZ of 1 (inserted using manual read screen). Affects AQ calculated. 1305: The WAALP period in AQ calculation is being ignored for the period where Meter point is in DE status resulting in incorrect AQ as the consumption during this period is being ignored. 1340: The monthly AQ Roll process is not calculating the AQ for the Local Distribution Zone (LDZ) and NTS telemetered sites where these sites have been flagged incorrectly as Twin Stream as part of migration. 1341: When replacing a class change read (from a class 4 to a class 3) the consumption is being incorrectly calculated for the class 4 period. 1377: Rolling AQ is being calculated incorrectly where correct reads are present in the system, however energy is showing as negative when they should be shown as positive 1411: The AQ is being incorrectly calculated for Class 1 MPRNs where an asset exchange has taken place. 1414: Where there is a class change from class 1 to class 2, energy is being incorrectly calculated based on the class change start date 1415: When an Xoserve user manually processes an actual read, the energy is being incorrectly calculated as zero. 1424: Following an update to a meter (non-physical) the volume which is calculated is based on the opening exchange read (OPNX) as opposed to calculating from the final exchange read (FINX) | AQ - Incorrect value | Shippers & Networks | Various | 2018-09-01 | 2019-12-01 | Red | Defect 1267: Deployed 29th March 2019 Defect 1340: Deployed 23rd April 2019 Defect 1122: Deployed 17th May 2019 XRN4676: Deployed 28th June 2019. Data correction still required. Defect 1199: Deployed 10th May 2019 Defect 1305: Deployed is 3rd May 2019 Defect 1341: Deployed 31st May 2019 Defect 1377: Deployed 12th August 2019 Defect 1411: Deployed 12th August 2019 Defect 1414: Deployment date is 10th December 2019 Defect 1415: Deployment date is 10th December 2019 Defect 1424: Deployment date is TBC Multiple closed defects have been identified as requiring data correction, this includes 1199, 720, 1146 (these were not originally classed as an AQ defect however incorrect consumption/energy affects future AQ calcs). Communication issued to customers on 30/08/2019 regarding defect 1146 and required actions in order for AQ's to be corrected and re-calculated with an effective date of 1st October 2019
38 | Closed | 896574 | P2 | N/A | N/A | IX file transfer service unavailable |  | Inbound and outbound file flow for Shippers impacted | IX | All Shippers |  | 2018-09-05 |  | Blue |  | 2018-09-05
39 | Closed |  | N/A |  |  | Estimated Transfer of Ownership Read Failure |  | Estimated Read not issued in MBR file following Transfer of Ownership . The two days affected were 15/06/2018 and 30/06/2018 and applied to 78 MPRN's (12 Shippers) | SPA - Transfer of Ownership | All Shippers |  | 2018-09-07 |  | Blue
40 | Closed |  | N/A | 1150 |  | Supplier details missing in the transfer of ownership (TRF) file |  | Issue with the Transfer of Ownership process where there is no asset on UK Link, the incoming Shipper has not received and will continue not to receive previous Supplier details in the TRF file (S75 file record). | SPA - Transfer of Ownership | All Shippers |  | 2018-09-07 |  | Blue
41 | Closed | 899761 | P2 | N/A | N/A | Gemini - Demand Attribution Failed for 16:00hrs |  | Demand did publish for 16:00 hrs. Latest NDM nomination and UIG nomination will not be visible on the screen, this will impact shipper's gas buying decision | Gas Nomination processes | All Shippers | Demand Attribution failed for 16:00 hrs. | 2018-09-14 |  | Blue |  | 2018-09-14
42 | Closed |  | N/A | 1162 |  | .UPI (User Pays Index) File not incrementing when new file is issued |  | The August User Pays Index (UPI) file was issued with the same file name as the July a file name, e.g. PN00000X5. | Files | All Shippers |  | 2018-10-01 |  | Blue
43 | Closed |  | N/A | N/A |  | Domestic M Number Helpline Incorrect Data |  | Since March the Domestic M Number Helpline service has not been providing accurate data in all cases | Helpline | All Customers |  | 2018-10-01 |  | Blue
44 | Closed |  | N/A | 1172 |  | Class 1 or 2 Sites populating Incorrect Run ID as SSP instead of LSP |  | Class 1 & 2 meter points are being assigned as 'SSP' instead of 'LSP' on the Amendment invoice supporting information files. | Invoice - Amendment | All Shippers |  | 2018-10-02 | 08/02/2019 | Blue
45 | Closed | 907330 | P2 | N/A | N/A | Data Enquiry Service currently unavailable |  | When trying to access the data enquiry portal, the system is timing out and not allowing users to access the portal | Data Enquiry | All Customers | Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2018-10-04 |  | Blue |  | 2018-10-04
46 | Closed | 911178 / 918851 | P2 | N/A | N/A | Delay in issuing some of the CFR files on 8th October |  | Small number of Confirmation response files not submitted to Shippers. 14 Shippers affected. | SPA - Transfer of Ownership | All Shippers | Files failed to process in AMT Marketflow. | 2018-10-08 |  | Blue |  | 2018-10-08
47 | Closed | 911345 | P2 | N/A | N/A | Delay in issuing some of the CFR files on Thursday 4th October |  | Incoming Shipper - For impacted Shippers, a response to their confirmation request was not sent within two Supply Point Systems business days. Outgoing Shipper - For impacted Shippers, withdrawal notifications and confirmation cancellation notifications were also delayed. | SPA - Transfer of Ownership | All Shippers |  | 2018-10-09 |  | Blue |  | 2018-10-09
48 | Closed | 911345 | P2 | N/A | N/A | Multiple confirmation responses in the Confirmation Response File (CFR) for the same confirmation request sent on 4th October. |  | Incoming Shipper - For impacted shippers, multiple confirmation reference numbers were issued for the same confirmation request. This means you have received two unique confirmation responses for the same transaction (meter point), one of which will be invalid. Outgoing Shipper - For impacted shippers, you have received two withdrawal notifications for your own confirmation. | SPA - Transfer of Ownership | All Shippers |  | 2018-10-09 |  | Blue |  | 2018-10-09
49 | Closed |  | N/A | 1179 |  | Class change from incumbent Shipper issue |  | Where a class change request is received from an incumbent shipper, there is currently no rejection which is causing AQ mismatch between UKLink and Gemini. Confirmed this is not an issue. | SPA - Class change | All Shippers |  | 2018-10-10 |  | Blue
50 | Closed |  | N/A | 1188 |  | Incorrect rejection for Interconnector request (RCI file) |  | Request to register on the Interconnector is rejecting incorrectly stating Contact Job Details not provided (CTT00012) even though the Contact Job Title has been provided in the file | SPA - Supply Point Updates | All Shippers |  | 2018-10-12 |  | Blue
51 | Closed |  | N/A | 1191 |  | Connection max AQ & SOQ incorrect in the Q44 record for iGT sites |  | Connection max AQ and SOQ values are incorrect in Q44 segment for the MPRNs that belong to CSEPs which are part of a nested configuration. This should have values for the parent CSEP, currently child CSEP AQ and SOQ values provided in this field. | AQ process | All Shippers |  | 2018-10-12 | 11/01/2019 | Blue
52 | Closed |  | N/A | 1190 |  | Formual Year SOQ not provided in TRF File |  | Formula year SOQ value not provided for the TRF flows where confirmation effective date is 02nd Oct 2018. | AQ process | Shippers & Networks |  | 2018-10-12 | 29/01/2019 | Blue
53 | Closed | 907423 | P2 | N/A | N/A | 43 files not processed in Marketflow, files stuck in Marketflow due to database issue, affected 15 Shippers. |  | 43 files submitted on the 4th October were not processed. Files affected: Supply Point update files, RGMA files and Class 3 & 4 read files. | SPA - multiple processes | All Shippers |  | 2018-10-22 |  | Blue |  | 2018-10-22
54 | Closed |  | N/A |  |  | UIG share & charges incorrect for since October 2017. |  | The UIG share & charges since October 2017 have been issued on the Amendment invoice incorrectly. This is due to the wrong UIG weighting factors being applied to two End User Category (EUC) bands. | UIG Adjustments | All Shippers | Incorrect weighting factors were uploaded into UKLink tables and seperately the UIG share was triggered before activities carried out by IS Ops were completed.; | 2018-10-26 |  | Blue | Original plan to deliver adjustments by 22/12/18. Final adjustments issued 02/04/19 | 2019-04-02
55 | Closed | 923446 | P2 | N/A | N/A | Two Confirmation files not processed. |  | Manual processing required to following a connectivity issue on 28th October. Two files were missed. | SPA - Transfer of Ownership | All Shippers | Manual error, 2 files were overlooked and not processed until Shipper raised a query. | 2018-10-28 |  | Blue |  | 2018-10-28
56 | Closed | 922156 | P2 | N/A | N/A | Gemini - Hourly capacity data is not published for IP auction |  | Gemini hourly capacity data not published for IP auctions from 23:00 on 28/10/28 to 04:00. on 29/10/18. | Gemini processes | GTs | An outage from 16:00 till 23:00 affected Gemini as files were not received. Team have restarted the auctions and Gemini received the hourly auction data for 04 hour bar at 23:32. | 2018-10-28 |  | Blue |  | 2018-10-28
57 | Closed | 922161 | P2 | N/A | N/A | EU nominations placed by the shippers will not be confirmed until we receive files from BBL and IUK TSOs |  | EU nominations placed by the shippers were confirmed late as we received the acknowledgement files late in Gemini. | Gemini processes | GTs | Gemini support team identified the files are stuck in system, service restarted to process the files. | 2018-10-29 |  | Blue |  | 2018-10-29
58 | Closed | 927554 | N/A | 1280 1236 | N/A | Issues relating to processing of daily metered reads and read notification files | For class 1 meter points, daily read information incorrect in the notification read files and Site Visit information recorded against the wrong meter for Twinstream sites. Low volume of MPRNs affected | 1280: Where a better estimate read is calculated and sent to Shippers/ DMSP, the read fields within the Daily Data Logger Readings (MDR) and DMSP Readings (DDR) file are being populated with incorrect data 1236: Where a DMSP inputs a site visit read for a Twin Stream Site via Portal, the read is being recorded against the incorrect Meter Serial Number than the one being selected | Read process | Shippers & Networks | TBC | 2018-11-15 | Jun-2019 | Blue | Defect 1280: Deployed on 10th May 2019 Defect 1236: Deployed on 21st June 2019. | 2019-06-21
59 | Open | 966533 | N/A | 1164 1205 1193 1319 1325 1398 1421 | N/A | Incorrect Formula Year SOQ & AQ values issued in notification or response files | Incorrect AQ/FYAQ values being issued in multiple notification files to Shippers and Networks. Defect 1325 affects a very small number of supply Points. | 1164: Issue where AQ & NDM SOQ are not getting updated correctly in UKLink and not populated in AQ notification (NRL) file where there is a Class change & AQ correction effective for the same day. Linked to defect 1205 1205:Formula year SOQ value is incorrect in the transfer (TRF) file when a Class change received through CNF and AQ correction goes live for the same effective date. Same issue has also occurred when Class change and EUC change happening on the same date. SOQ values in TRF / CFR and NMR files sent incorrectly 1193: Where a class change from 2 to 4 and effective date for 1st October 2018, EUC values are not being processed correctly where the NDM SOQ is derived Same issue has also occurred when Class change and EUC change happening on the same date. SOQ values in TRF / CFR and NMR files sent incorrectly 1319: Incorrect Formula Year AQ Value has been incorrectly populated in the .NRL file where an AQ correction has taken place between April 2018 - February 2019. 1325: The Monthly NRL file (AQ Notification file) is not being sent to shippers on the the NTS Interconnector notifying them of the change in AQ value as part of the Monthly AQ Roll process. 1398: Incorrect EUC details are being sent out in the NRL file for the WC correction when it is processed on M-2 where M is the effective date. 1421: When a shipper submits AQ Correction file (AQI) the read is incorrectly accepting as the system is not validating the read and read date to ensure it matches | AQ - Notification | Shippers & Networks | TBC | 2018-11-15 | TBC | Amber | Defect 1164: Deployed 29th March 2019 Defect 1205: Deployed 29th March 2019 Defect 1193: Deployed 29th March 2019 Defect 1319: Deployed 19th April 2019 Defect 1325: Deployed 28th June 2019 Defect 1398: Deployment date TBC Defect 1421: Deployment date is 6th September 2019
60 | Closed |  | N/A |  |  | Incorrect Read Reason (READ_REASON) sent on the read file (MBR) notifying of an estimated opening read |  | Following registration of a meter point by a Shipper, if an opening meter reading is not submitted by D+10 of the transfer effective date an estimated read is calculated and issued to both incoming & outgoing Shipper. The read issued to the Incoming Shipper gave 'Read Reason' as 'CYCL', it should be 'OPNT'. This has affected 51, 000 meter points between 24/11/18 and 27/11/18. | Read process | All Shippers |  | 2018-11-28 |  | Blue
61 | Closed | 963811 | N/A | 1241 | N/A | Incorrect values in Gemini | Incorrect SOQ value in Gemini for Class 1 meter points. No impact to energy or UIG. No workaround in place, however data correction to be completed once the defect is deployed. | The Current Year Maximum Supply Offtake Quantity (CYM SOQ) value is not being revised in Gemini when there is a change in the energy value | Gemini processes | Shippers & Networks | TBC | 2018-11-28 | 2019-06-01 | Blue | Defect 1241: Deployed on 28th June 2019 | 2019-06-28
62 | Closed | 936152 | P2 | N/A | N/A | Gemini - UIG Nomination Job Overrunning |  | There has been a delay in publishing the UIG nomination values in Gemini. The 10:00am UIG nomination process is still running. This has caused the 11:00am UIG nominations to not start. | UIG | All Shippers | The monthly Annual Quantity (AQ) update has overrun due to a large number of records. This has caused a delay to the 10:00am UIG nomination job in Gemini. The AQ job completed at 11:45am but the UIG nomination process is still in progress. The next UIG job was due to start at 11:00am, however this will be put on hold and the nomination job at 1:00pm will be run instead. | 2018-11-30 |  | Blue |  | 2018-11-30
63 | Closed | 937188 | P2 | N/A | N/A | Users unable to query Data Enquiry Servoce (DES) |  | Users unable to access DES due to high system utilisation. DES not available from 04:17 to 05:37 | Data Enquiry | All Customers | Formula year AQ/SOQ extraction and the monthly NLSP load were running in parallel and causing the high utilisation. Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2018-12-03 04:17 |  | Blue |  | 2018-12-03 04:17
64 | Closed | 938847 | P2 | N/A | N/A | Connectivity issue with NG Metering |  | Daily reads file (.DLC) not received from DMSP at usual time due to a connectivity issue with the IX. | IX | Shippers & Networks | router fault as the circuit tests showed no issues | 2018-12-08 |  | Blue |  | 2018-12-08
65 | Closed |  | N/A | 1247 |  | Winter Consumption process not using all reads types during calculation |  | Winter Consumption calculation process in not using all read types to calculate the WC. | Read process | Shippers & Networks |  | 2018-12-20 | 22/03/2019 | Blue
66 | Closed | 945238 | P2 | N/A | N/A | Daily Read file (.MDR) not issued before 14:00 hrs. |  | Delay in submitting the daily reads file to Shippers (.MDR) file. | Read process | All Shippers | UK Link – AMT Market flow slowness / performance issue | 2018-12-31 |  | Blue |  | 2018-12-31
67 | Closed |  | N/A | 1256 Problem ID 1996 |  | Opening Reads Sent via the U03 file in Error to Previous Shipper |  | For Class 3 meter points, where a cyclic read is received from the Outgoing Shipper (via the .UBR file), for a read date, which is the same as the registration effective date (transfer date), the system is accepting the read, it should reject the meter reading. The read is being recorded as the Opening read (U03) and is being sent to the Shipper who submitted the read, and to the current Shipper as a Final read (U04) indicator | Read process | All Shippers |  | 2019-01-04 | 08/03/2019 | Blue
68 | Closed | 947237 | P2 | N/A | N/A | Issue with sending the NTS Exit Capacity Invoice |  | The NTS Exit Capacity Invoice (.NXC) for the December 2018 billing period failed to send due to the CHARGE_ITEM_REF_NUMBER being 10 digits. Previously it has always been a maximum of 9 digits but due to incrementation it is now 10 digits. This is a mandatory field in the file formats with a numeric field length of 9 digits. | Invoice - NTS Capacity | All Shippers | This is due to the incrementation of the charge item reference number from 9 digits to 10 digits | 2019-01-07 |  | Blue |  | 2019-01-07
69 | Closed |  | N/A | 1265 |  | NDMSOQ Incorrect due to Winter Consumption process |  | The Winter Consumption calculation process does not create records in the correct table in UK Link, this results in the NDMSOQ value being incorrect for the annual FYAQ calculation. | AQ process | Shippers & Networks |  | 2019-01-16 | 08/03/2019 | Blue
70 | Closed |  | N/A | 1264 |  | Incorrect data provided in AQ notification file T98 file record |  | The monthly AQ Roll process is populating the incorrect EUC number, EUC description and confirmation reference number in the T98 file record of the NRL file (AQ notification) | AQ process | Shippers & Networks |  | 2019-01-16 | 22/03/2019 | Blue
71 | Closed | 888087 | N/A | 1274 | N/A | Class Change requests incorrectly rejecting following Transfer of Ownership | Shipper unable to change Class until after 2 months of taking ownership of the meter point. Does not prevent transfer of ownership. Workaround in place to stop files rejecting however minimal impact - low volumes of Shippers affected | Shipper Class change requests are incorrectly rejecting where a change of ownership has taken place within 2 months of the previous Class change request | SPA - Class change | All Shippers | TBC | 2019-01-22 | 2019-05-01 | Blue | Defect 1274: Deployed 17th May 2019 | 2019-05-17
72 | Closed | 950723 | P2 | N/A | N/A | Incorrect energy and incorrect estimated daily reads for Class 1 and 2 meter points |  | Incorrect energy for Class 1 and 2 meter points for Gas Flow Day (GFD) 18th January 2019 and incorrect estimated daily reads for Class 1 and 2 meter points issued in the MDR file for GFD 20th, 21st, 22nd and 23rd January 2019 | Read process | All Shippers | On 18th January 2019 a P2 incident (950723) was raised due to a batch failure which resulted in a delay issuing the daily reads (MDR file) to Shippers. The files were issued at 7:00pm on 19th January when they should have been issued by 2:30pm. Unfortunately, this had a knock on affect to subsequent days; 1. The actual Calorific Value (CV) was not loaded into UK Link on 19th January for GFD 18th January. Therefore the energy calculated used an estimated CV value. 2. Estimated reads, where an actual read was not received/accepted, was not calculated for GFD 19th January and was not loaded into Gemini nor issued to Shippers (via the MDR file). 3. Any estimated reads required for GFDs 20th, 21st, 22nd and 23rd January did not calculate correctly. The energy was correct but the meter reading issued in the file (MDR) was incorrect. | 2019-01-23 |  | Blue |  | 2019-01-23
74 | Closed | 954337 | P2 | N/A | N/A | Delay in publishing UIG Gas Nominations for 1st Feb. |  | Delay in publishing the UIG Gas Nominations for 1st Feb | UIG | All Shippers | Gemini: UIG Nomination Day Ahead Batch Job Failed Due to Incorrect Meter ID Entries in file to gemini | 2019-01-31 |  | Blue |  | 2019-01-31
75 | Closed | 955031 | P2 | N/A | N/A | EU Nominations are not getting confirmed |  | EU Nominations in Gemini are not getting confirmed affecting 6 Shipper. | Gemini processes | GTs | Service restarted, files started to flow successfully without any issues. | 2019-02-02 |  | Blue |  | 2019-02-02
76 | Closed |  | N/A | 1293 | N/A | Incorrect data provided within the Asset Invoice supporting file (MIF) |  | Issue with the Asset Invoice MIF File (Supporting information file generated as part of the MAS invoice). The K50 file record (Meter Portfolil Detail) is being populated with the incorrect data. | Invoice - Ancillary | All Shippers | TBC | 2019-02-05 | 05/04/2019 | Blue | Deployed on 05/04/2019 | 2019-04-05
77 | Closed | 959618 | P2 | N/A | N/A | Demand attribution is not published for 17th and 18th gas day |  | Gas nominations & allocations not published for the 17th & 18th February in Gemini. | Gas Nomination & Allocation processes | All Shippers |  | 2019-02-18 |  | Blue |  | 2019-02-18
78 | Closed | 962629 | P2 | N/A | N/A | CMS Unavailable |  | CMS - Application unavailable between 12:04 to 13:10. | CMS | All Customers | File Exchange service went down. P3 ticket has been raised for monitoring | 2019-02-25 |  | Blue |  | 2019-02-25
79 | Closed | 963956 | P2 | N/A | N/A | Gemini application will be unavailable |  | Unavailability of Gemini from 03:01 to 09:13 meaning Users will not be able to perform any of the business process untill the services are restored. | Gemini processes | Shippers & Networks | P3 ticket (964561) has been raised for monitoring | 2019-02-27 | 2019-02-27 | Blue |  | 2019-02-27
80 | Closed | 972030 | P2 | N/A | N/A | No access to Data Enquiry System (DES) |  | Users unable to access DES, identified on 18/03/19 at 11:10 | Data Enquiry | All Customers | Application support team identified a high number of sessions were open which resulted in the outage of the application from 11:10 to 11:35. Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2019-03-18 | 2019-03-18 | Blue |  | 2019-03-18
82 | Closed | 974369 | P2 | N/A | N/A | Intermittent login issue with Xoserve Portal |  | Users experiencing intermittent issues with loggin into the Portal, error message displayed. Identified at 08:46 on 22/03/2019 | Portal | All Customers | The User Identification (IDAM) issue, system was re-started which resolved the issue at 10:16. | 2019-03-22 | 2019-03-22 | Blue |  | 2019-03-22
83 | Closed | 974852 | P2 | N/A | N/A | Users unable to access Gemini |  | Users unable to access Gemini impacting Gas Nominations, UIG Nominations, demand estimation & Capacity Auctions. | Gemini processes | All Customers | Database error. Raised at 23:25, service resumed at 02:35 and all activities completed before maintenance window. | 2019-03-25 | 2019-03-25 | Blue |  | 2019-03-26
84 | Closed | 976190 | P2 | N/A | N/A | Intermittent access issue with Xoserve Portal |  | Identified on 25/03/2019 at 15:36 that users were getting intermittent issues with accessing the Xoserve Portal. | Portal | All Customers | Intermittent network issues between 15:00 and 16:00. Serviced resumed at 16:00. Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2019-03-25 | 2019-03-25 | Blue |  | 2019-03-25
85 | Closed | 976637 | P2 | N/A | N/A | Users unable to view data in online Gemini screen |  | Users were able to access Gemini but unable to view data in the online screens. Raised at 23:55. | Gemini processes | All Customers | Database error resulting in batch job failure. Archived log full, old files deleted. Service resumed on 27th March at 00:30. | 2019-03-26 | 2019-03-27 | Blue |  | 2019-03-27
86 | Closed | 977126 986730 | P2 | 1336 | N/A | File Record incorrectly being sent for lapsed Nomination Offers | Data being issued to Shippers when they are not entitled to it. Workaround in place to stop S91 records being sent for lapsed nomination offers in .NRL file each month. Data correction being carried out on monthly basis. | Revised Supply Point Data Notifications (S91 File Record), within the Annual Quantity (AQ) Notification file (NRL), have been incorrectly issued to the Nominating Shipper after the Nomination Offer has lapsed; 748 meter points have been affected | SPA - Transfer of Ownership | All Shippers | System functionality - defect raised. As part of our resolution to fix the issue, and in preparation to generate the correct .NRL file in April, a system data fix to update the status of the Offers was carried out. Three MPRNs were not included in the data fix, which resulted data being issued in the NRL file on Thursday 18th April. | 2019-03-27 | 2019-05-01 | Blue | Additional ticket number added due to incident re-occuring on 18/04/2019 Defect 1336: Data fix deployed 12th April Enduring fix deployed 10th May 2019. Business validation on the AQ notification file completed 23rd May and .NRL files successfully delivered on 24/05/2019 | 2019-05-24
87 | Closed | 977205 | N/A | N/A | N/A | Delay in sending the daily read files (MDR) to Shippers |  | On the 28th March 2019 the daily read files (for Gas Flow Day of the 27th march 2019 ) for Class 1 sites were issued late to Shippers | Read process | All Shippers | To be confirmed | 2019-03-28 | 2019-04-01 | Blue |  | 2019-04-02
88 | Closed | 977462 | P2 | N/A | N/A | IX – Connectivity issue with multiple shipper sites. |  | On 29/03/2019 at 16:07 it was identified there was an IX connectivity issue for multiple customers. | All processes | All Customers | Outage in network affecting multiple customers. Service was restored at 17:30 | 2019-03-29 | 2019-03-29 | Blue |  | 2019-03-29
89 | Closed | 977961 | P2 | N/A | N/A | UIG Gas Nomination not published. |  | UIG for the 1st April not published. Identified on 31/03/19 at 11:16 | UIG | All Shippers | Data issue causing UIG batch job to fail. Fix applied and UIG published at 14:32. | 2019-03-31 | 2019-03-31 | Blue |  | 2019-03-31
90 | Closed | 978104 | P2 | N/A | N/A | CMS services unavailable |  | All users unable to perform any operations in CMS, identified at 08:24. | CMS | All Shippers | Identified at 08:24. SQL exceptions raised, Vendor involved and logs shared. Service restored at 11:15. | 2019-04-01 | 2019-04-01 | Blue |  | 2019-04-01
91 | Closed | 978225 | P2 | N/A | N/A | IX – Connectivity issue for multiple customers. |  | On 01/04/2019 at 12:12 it was identified there was an IX connectivity issue for multiple customers. This also affected the ability to connect to Gemini via Citrix . This was due to capacity issue with Xoserve's Third Party Suppliers automation software | All processes | All Customers | Outage in network affecting multiple customers. Service was restored on 01/04/2019 at 12:45. | 2019-04-01 | 2019-04-01 | Blue |  | 2019-04-01
92 | Closed | 978730 | P2 | N/A | N/A | Portal Services performance issues |  | Some Users experiencing performance issues with Portal & CMS | Portal | All customers | Configuration change implemented on 28th March 2019. Portal team reverted the configuration change on 12/04/19 which was originally implemented on 28th March to resolve the issue. (RFC 8086 : Modify Portal Maintenance configuration to support application specific maintenance page) | 2019-04-02 | 2019-04-02 | Blue | P2 closed as fix complete on 12/04/2019 | 2019-04-12
93 | Closed | 978889 | P2 | N/A | N/A | Transfer of ownership file (.TRF & .MRI) held in AMT- Market flow |  | On 02/04/2019 at 20:43 it was identified there was an issue in Market flow where files were not being processed. Alerts triggered, files prioritised & TRF/MRI files processed within D-1 of the registration effective date. Files generated on 2nd April, delivered to customers on the 3rd April. Effective date in these files was 4th April. | SPA - Transfer of Ownership | All Shippers | Files stuck in Market Flow due to increase of files received on 02/04/19 | 2019-04-02 | 2019-04-03 | Blue |  | 2019-04-03
94 | Closed | 979373 | P2 | N/A | N/A | UIG Nomination not published in time within Gemini |  | UIG Nominations were delayed in being published for GFD 5th April 2019 | UIG | All Shippers | Meter Details file (.MDS) was received on 03/04/19 and had two records associated to the same UG meter. Datafix applied to update the UG meter for which the data was not present. | 2019-04-04 | 2019-04-04 | Blue |  | 2019-04-04
95 | Closed | 979500 | P2 | N/A | N/A | Delay in issuing the Invoicing (.INV) files |  | Delays in issuing the invoicing (.INV) files from AMT Market flow due to a backlog of files. Alerts triggered and files prioritised. All files were issued before 17:00 hrs. | Invoicing - General | All Shippers | Backlog of files were holding up the processing of the Invoicing files and therefore caused delay | 2019-04-04 | 2019-04-04 | Blue |  | 2019-04-04
96 | Closed | 981847 | P2 | N/A | N/A | IX – Connectivity issue for multiple customers. |  | On 08/04/2019 at 17:06 it was identified there was an IX connectivity issue for multiple customers affecting the flow of files. Service resumed at 18:51 | All processes | All Customers | Third party technical fault | 2019-04-08 | 2019-04-08 | Blue |  | 2019-04-08
97 | Closed | 980799 | P2 | N/A | N/A | EU Gas Nominations Job Failures in Gemini |  | Shippers are unable to confirm EU nominations in Gemini due to a delays in receiving auction details. Impact time 01:38am and resolved at 14:07pm | Gemini processes | All Shippers | Batch Job Failure | 2019-04-08 | 2019-04-08 | Blue |  | 2019-04-08
98 | Closed | 986190 | P2 | N/A | N/A | Data Enquiry Service currently unavailable | Customers unable to access the Data Enquiry system | Xoserve system failed which resulted in customers not being able to access the Data Enquiry Service from 05:11am until 15:41pm on 22nd April | Portal | All Customers | Xoserve system failing due to third party technical error. Service review or Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-04-22 | 2019-04-22 | Blue |  | 2019-04-22
99 | Closed | 983611 979757 | N/A | 1350 1363 | N/A | Issues relating to processing of Supply Point Updates | Shippers are unable to update Supply Meter Point details | 1350: When a Shipper is trying to amend Supply Point Meter Details via the .SPC file, the files are being rejected for NTS Direct Connect Telemetered Sites due to postcode validation not existing in the system. Low volume of MPRNs affected 1363: Requests to update the Shipper Nomination Reference Number via the RFA file are being rejected incorrectly. | SPA - Update of Supply Meter Point Details | All Shippers | System functionality not having the required validation in place | 2019-04-12 | 2019-05-01 | Blue | Defect 1350: Deployed 17th May 2019 Defect 1363: Deployed 10th May 2019 | 2019-05-17
100 | Closed | 989460 | P2 | N/A | N/A | CMS Performance issues | Users experiencing slowness with the service | 11:43 CMS performance issues, with users advising that the service was running slow. 12:46 System performance resolved and running back to full capacity | CMS | All Customers | CMS applications team found a long running query in the system which they then stopped and performance was improved. A P3 ticket has been raised for ongoing monitoring. | 2019-04-30 | 2019-04-30 | Blue |  | 2019-04-30
101 | Closed | 989433 | P2 | N/A | N/A | Data Enquiry (DES) Performance issues | Users experiencing slowness with the service | 10:16 Some users experiencing performance issues with Data Enquiry Service 14:50 System performance resolved and running back to full capacity | Data Enquiry | All Customers | Batch job overrun. Prevention – Improved identification of high CPU spikes. Service review of Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-04-30 | 2019-04-30 | Blue |  | 2019-04-30
102 | Closed | 987198 | P2 | N/A | N/A | Monthly AQ not updated for 9,000 MPRNs | Shippers had not received notification of an AQ revision in the montly .NRL file .NRL files are being manually for affected MPRNs sent to Shippers via the IX / Email. | During the AQ calculation process for April 2019, a system exception was created for approximately 9,000 Supply Meter Points. The exceptions were not processed in time, before the notification file (.NRL) was sent, which resulted in a revised AQ not being calculated with an effective date of 1st May 2019 and notified to Shippers. NDM Nominations and UIG Gas Allocations were incorrect for Gas Flow Day 1st May 2019 however the gas allocations were corrected for the 1st May 2019 before GFD+5. All relevant tables updated prior to the generation of AQ reports issued to Networks. | AQ process | All Shippers | Exceptions were not resolved and processed before the AQ process and notification files were isued. | 2019-04-24 | 2019-05-01 | Blue | Incident closed on 31st May. Communication sent to Shippers, requesting preferred method to receive the AQ Notification files (NRL). Customer Advocates have contacted outstanding Shippers directly to advise on this. | 2019-05-31
103 | Closed | 990784 | P2 | N/A | N/A | CMS Performance issues | Users not able to access the system | 07:31 CMS performance issues, with users advising that the service is running slow and that they are being timed out of the system. 10:48 Service resumed and running back to full capacity | CMS | All Customers | Database start-up was delayed as there was an implementation change carried out, start-up job got failed, which resulted in unnecessary timeouts with the system. | 2019-05-03 | 2019-05-03 | Blue |  | 2019-05-03
104 | Closed | 991005 | P2 | N/A | N/A | Delay in publishing UIG Gas Nominations for 4th May | Shippers unable to determine how much gas they need to buy via online screen for next gas day due to information not being published on time in Gemini | Delay in publishing the UIG Gas Nominations for Gas Flow Day 4th May 2019 | Gemini processes | All Shippers | Manual Error. Prevention – Review appropriate checks are completed. | 2019-05-03 | 2019-05-03 | Blue |  | 2019-05-03
105 | Closed | 995034 | P2 | N/A | N/A | Data Enquiry Service unavailable for customers | Users unable to access Data Enquiry Service | Customers were able to access the Xoserve Portal, however there were multiple customers unable to access the Data Enquiry Service from 11:15am. Service was resumed at 11:30am | Data Enquiry | All Customers | Concurrent maximum threshold for users was exceeded Prevention – Increase the threshold for users planned change target 22/06/19 Service review or Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-05-16 | 2019-05-16 | Blue |  | 2019-05-16
106 | Closed | 989429 | N/A | N/A | N/A | Delay in issuing the Notification of Meter Point Status Change files (.NMS). | Shippers were not notified of changes to meter point statuses, or effective change dates in UK Link for Supply Meter Points in their ownership. For example, meter point status changes from Dead (DE) to Live (LI) and the date that this was effective from. | From Monday 8th April 2019 to Friday 3rd May 2019, Shippers had not received the Notification of Meter Point Status Change files (.NMS) | SPA - Supply Point Updates | Shippers | The files were not sent as a result of a system restart error in SAP ISU. One .NMS file failed which then prevented any subsequent files to be processed. | 2019-05-08 | 2019-05-16 | Blue |  | 2019-05-16
107 | Closed |  | N/A | N/A | N/A | Issue identified with the current Find My Supplier web service | The web service was unavailable for customers from 3:15pm on 20/05/2019 until 12:00pm on 22/05/2019. Users attempting to use the web service were redirected to the Xoserve Domestic Consumer M Number Helpline | Internal validation code testing identified an issue in the current Find My Supplier web service that could potentially be abused by a malicious user. In order to resolve this issue, the service was suspended with immediate effect. During the service outage a message was displayed on the website informing users of the ongoing maintenance. | Find My Supplier | All Customers | Development and build of the system lacked security to prevent malicious users from hacking the system. | 2019-05-20 | 2019-05-22 | Blue |  | 2019-05-22
108 | Closed | 981489 | N/A | 1378 | N/A | Conflicting data provided in Network reports | Incorrect Weather Variance Correction (CWV) values provided in reports which are sent to Networks on a weekly basis Xoserve manual workaround in place to retrieve correct values which mitigates impact to customers | It has been identified that there is a mismatch of Weather Variance Correction values (CWV) within two reports which are sent to Networks on a weekly basis (Network Throughput Data Weekly Report and Weather and CV Report) | Revenue Assurance Reporting | Networks | TBC | 2019-04-08 | 2019-06-01 | Blue | Defect 1378: Deployed 7th June 2019 | 2019-06-07
109 | Closed | 998106 | P2 | N/A | N/A | Xoserve Portal Service unavailable for customers | Users unable to access Xoserve Portal | All users unable to perform any operations in Xoserve Portal from 8:06am on 23/05/2019. Service was restored at 08:36am on 23/05/2019 | Portal | All Customers | Portal services failed to load, following maintenance checks carried out. Service review or Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-05-23 | 2019-05-23 | Blue |  | 2019-05-23
110 | Closed | 998274 | P2 | N/A | N/A | CMS Performance issues | Users experiencing slowness with the service | 09:10 CMS performance issues, with users advising that the service is running slow and that they are unable to navigate round the system 10:20 Service resumed and running back to full capacity | CMS | All Customers | Increased traffic in the system caused the application to run slower than normal | 2019-05-23 | 2019-05-23 | Blue |  | 2019-05-23
111 | Closed | 999101 | P2 | N/A | N/A | Data Enquiry (DES) Performance issues | Users experiencing slowness with the service | 10:21 Due to an internal batch job overunning, there was a subsequent effect on DES performance for customers, experiencing intermittent speed and access issues with Xoserve Portal 1:31pm Service was restored and running back to full capacity | Portal | All Customers | Delay of files from CMS which has had a subsequent effect to the daily job in Portal and resulted in high volume of traffic in the system. Service review or Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-05-24 | 2019-05-24 | Blue |  | 2019-05-24
112 | Closed | 999785 | P2 | N/A | N/A | Issues generating AAQ and MDS Files | Gas Nominations and allocations in Gemini would have been incorrect if the files were not manually corrected | Due to deployment of another defect, Aggregated Annual Quantity (AAQ) and Meter Details (MDS) files for Gas Flow Days 24th, 25th and 26th were not generated. There was a workaround in place for the files to be loaded into Gemini by the end of the day, and therefore there was no impact to Demand Attribution or UIG. | Gemini processes | All Shippers and Networks | Due to the implementation of defect 1310 | 2019-05-26 | 2019-05-26 | Blue |  | 2019-05-26
113 | Closed | 1001036 | P2 | N/A | N/A | Slowness with Xoserve Service Portal | Users experiencing slowness with the service | 15:10 Low number of customers raised tickets, advising that they were experiencing slowness within Portal 15:25 Service was restored and running back to full capacity | Portal | All Customers | Database error referred to Third Party for analysis and recommended to apply a patch. Prevention – Testing of patch in progress target date 02/07/19. Service review or Portal, Offline services & Data Enquiry Service being carried out July 2019. | 2019-05-30 | 2019-05-30 | Blue |  | 2019-05-30
114 | Closed | 1004222 | P2 | N/A | N/A | AMT Market Flow stopped polling inbound DLC files | Estimated reads may not be accurate | AMT Market Flow stopped polling inbound Daily Read Equipment Read (.DLC) files. The application was restarted and files were successfully processed in time, therefore no impact to systems | Read process | Shippers and Networks | Root cause analysis ongoing | 2019-06-05 | 2019-06-05 | Blue |  | 2019-06-05
115 | Closed | 1004230 | P2 | N/A | N/A | Xoserve Portal Service unavailable for multiple customers | Low number of customers unable to access the Xoserve Portal | 08:35am Low number of customers were unable to access the Xoserve Portal 08:52am Service was resumed | Portal | All Customers | Due to system downtime being short no logs were taken to be able to investigate the route cause. | 2019-06-05 | 2019-06-05 | Blue |  | 2019-06-05
116 | Open | 995137 | N/A | 1394 | N/A | Issues with manual Replacement Reads | This may impact reconciliation charges, and issuing of Billable Meter Readings (.MBR) No workaround in place, however all meter points affected will require a data correction once the fix has been deployed. | Where an Xoserve user manually replaces an opening read on behalf of a Shipper, an internal table within the system is not updating correctly, which is causing downstream impacts | Read process | All Shippers | Root cause analysis ongoing | 2019-05-16 | 2019-09-06 | Green | Defect 1394: Target deployment date is 6th September 2019
117 | Closed | 1006278 | P2 | N/A | N/A | UIG Allocations not published in Gemini | UIG allocations are not visible in Gemini for GFD 8th June 2019. | UIG allocations have not been calculated for GFD 8th June, resulting in UIG allocations not being published in Gemini on time. | Gemini processes | All Shippers | The Calorific Values File (CVV) was rejected by Gemini, as it was outside of the acceptable validation range. | 2019-06-10 | 2019-06-10 | Blue |  | 2019-06-10
118 | Closed | 1007415 | P2 | N/A | N/A | AMT Market Flow application unavailable | Customers unable to send or receive files | AMT Market Flow primary server was unavailable from 8:30am on 12th June 2019. As a result, Xoserve were unable to process incoming and outgoing files. | AMT | All Customers | The overrunning of a file permissions script Prevention – Improved identification of high CPU spikes and ongoing investigations with 3rd party vendor to address script overrunning. | 2019-06-12 | 2019-06-12 | Blue |  | 2019-06-12
119 | Closed | 1007416 | P2 | N/A | N/A | Xoserve Portal Service unavailable for customers | Users unable to access Xoserve Portal | All users unable to perform any operations in Xoserve Portal from 8:31am on 12/06/2019. | Portal | All Customers | A number of concurrent user sessions exceeding normal daily usuage Prevention – uprgade to usuage permissions | 2019-06-12 | 2019-06-13 | Blue |  | 2019-06-13
120 | Closed | 1008921 | P2 | N/A | N/A | Users unable to access DES Portal | Low number of customers unable to access Data Enquiry Service | 11:52am Low number of customers were unable to access Data Enquiry 11:55am Service was resumed | Data Enquiry | All Customers | Increased traffic in the system caused the application to run slower than normal. Service review or Portal, Offline services & Data Enquiry Service being carried out June 2019. | 2019-06-17 | 2019-06-17 | Blue |  | 2019-06-17
121 | Closed | 1009091 | P2 | N/A | N/A | UIG Allocations not published in Gemini | The allocations for Gas Flow Day 16th June 2019 not visible in Gemini | Allocations have not been calculated for GFD 16th June and not published in Gemini until 19th June. | Gemini processes | All Shippers | Allocation suite and invoice batch jobs had not completed delaying the allocation batch process. Full RCA expected 09/07/2019 | 2019-06-18 | 2019-06-18 | Blue |  | 2019-06-18
122 | Closed | 1010254 | P2 | N/A | N/A | CMS Performance issues | Users are experiencing performance issues while accessing the application | 10:23 P2 raised as Users experiencing performance issues with CMS application & internal users unable to upload files. Outage between 11.30 to 11:50 and again from 12:40 to 13: 15. Service resumed at 13:15. | CMS | All Customers | RCA expected 20/08/2019 | 2019-06-21 | 2019-06-21 | Blue |  | 2019-06-21
123 | Open | 963807 | N/A | 1311 1407 1422 1418 1441 | N/A | Issues with customer reports | 1311: Networks will be undercharging the price of gas to their customers 1407: Network is receiving incorrect emergency contact details within their files 1422: IGT's are not receiving emergency contact details 1418: Incorrect isolation contact details issued in files 1441: Conflicting information held between two reports issued to Shippers | 1311: The BOPRI report is issued to DNs monthly. Issue affects 1 GT where the AQ has dropped by a total of 1.7% since the previous month. 1407: Where a Shipper is providing new emergency contact details for a site, the National Grid Emergency File (EWS) is being populated with the updated details as required, however it is also containing the previous contact number within the 'Alternative Contact 2' field 1422: Where a Shipper is providing new emergency contact details for an IGT site, the Daily Delta File (IDL) is not containing any emergency contact details 1418: Legacy isolation contact details are not being correctly end dated within the National Grid Emergency File (EWS) 1441: The values in the Performance Assurance Report Register(PARR) for the 'No Meter Attached' and 'No Meter Attached but Data Flows Received' tabs do not agree to the corresponding values issued within the monthly Shipper Packs. | Reporting | Networks |  | 2019-02-26 | 2019-09-20 | Green | Defect 1311: Defect closed as not code fix required. Defect 1407: Deployed 5th August 2019 Defect 1418:Deployed 5th August 2019 Defect 1422: Deployment date is 20th September 2019 Defect 1441: Deployment date TBC
124 | Closed | 943678 | N/A | 1348 | N/A | Incorrect NDM forecasts in Gemini | The effective temperature value for gas nominations in Gemini is incorrect which is causing significantly higher Non Daily Metered forecasts due to the temperature discrepancy. All LDZs impacted | Multiple internal files are required to be processed in Gemini in a certain order to calculate the weather temperature for D-1, however due to the files not being processed in the required order, the effective temperature for Gas Day -1 is being calculated incorrectly. | Gemini processes | Shippers & Networks |  | 2018-12-28 | 2019-06-27 | Blue | Defect closed as files have been automated | 2019-06-27
125 | Closed | 968192 | N/A | 1366 | N/A | Allocation Agent file not delivered (for a Shared Supply Meter Point (SSMP)) | Agent requires the file in order to allocate energy between Sharing Users in Gemini Minimal mpact as Xoserve are manually sending the files | Comm Ops Agent File (CMA) which is sent to NG (Gemini) 3 times a day, is only being sent twice | Gemini processes | Networks |  | 2019-03-08 | 2019-08-01 | Blue | Defect 1366: Deployed on 30th August 2019 | 2019-08-30
126 | Closed | 985357 | N/A | 1371 | N/A | Consumption Adjustment incorrectly rejecting following class change | Shippers are unable to amend adjustmemts where there has been a class change No workaround currently in place, however any sites which are facing this issue can have Consumption Adjustment once the defect has been deployed | Where an Xoserve user manually processes a Consumption Adjustment on behalf of a Shipper, where there has been a class change from Class 1, 2 and 3 to Class 4, the system is incorrectly rejecting due to the adjustment period not being a valid meter read period. However the read period is correct and should be accepted. | Consumption Adjustment | All Shippers |  | 2019-05-06 | 2019-08-01 | Blue | Defect 1371: Deployed on 30th August 2019 | 2019-08-30
127 | Closed | 990336 | N/A | 1404 | N/A | System files not correctly processing into UK Link | Defect 1404: Shippers will be billed incorrectly if the file is not loaded into the system when the invoice is issued. As Shippers will not be billed until the file is successfully loaded into the system, there is no direct impact to customers. | 1404: The Post Closeout Allocation file (PCA) which is an internal fie processed from Gemini to UK Link, is causing energy data for Interconnectors to not update in the system with the revised energy values from Gemini | Energy | All Shippers | Post Closeout Allocation file is not automatically being processed as required. Technical team is manually having to upload the file into the system until fix is deployed. | 2019-06-17 | 2019-08-01 | Blue | Defect 1404: Deployed on 30th August 2019 | 2019-08-30
128 | Closed | 1012333 | P2 | N/A | N/A | CMS services unavailable | Customer unable to carry out any actions in CMS | All users unable to perform any operations in CMS, identified at 07:13 | CMS | All Customers | Configuration files were removed from server statup location, when system was rebooted the system could not locate the files, therefore system would not reboot. | 2019-06-28 | 2019-06-28 | Blue | CMS restored 10.32am | 2019-06-28
129 | Open | 1010369 | N/A | 1409 1430 1406 1443 1444 | N/A | Reads not being processed correctly | Potentially affect reconciliation and submission of future reads | 1409: When a Shipper replaces an Opening Read with a Non-Opening Read (Reason code 'N'), the request is being accepted however should reject as this should not be possible 1430: Following the removal of an AMR via an asset update (ONUPD) without a read, the estimated transfer read is not getting generated and loaded to the system. 1406: Following a cosmetic correcter exchange (decreasing number of dials), the opening read value sent within the Dataset Read Notification File (DRS) to Shippers is incorrect 1443: Where a meter exchange and class change happens one day apart, the consumption and energy is not being calculated for this period 1444: On receipt of a Site Visit and asset fault notification file (.SFN), read validation tolerance checks are being carried out for all meters, as opposed to the billable asset | Read Process | All Shippers |  | 2019-06-21 | 2019-10-04 | Green | Defect 1409: Deployed on 30th August 2019 Defect 1430: Deployment date is 4th October 2019 Defect 1406: Deployment date is TBC Defect 1443: Deployment date is TBC Defect 1444: Target deployment date is 8th November 2019
130 | Closed | 1013931 | P2 | N/A | N/A | Intermittent access issues for multiple shippers using Gemini | Customers unable to access Gemini and carry out any processes. | Shippers did not have access to Gemini via the API and were unable to progress any automated processes and will not be able to complete any bulk uploads or downloads. | Gemini processes | All Customers | Awaiting RCA from third party vendor | 2019-07-03 | 2019-07-03 | Blue | System restored | 2019-07-03
131 | Closed | 1015019 | P2 | N/A | N/A | Delay in publishing UIG Gas Nominations | Shippers unable to determine how much gas they need to buy via online screen for next gas day due to information not being published on time in Gemini | Delay in publishing the UIG Gas Nominations for Gas Flow Day 6th, 7th and 8th July 2019 | Gemini processes | All Shippers | Awaiting RCA from third party vendor | 2019-07-07 | 2019-07-07 | Blue | System restored | 2019-07-08
132 | Closed | 1016280 1018932 | P1 | N/A | N/A | Historic Emergency Contact & isolation contact details & 'alternative contact details' being issued in files | Gas Transporters could potentially use incorrect contact details in emergency situation | Historic Emergency & isolation contact details are being provided to the Networks and IGTs within the Daily Delta Files and Quartlery Delta Files (EDL, EWS, EQL, IDL & IQL). Code fix and data fix implemented to correct any corrupt data. Scenario also applied to 'alternative contact details' provided as part of PSR data. | SPA | All Gas Transporters | Due to data migration from legacy system, files not end-dating details following an update. | 2019-07-10 | 2019-07-10 | Blue | Code fix and data fix implemented to correct any corrupt data. | 2019-07-21
133 | Closed | 1018468 | P2 | N/A | N/A | Potential delay in sending the UPI invoice support information files | Delay in customers receiving their supporting files therefore unable to validate or interrogate their invoice charges | Invoice issued as expected however the supporting files are not producing in the time expected. | Invoicing - General | Customers | Expected 23rd August 2019 | 2017-07-15 | 2019-07-15 | Blue | Code fix implemented after testing it in pre-production environment. All the supporting information files were generated successfully in ISU. AMT Market flow team confirmed that all the files has been delivered to shippers within SLA and delivery receipt received | 2019-07-15
134 | Closed | 1023187 | P2 | N/A | N/A | Delay in processing read files | Delay for customers receiving their read response file notifying if the reads have been accepted or rejected. | Read files for Class 3 and 4 meter points received on 31t July ans 1st August were not processed until 2nd August. Although the SLA is 2 business days the files are usually processed and a response sent within 1 business day. | Read process | All Shippers | Files for the 31st July were held in the system which meant any subsequent read files were also held. Full RCA expected on 23/08/2019. | 2019-08-02 | 2019-08-02 | Blue | Files received on the 31st July were not processed and responed to until 2nd August 2019 | 2019-08-02
135 | Closed | 931836 | P2 | N/A | N/A | Multiple Job Failures in Gemini Entry System | This will impact shipper's gas buying decision | Demand did publish for 00:00 hrs. Latest NDM nomination and UIG nomination will not be visible on the screen | Gemini processes | All Shippers | Expected 23rd August 2019 | 2019-08-02 | 2019-07-07 | Blue | System restored at 16:00 | 2019-07-07