## query
Title | Meeting Date | Action | Owner | Status | Update | Date Of Latest Update | Target Completion Date
0101 | 22/01/2018 | XRN4273 - Installed Status of Failed MOD614 - To consider impacted reports if known through the impact assessment. | Xoserve | Closed | Part of Release 3.0 impact assessment.
0102 | 22/01/2018 | XRN4381 - The Updating of the ZDT_AQ_OPER table - Share the change that this links to with DSG | Xoserve | Closed | Confirmed no link to other change and removed from R3. To be delivered by Minor Enhancements.
0103 | 22/01/2018 | XRN4431 - Reads failing market breaker tolerance to be accepted for correct date following AQ Correction - Xoserve to add to the agenda on 5th February and bring solution options. | Xoserve (ES) | Closed | Options provided as part of 19th Feb DSG agenda. New action (0211) associated to this XRN.
0104 | 22/01/2018 | XRN4477 -Response file for (AIR) the request to bill (RTB) submission from Networks are not getting generated for the originator. The change is to be issued to the Networks and the Networks to confirm that it can be closed. | Xoserve (RH) | Closed | Action closed as the change has been issued within Change Pack (1856.1) on 31st Jan as 'proposed to close'
0105 | 22/01/2018 | XRN4453 - File format should have changes - Xoserve to release the list containing the 270 changes and DSG to confirm if there are functional changes that need to be considered within R3.0. | Xoserve (RH) | Closed | Issued in a Change Pack (1856.3) on 31st January. Open for representation comments until 21st Feb. Extended f2f DSG meeting arranged on 5th March to discuss these changes.
0106 | 22/01/2018 | XRN4436 -Change number of occurances for K13 record for SSMP’s - Xoserve to write out to all Shippers who manage shared supply point contracts to seek views | Xoserve (RH) | Closed | As there is no distribution list for SSMP Shippers and to solicit views of the change for other Shippers who will be impacted we issued in CP 1866.4 on 9th February. Representation period open untl 23rd February.
0107 | 22/01/2018 | XRN4432 - Amendment to U82 record to include the revised NTS optional tariff rate - The number of occurrences this has occurred to be shared. Xoserve to check all the hierarchies have been included within the change. | Xoserve | Closed | This will be included within the impact assessment for the change to be included within Release 3
0108 | 22/01/2018 | XRN4486 - Meter Type O = Orifice to be an acceptable value in file formats and reports - Impacted records and files to be communicated. | Xoserve | Closed | Will be considered within the impact assessment for Release 3
0109 | 22/01/2018 | XRN3656 -Read Validation Tolerances - Analysis from across the industry / Xoserve analysis needs to be completed prior to the 5th February meeting. | Xoserve (RH) | Closed | This information is currently not available from SAP-BW until after R2. Request for the industry to share any analysis undertaken by 5th March DSG meeting
0110 | 22/01/2018 | XRN4484 - Remove restriction on nominated SOQ (as per MOD 445)- To issue within a Change Pack for ratifying at ChMC | Xoserve | Closed | This is an internal impact to Xoserve. A CP will be issued when the change is being delivered
0111 | 22/01/2018 | XRN 4465 - Annual Production and notification of LIS-3years read - The change needs to be communicated - how the reads will be issued. Update to be provided to DSG on 5th February | Xoserve | Closed | Will be implemented in early March, will provide reads as estimates on the MBR file except for any twin stream /uniques/prime, for which there will be an exceptional process which would require manual read creation and notification.
0112 | 22/01/2018 | XRN4438 - Contact titles nullified report - Recommended either requires sponsorship or should be closed as couldn't gauge the benefit of such a report | Xoserve | Closed | Issued for industry views within Change Pack 1856.1 on 31st January. No comments received during the representation period and it is expected that this change will be closed.
0113 | 22/01/2018 | XRN4528 - The word ‘PLOT’ as a prefix - Confirm this is prior to the 'plot' change within Release 2.0 | Xoserve | Closed | This is due for delivery on 30th March, being delivered as a defect and is separate to the change being implemented in R2
0114 | 22/01/2018 | XRN4482 - SAP Meter Read Entry Screen - To define the outputs of the reads - how will Shipper Users know of the reads that have been entered manually | Xoserve | Closed | This activity can be completed through a minor enhancement. The Change Pack to be issued will inform Users of how to identify these reads
0115 | 22/01/2018 | XRN4503 - Late Meter Attached resolution - Further analysis to be completed | Xoserve | Closed | Change not within scope of R3. Potential closure of change TBC.
0116 | 22/01/2018 | XRN3732 - Capability to replace a sequence of readings - To be confirmed if required based on RAASP requirements. The industry wants to consider further scenarios to establish if there is a need to deliver this change. | DSG | Closed | No analysis to support the continuation of this change. Industry parties confirmed they had found no scenarios to support this change. Agreed by DSG to close this action.
0117 | 22/01/2018 | XRN4541 –Read Design Gaps - Missing Overide Flags In RGMA and Retro Files - Clarification will the removal of the outer tolerance validation be included within the change. Potential to introduce new rejection codes. | Xoserve | Closed | To be completed within the IA within R4
0118 | 22/01/2018 | XRN4495 - Energy Tolerance Rejection Code - Solution to be explored and assessment whether it can be in R3.0 | Xoserve | Closed | To be completed as part of the IA within R3
0119 | 22/01/2018 | XRN3667 - Provision of Formula year AQ - Solution to be explored and assessment whether it can be in R3.0 | Xoserve | Closed | To be completed as part of the IA within R3
0120 | 22/01/2018 | To request the defect drop be added into the bulletin | Xoserve | Closed | Has been completed
0201 | 05/02/2018 | EL to check with Matt Smith and advise KB regarding 2 defects | Xoserve | Closed | EL has provided an explanation to KB regarding the difference in defect and Service Desk priority scoring. Awaiting confirmation from KB that this has answered the query before closure.
0202 | 05/02/2018 | LC to send list of Primary and Secondary Scope items to BC | Xoserve | Closed | Has been completed
0203 | 05/02/2018 | LC to consider the question around sequencing and provide DSG members with an update | Xoserve | Closed | Data Migration plan to load files since service was stopped continues to be defined through design; options will be presented to DSG on 5th March. XRn4249 plan will have a DM phase within the plan and be tracked
0204 | 05/02/2018 | Customers to confirm training requirements at the next DSG meeting on 19th February | DSG | Closed | DSG members to input to training requirements by 19th.
0205 | 05/02/2018 | Customers to confirm preferred testing option for XRN4449 at next DSG meeting on 19th February | DSG | Closed | As of today
0206 | 05/02/2018 | Summary document and Change Packs to be sent to BC | Xoserve | Closed | Has been completed
0207 | 05/02/2018 | File format change document to be sent to BC | Xoserve | Closed | Has been completed
0208 | 19/02/2018 | XRN4449 - PSR reports - Xoserve to issue an anonymised example report within the minutes of the DSG meeting on 19th Feb. | Xoserve | Closed | Example report issued within the DSG minutes
0209 | 19/02/2018 | XRN4449 - PSR - Xoserve to issue the final version of PSR mapping rules via the uklink@xoserve.com box account. | Xoserve | Closed | Require confirmation from Tahera regarding the latest mapping rules. 04/05 - TC sent Mapping Rules in the DSG Meeting Minutes on 23/05.
0210 | 19/02/2018 | XRN4449 - Xoserve to add 'Volume of CNC updates' to the next DSG agenda. | Xoserve | Closed | Added to the agenda on 5th March and issued within the invite on 19th February. Action complete.
0211 | 19/02/2018 | XRN4431 - Reads failing market breaker tolerance to be accepted for correct date following AQ Correction - Xoserve to update the Option slides and present again at DSG on Monday 5th March | Xoserve | Closed | Slides to be updated and issued ahead of meeting.
0212 | 19/02/2018 | Xoserve arrange and issue invite to face to face DSG meeting on Monday 5th March. | Xoserve | Closed | Invite has been issued on 19th February. Action completed
0213 | 19/02/2018 | DSG members to provide feedback on the Xoserve website. | DSG | Closed | Feedback to be provided to the uklink@xoserve.com box account
0211 | 19/02/2018 | Xoserve to issue the latest version of the R2 Customer Training Requirments | Xoserve | Closed | Latest material issued within the minutes for the DSG meeting on 19th February
0301 | 05/03/2018 | XRN4249 - Xoserve (CF) to check whether it is possible to distinguish NAC update files compared to the normal update process. Retrospective updates, do NAC files go to both the incumbent and old Shipper? | Xoserve | Closed
0302 | 05/03/2018 | XRN4249 - Xoserve (CF) to look into system capacity for processing different levels of updates and any downstream updates (Eg MAMs). | Xoserve | Closed
0303 | 05/03/2018 | XRN4249 - Xoserve (CF) to assess whether the file updates can be stopped by Shippers too. | Xoserve | Closed
0304 | 05/03/2018 | XRN4449 - Customer Team to write out to request any further organisations wanting to test, to confirm by Friday 16th March. | DSG | Closed
0305 | 05/03/2018 | XRN4449 - Xoserve (CF) to publish the test scenarios on Xoserve.com | Xoserve | Closed
0306 | 05/03/2018 | XRN4449 - Xoserve (CF) to provide a run through of the Customer Testing Strategy during the next DSG meeting. | Xoserve | Closed | Closed - session completed at DSG 18/06
0307 | 05/03/2018 | XRN4449 - Xoserve (CF) to assess whether there is a limit on the number of test files that can be submitted. | Xoserve | Closed
0308 | 05/03/2018 | Portfolio up-loads - meeting participants to provide a direct contact who will be part of the XRN4449 process. | DSG | Closed
0309 | 05/03/2018 | Priority Service Register (PSR) - Xoserve (CF) provide an understanding of the size of the one off Shipper report. | Xoserve | Closed
0310 | 05/03/2018 | Priority Service Register (PSR) - Xoserve (TC): To consider the options of sending the one-off report by either encrypted USB or email. | Xoserve | Closed
0311 | 05/03/2018 | Volume of CNC Update - Daily Cap to be defined by Xoserve to share to Shippers. | Xoserve | Closed
0312 | 05/03/2018 | Release 3.0 Update - Xoserve (PD) to assess feasibility of booking early engagement meetings in advance. | Xoserve | Closed
0313 | 05/03/2018 | XRN4431 - Xoserve (ES) to provide scenarios with the different variations by the next meeting. | Xoserve | Closed
0314 | 05/03/2018 | XRN4431 - Shippers to provide scenarios to assist with testing. | DSG | Closed
0315 | 05/03/2018 | Xoserve (ES) ROM and costing required for XRN4431. | Xoserve | Closed
0316 | 05/03/2018 | XRN4539 - Centrica (BC) to assess what happens to files which go into a blackhole – how often this happens and if someone checks the blackhole. | Centrica | Closed
0317 | 19/03/2018 | Defect Dashboard - to be confirmed which date and defect release it is proposed to be completed within. | Xoserve | Closed
0318 | 19/03/2018 | XRN4431 - To update AQI file hierachy on the slides (includes read response files) and publish. | Xoserve | Closed
0319 | 19/03/2018 | XRN4431 - Xoserve to check the reconciliation process for any constraints with extending the time to submit the read with the AQ Correction to 3 months. | Xoserve | Closed
0320 | 19/03/2018 | XRN4539 - Communication to be issued to support Users to avoid this file level rejection. | Xoserve | Closed
0321 | 19/03/2018 | XRN4249 - Catch up exericse - Xoserve (CF) to issue communication detailing the catch up activies. | Xoserve | Closed
0322 | 19/03/2018 | XRN4249 - Catch up exercise - Xoserve (CF) to provide the plan for catch up activies. | Xoserve | Closed
0323 | 19/03/2018 | Implementation Plan - Xoserve to confirm this can be completed and discussions at the next DSG to discuss | Xoserve | Closed
0324 | 19/03/2018 | Xoserve to send out a communication to explain that administrative changes in files will not increment and seek industry views. | Xoserve | Closed
0401 | 09/04/2018 | Xoserve (DJ) to advise where in the process defect 655 currently is and if a fix has been identified. | Xoserve | Closed
0402 | 09/04/2018 | Xoserve (EL) to provide an update on ASP penny-mismatching. | Xoserve | Closed
0403 | 09/04/2018 | Shipper organisations who are participating in the industry testing need to provide key contact details, for communications to be issued directly. | DSG | Closed
0404 | 09/04/2018 | Xoserve (LC) to confirm the rejection code per file type. | Xoserve | Closed
0405 | 09/04/2018 | Xoserve (LC) to clearly advise timings in the lower level implementation plans. | Xoserve | Closed | Now provided in revised R2 Implementation Approach which is on the ChMC Agenda for Approval - Link. The lower level R2 cutover & implementation plan will then be shared with Customers via the DSG
0406 | 09/04/2018 | Xoserve (RH) to make documentation clear that the number of needs codes are per MPRN and not per file. | Xoserve | Closed | 04/05 - We would like clarification from DSG with the requirements
0407 | 09/04/2018 | Read Validation - Xoserve (LW) to speak with (MD) about training process; (ES) to compile an information document and send out to the industry. | Xoserve - David Addison | Closed | 01/08/2019 - As per previous discussion in the meeting, DSG were to look into the material, and to confirm if they were happy with the format and that this is what they wanted, and if so we would get this prioritised. 02/09/2019 - Link to the training material has been included in the minutes document. Action Closed. | 2019-08-01 | 2019-08-19
0408 | 09/04/2018 | Npower (JB) to provide further details on the issue for Npower on implementing XRN4431. Xoserve (MD) to organise a teleconference with meeting participants to further discuss this issue. | Npower/Xoserve | Closed | Meeting with Npower initial solution remains - if you do not wish to send a read you can also send your market breaker read code. Will then do validation check it does now - will market breaker read allows if you want to make changes to your systems.
0409 | 09/04/2018 | Xoserve (PD) to outline the impacts to DES separately for XRN4454. | Xoserve | Closed | This has done with Cadent and NG.
0410 | 09/04/2018 | Xoserve (RH) to provide a list of workarounds which will be retired as a result of XRN4454. | Xoserve | Closed
0411 | 09/04/2018 | Xoserve (RH) to correct the error within the documentation. | Xoserve | Closed | 0411 was corrected and issued in a revised change summary - 1917 on the 11th April.
0412 | 09/04/2018 | Xoserve (RH) to update the meeting times for DSG on Xoserve.com | Xoserve | Closed
0413 | 09/04/2018 | Xoserve (RH) to send out a notification about AQs of 1 (XRN3667.A). Will give an update at next DSG. | Xoserve | Closed | 04/05 – am update will be given to the industry on 09/05 following DSGs recommendation and a CP can be issued on 11/05
0414 | 23/04/2018 | UPD Address Dataset - Xoserve (DA) to put a formal change pack out and ask people to vote with all options and describe the options. | Xoserve | Closed | Will include within the next formal change pack.
0415 | 23/04/2018 | Read Validation Report - Xoserve (ES) to get an ETA when the report will be ready | Xoserve | Closed | Linked to Action 0407.
0416 | 23/04/2018 | XRN4449/UKLP273 - Xoserve (CF) needs to check on CP for this and confirm who said what. Also needs to look at other options if not via IX. (CF) to talk through these options with (TC). | Xoserve | Closed | This relates to the Supplier Report and Tahera has clairifed some aspects that we are working up in the File Format. 08/05 - TC provided an update to DSG.
0417 | 23/04/2018 | Xoserve (PD) to upload the 8 CRs for R3 changes. | Xoserve | Closed
0418 | 23/04/218 | Documentation Changes Feb 2019 - Xoserve (LW) to take on board British Gas comments regarding the the documentation release needs to be for everyone not just Xoserve. | Xoserve | Closed | 08/05 - on AOB at ChMC
0419 | 23/04/2018 | Inrease in AQs of 1 and understated AQs. Group to go away and think about options presented at DSG on 23/04 | DSG | Closed | Discussed at DSG on 08/05
0501 | 08/05/2018 | Defect Dashboard - DSG to go away and think about the current process of the Defect Dashboard, is this the right level for people? | DSG | Closed | To be discussed at next DSG on 21/05.&nbsp; Update:&nbsp; 21/05 - No further feedback from DSG.&nbsp; Xoserve to go away and think about new process. 02/07 - Xoserve considering the defect dashboard. Closed
0502 | 08/05/2018 | Release 2 Implementation Plan - - Xoserve (LC) to check if timestamps are in old file format up to and including 23:59? LC will clarify this and incorporate into the Implementation Plan. | Xoserve (LC) | Closed | The last file submitted by a Customer will be taken from their IX Servers if it is present in the import folder at 22.59.59. Customers need to ensure that they allow enough time for file(s) to be transferred successfully to their IX import folder.
0503 | 08/05/2018 | XRN4658 - Read Validation - Xoserve (DA) to send out updated slide deck published for Distribution Workgroup on 26th April with revised Gazprom numbers. | Xoserve (DA) | Closed | The slides were sent out to DSG on 08/05/2018
0504 | 08/05/2018 | XRN4658 - Read Validation - Xoserve (ES) asked the group to have a view if we can implement any sooner than a major release taking into account Gazprom's proposal and whether assumption holds within your company? Timelines. | Xoserve (ES) | Closed | To be discussed at next DSG on 21/05
0505 | 08/05/2018 | AQs of 1 - Xoserve (LW) to look at volumetrics that might support this and confirm back at the next DSG. Also look at projections after 12 months & what the 0.03% will be like then and see if any other solution options can be considered. | Xoserve (LW) | Closed | Xoserve to bring to the next DSG and discuss on 21/05. Update: 21/05 Will continue to discuss options, not a lot of interest for supporting this change. Difficult to get 0.03% unable to get that level of detail.
0506 | 08/05/2018 | XRN4576 - Class 4 Transfer Reads - Xoserve (ES) to check this change reference must reads and will get some information to show uncorrected reads. Also look at read date (read period). | Xoserve (ES) | Closed | To be dicsussed at next DSG on 21/05. Upate: 21/05 - yes we can include correct and uncorrected reads.
0507 | 08/05/2018 | Release 2 PSR Changes - Xoserve (TC) to take away how the interim delivery mechanism may work . TC to arrange something separately with BC (Centrica). | Xoserve (TC) | Closed | To be discussed at next DSG on 21/05. Update: 21/05 - change pack has gone out about creating a file format.
0508 | 21/05/2018 | End to End Change Process - Xoserve to send out link to Customer Day slides once they have been published on Xoserve.com | Xoserve | Closed | Closed - has been sent
0509 | 21/05/2018 | XRN4655 - Creation of New End User Catergories - Xoserve (ES) to check if EUC information appears on DES | Xoserve | Closed | Yes on SMPs in Shipper portfolio - Closed
0510 | 21/05/2018 | U06 Flow - last meter inspect date what is being populated - Xoserve (ES) to establish if default dates are set for U06 flow. | Xoserve | Closed | Closed
0511 | 21/05/2018 | AQs of 1 - Xoserve (ES) to bring back to next DSG meeting to discuss. | Xoserve | Closed | Closed
0512 | 21/05/2018 | XRN3667.A - DSG to look over this so hopefully we can make a decision and recommendation. | DSG | Closed | To be discussed at next DSG regarding permissions. Update 18/06 - a modification may be required regarding API. Closed
0606 | 04/06/2018 | XRN3667.A - Provision of Formula Year AQ and SOQ data: Update to be provided at the next DSG | Xoserve | Closed | Closed - Discussed today
0706 | 04/06/2018 | DSG to provide any examples of erroneous dates in the U06 | DSG | Closed | Closed
0806 | 04/06/2018 | AQ of 1: Can the slides be amended to include the release options | Xoserve | Closed | Closed - completed
0906 | 04/06/2018 | AQ of 1: CP to be raised which includes all the information given to DSG to date. | DSG | Closed | Closed - completed
1006 | 04/06/2018 | XRN4670 - Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date - to be discussed at the next DSG | Xoserve | Closed | Carried forward to 2nd July - provided on 2nd July - Closed
1206 | 18/06/2018 | Parties to confirm to uklink@xoserve.com if they wish Xoserve to monitor R2 impacted file flows submitted via IX files on Friday 26th June (inbound and outbound). Parties should provide contact details, likely submission file times/volumes by 27th June | DSG | Closed | Communication 1977 was issued on Friday 22nd June to request this information from all Users - Closed
1306 | 18/06/2018 | IDR outcomes to be communicated to the industry | Xoserve | Closed | Communication 1979 was issued on Friday 22nd June to inform parties of the successful outcomes
1406 | 18/06/2018 | GONG meeting to be set up on Wednesday 27th June. | Xoserve | Closed | Communication 1978 was issued on Friday 22nd June to inform parties of the GONG meeting
1506 | 18/06/2018 | DSG to confirm if they wish to receive optional communications by 26th June | DSG | Closed | Closed - R2 Implemented
1606 | 18/06/2018 | Xoserve to split the two tracks for Release 3 on the dashboard | Xoserve | Closed | Completed
1706 | 18/06/2018 | DA to consider aligning the changes to be implemented at the same time (UNCVR tolerance bands) | Xoserve | Closed | Completed
1806 | 18/06/2018 | DSG to consider any further solution options for XRN4676 - Reconciliation issues with reads recorded between D-1 to D-5 | DSG | Closed | Completed
1906 | 18/06/2018 | XRN4665 - Creation of new EUCs: Xoserve to notify parties of which files are changing - internal or external and if external which files. | Xoserve | Closed | Completed
2006 | 18/06/2018 | DSG to assess their portfolio of Supply Meter Points where a Convertor and AMR device is fitted and to report back what indexes they are receiving from their Service Providers. | DSG | Closed | 16/07 Discussed and closed at DSG meeting
2106 | 18/06/2018 | XRN4687 - PSR updates for Large Domestic Sites DSG to consider the change and solution options | DSG | Closed | 16/07 Change discussed at DSG – closed.
2206 | 18/06/2018 | DSG to consider effectiveness and structure of the meeting | DSG | Closed | 16/07 Discussed at DSG. On-going action 03/09 - 03/09 - Suggestions for improvement regarding action updates raised at DSG: add a target date and date of last update to the DSG Action log. Publish DSG Actions prior to each meeting. 19/11 - discussed during DSG; please review the minutes for the AOB section of this meeting 17/12 - Close as will bring up at DSG | 2018-11-19 | 2018-12-03
2306 | 18/06/2018 | DSG to consider how to receive change packs | DSG | Closed | Come with solution options 16/07 Still under review 20/08 - This went out in the August Change Pack; Action closed.
0601 | 04/06/2018 | Respond to BC regarding the process for correcting historic data following defect resolution. Inform the industry of the outcomes. | Xoserve | Closed | Closed - DJ has been discussing with BC and is undertaking a defect process review
0602/0611 | 04/06/2018 | All users to inform uklink@xoserve.com of the implementation contact for R2 | DSG | Closed | Any other parties to respond. 16/07 closed as R2 now implemented
0603 | 04/06/2018 | Seperate session to be set up with project leads for R2. Xoserve CAMs will be contacting organisations who have not submitted contact details | Xoserve | Closed | Closed - session completed at DSG 18/06
0604 | 04/06/2018 | Xoserve to verify NTS as a short code | Xoserve | Closed | Confirmed
0605 | 04/06/2018 | XRN4676 - Reconciliation issues with reads recorded between D-1 to D-5: Issue a communication to explain this scenario to allow DSG to consider any alternative solution options | Xoserve | Closed | Closed - Discussed today
0701 | 02/07/2018 | XRN4249 - Address management data load activities to be discussed at DSG on 16th July | Xoserve Lee Chambers | Closed | On the agenda for 16th July meeting 16/07 - Discussed at DSG
0702 | 02/07/2018 | The Release 3 MT approach to be issued to DSG | Xoserve Padmini Duvvuri | Closed | 16/07 - Approach to be issued later this week. 06/08 - Closed as presented at DSG on 6th August
0703 | 02/07/2018 | Option to reduce MT to be considered as a fifth option | Xoserve Padmini Duvvuri | Closed | 16/07 provided to DSG in options slides
0704 | 02/07/2018 | DSG to consider preferred options and feedback to Change Managers | DSG | Closed | 16/07 discussed at DSG, Extra ChMC on 23/7
0705 | 02/07/2018 | All documents to be saved and the sources updated if the boxes have been amended | Xoserve | Closed | 16/07 action completed
0706 | 02/07/2018 | XRN3667.A - Provision of Formula Year AQ and SOQ data, SH to assess the limitations on the API Solution | Xoserve Simon Harris | Closed | 16/07 will be bought to next DSG 06/08 - closed as presented at DSG
0707 | 02/07/2018 | SH to review the terms of service of an API solution for controls/audit. | Xoserve Simon Harris | Closed | 16/07 update at next DSG 06/08 - Closed at DSG.
0708 | 02/07/2018 | SH to confirm availability of the service | Xoserve Simon Harris | Closed | SH: Standards of service states 98% availability 06/08 - Carried forward to next DSG on 20th August. 20/08 - Action still ongoing 13/09 - Closed as its summarised by 0820
0709 | 02/07/2018 | XRN4645 Incrementing Reads on Isolated Supply Meter Points. DSG to confirm the proposed solution option is acceptable and an appropriate release date | DSG | Closed | 16/07 discussed at DSG. No comments
0710 | 02/07/2018 | XRN4621 DSG to confirm volumes of SMPs impacted and to consider solution options | DSG | Closed | 16/07 discussed at DSG, only 1 response rec’d
0711 | 02/07/.2018 | XRN4676 - Reconciliation issued with reads recorded between D-1 and D-5 - Xoserve to impact assess options 3, 4 and 5 | Xoserve | Closed | SH: Progressing with impact assessment, action ongoing 06/08 - Carried forward as further clarification required. 20/08 - Action closed as it was presented at DSG.
0712 | 02/07/2018 | Customer Advocates to discuss with Shipper User why replacement reads are being issued with the same read on the same date | Xoserve | Closed | 12/07 - List of targeted Users identified for the Customer Advocates to contact 06/08 - Closed at DSG
0713 | 02/07/2018 | XRN4670 - Reject a replacement read where the read provided is identical to that already held in UK Link for the same read date - Xoserve to impact assess the solution options | Xoserve | Closed | SH: Progressing with impact assessment, action ongoing 06/08 - Carried forward to next DSG on 20th August. 20/08 - Carry forward to next DSG. 03/09 - Carried forward to next DSG. 13/09 - Impact Assessment will return on 14/09; it'll be included in the Change Pack and Presented at DSG. 28/09 - Closed as it out for solution consultation. | 2018-09-28 | 2018-09-17
0714 | 16/07/2018 | Xoserve to provide further clarification in respect of the defects 866 & 863 listed on Slide 7 – Invoice impacting defects. | Xoserve - Emma Smith | Closed | DEFECT: 886 - Read Screen issue for FINX read DEFECT: 863 - Incorrect volume & energy following replacement read
0715 | 16/07/2018 | Xoserve to produce and issue an illustration of invoice activities and how invoices will run through Jan, Feb, March with the implementation date of Cadent Invoicing change being Feb 1st. | Xoserve - Emma S | Closed | 06/08 - Closed as presented at DSG
0716 | 16/07/2018 | Confirm impacts of 1st Feb release for XRN4454 (Cadent Billing) consider the options for next extra ChMC 23rd July | DSG | Closed | Feed comments to change managers 20/08 - Closed as it was presented at DSG.
0717 | 16/07/2018 | - XRN4621- DA to pull together details of the quantity of gas this is concerning. Who is most affected/ impacted with this and what is the potential impact. | Xoserve - Dave A | Closed | 06/08 - Closed at DSG
0719 | 16/07/2018 | XRN4687 (XRN4687 (PSR Updates for Large Domestic Sites) Xoserve will look at configurable values being an option | Xoserve | Closed | 06/08 - Carried forward to next DSG on 20th August 20/08 - Closed as it was presented at DSG.
0720 | 16/08/2018 | XRN4328 (Report of iGT meter points where the confirming shipper is not the elected shipper) - Xoserve to look to see if MPRN level detail can be automatically provided rather than to having to request this. | Xoserve - Paul O | Closed | 20/08 - Carry forward to next DSG. 14/09 - We have now implemented XRN4328 and this will be produced on a monthly basis in line with the reporting specification.
0721 | 16/07/2018 | : XRN4679 (Requiring a meter reading following a change of LDZ or EZ) - Question for DSG – are there any existing codes expected to be re-used? Or would you want a specific read reason code? | DSG | Closed | 03/09 - Carry forward to next DSG. 17/09 - A new one is required. We haven't got many reason codes to select from; OPNT is the only one appropriate for estimates. Action closed. | 2018-09-03 | 2018-09-17
0722 | 16/07/2018 | XRN4679 - Xoserve to review to see if any existing read reason codes would be suitable | Xoserve - Dave A | Closed | 06/08 - Closed at DSG
0723 | 16/07/2018 | DSG members to encourage attendance at the Release 3 customer day | DSG | Closed | 20/08 - Carry forward to next DSG. 03/09 - There are 23 attendees at the moment. Action closed.
0724 | 16/07/2018 | LW will look in ways of grouping DSG agenda items | Xoserve - Linda A | Closed | 06/08 - Work is ongoing to continue the improvement of the agenda structure. Each subject on the agenda should have an objective. 20/08 - Closed at DSG
0725 | 16/07/2018 | LW confirmed that internal PMBs take place on Thursdays & Fridays so will look to move PMB to Wednesday to get material out on Thursday. Xoserve will always endeavour to get out as soon as we can. | Xoserve - Linda | Closed | 06/08 - Closed at DSG.
0801 | 06/08/2018 | Michele Downes to identify the materiality of the incorrect AQ values, of the affected MPRNs, by defect, along with any risks, assumptions & caveats | Michelle Downes | Closed | 20/08 - Action ongoing 22/08 - Provided on 22/08. Action Closed
0802 | 06/08/2018 | AMR defect – create a plan: CR to be moved to CP and tabled at September ChMC for visibility. | Michele Downes and Emma Smith | Closed | 16/08 - On track for September ChMC. 29/08 - No update from Michele 03/09 - Action Ongoing 13/09 - Discussions are ongoing to create a plan. 17/09 - Carry forward to next DSG. 27/09 - This was an internal change only; it has therefore been closed | 2018-10-01 | 2018-09-17
0803 | 06/08/2018 | Michele Downes to provide plan defect fixing and supporting data. | Michele Downes | Closed | 20/08 - Ongoing 29/08 - No update from Michele 17/09 - Carry forward to next DSG 27/09 - This was provided at the last DSG. | 2018-10-01 | 2018-09-17
0804 | 06/08/2018 | Christina Francis to provide an update on the target date of completion for Release 2 PIS | Christina Francis | Closed | 20/08 - Closed at DSG
0805 | 06/08/2018 | DSG members to review the downstream impacts of the Release 3 changes listed on slide 20. | DSG | Closed | 03/09 - Action Ongoing 17/09 - Closed at DSG | 2018-09-03 | 2018-09-17
0806 | 06/08/2018 | DSG members to inform their respective organisations of the Release 3 Market Trials registration survey. All registrations will need to be submitted by 14th August. | DSG | Closed | 20/08 - Closed as the deadline has passed.
0807 | 06/08/2018 | Padmini Duvvuri to provide a high level view of the proposed test scenarios at the next DSG meeting. | Padmini Duvvuri | Closed | 20/08 - Closed as they were presented at DSG.
0808 |  | Padmini Duvvuri and the Release 3 technical lead to understand if Shippers will receive THICK files | Padmini Duvvuri | Closed | 20/08 - Ongoing 30/08 - THICK files (AML/ASP) are in scope for Release 3 Market Trials. | 2018-08-30
0809 | 06/08/2018 | Feedback requested from DSG on MT approach and any additional information needed | DSG | Closed | 20/08 - Still in progress. 03/09 - Closed as we're nearly in Market Trials | 2018-09-03
0810 | 06/08/2018 | Xoserve Customer Change team to review implementation dates on Change Register. | Xoserve - CCT | Closed | 16/08 -Changes in Capture don’t have an implementation date as the requirements are still being defined at this early stage. The identification of the implementation date will occur later in the project.
0812 | 06/08/2018 | XRN4621 (Suspension of the validation between Meter Index and Unconverted Converter Index) Possible Solution Options to be included the Change Pack on 10th August | Xoserve - CCT | Closed | 16/08 - This was included in the Change Pack: Change Pack reference: 2043.6 - RJ - RH
0813 | 06/08/2018 | Simon Harris to investigate the following question: what would happen if the API system is down outside of the 08:30 to 17:30 period? (3667a) | Simon Harris | Closed | 20/08 - Further action required for Simon Harris. 03/09 - Summarised by 0820.
0814 | 06/08/2018 | For XRN4679 (Requiring a meter reading following a change of LDZ or EZ), include the solution options, presented at DSG on 6th August, in the Friday 10th Change Pack. | Xoserve - CCT | Closed | 16/08 – This was included in the Change Pack: Change Pack reference: 2043.4 – RJ – RH
0815 | 06/08/2018 | Regarding 4679, David Addison (Requiring a meter reading following a change of LDZ or EZ) to consider whether an existing reason code would work. | David Addison | Closed | 20/08 - DA provided an update in the last DSG that I didn’t believe an existing Code would be specific enough. DSF agreed with this. Action Closed.
0816 | 06/08/2018 | CNC Solution Options to be included in the Change Pack in September | David Addison | Closed | 20/08 - Still awaiting approval from the IS Operations team with respect to the proposed solution (amendment to the batch timings). 03/09 - Carried forward to next DSG. 17/09 - Closed at DSG. | 2018-09-03 | 2018-09-17
0817 | 06/08/2018 | Xoserve Customer Change team to raise a Change Proposal for the CNC batch timing change. | Emma Smith | Closed | 10/08 RJ - Draft Change Proposal sent to David Addison for review. 20/08 - Drafted an internal CR for this work (which would have the same effect as desired to assign the XRN. 03/09 - Carried forward to next DSG. 17/09 - This action is still in progress. 01/10 - Action handed over to ES; ES to write a Change Proposal 10/10 - Completed | 2018-10-19 | 2018-09-17
0811 | 06/08/2018 | Update wording on 4691 Change Proposal | Xoserve | Closed
0818 | 20/08/2018 | Padmini Duvvuri to remind the 11 participants, of Release 3 Market Trials, of connectivity testing. | Xoserve - Padmini Duvvuri | Closed | 30/08 The Release 3 Project Team intend to remind the participants of connectivity testing during the Market Trials pre-meetings scheduled for 31st August. | 2018-08-30
0819 | 20/08/2018 | Lee Chambers’ team to collate the target dates, for the completion of Capture, for all Changes in scope for the June 2019 release. | Xoserve - Lee Chambers | Closed | 29/08 - Update to be provided by Catrin Morgan at DSG. However, the target dates for the completion of Capture have not been identifed yet as the changes are still progressing through Impact Asssessments. 03/09 - Timeline to be sent to ChMC next week. 13/09 - The Timeline was presented at ChMC. Action Closed. | 2018-09-03 | 2018-09-17
0820 | 20/08/2018 | Simon Harris to speak to the Xoserve Data Office to understand more about API availability. | Xoserve - Simon Harris | Closed | 28/08 - TBC 03/09 - Still waiting for information from the Xoserve Data Office. Their answers will be presented at the next DSG. 13/09 - Previous presentation material still stands. If the support hours need to be amended from 08:30 to 17:30, the support contract would have to be amended, resulting in greater cost for customers. | 2018-09-03 | 2018-09-17
0821 | 20/08/2018 | Simon Harris to present implementation timelines, for 3667a (Provision of Prospective Formula Year AQ/SOW to Proposing User); working with the project team to formalise a timeline. | Xoserve - Simon Harris | Closed | 28/08 - Carried over to the next DSG meeting; change formally handed to project team. It is awaiting implementation timelines. 13/09 - Deferred to first DSG of October. 17/09 - Timelines will be presented at the next DSG. 01/10 - Carried forward 10/10 - Carried forward 12/11 - Closed as it was presented at DSG on 5th November | 2018-11-12 | 2018-11-05
0822 | 20/08/2018 | Rachel Hinsley to raise 4713 (Actual read following estimated transfer read calculating AQ of 1) at the next ChMC for approval) | Xoserve - Rachel Hinsley | Closed | 29/08 - On hold due to impact assessment pending completion. 03/09 - Closed as it is going to ChMC. | 2018-09-03 | 2018-09-12
0823 | 20/08/2018 | Simon Harris/David Addison to evaluate the relationship of 4676 (Reconciliation issues with reads recorded between D-1 to D-5) with Smart Metering. | Xoserve – Simon Harris/David Addison | Closed | 28/08 - Carried forward to next DSG meeting. 17/09 - This issue would be worse with Smart Metering; the solution options put forward would mitigate the impact on Smart Metering. Action closed. | 2018-09-03 | 2018-09-17
0824 | 20/08/2018 | Simon Harris/David Addison to acquire clarification on the opening read process for Class 3 and 4 Meter Points (4676 (Reconciliation issues with reads recorded between D-1 to D-5) | Xoserve – Simon Harris/David Addison | Closed | 28/08 - XRN4676 relate to Class 4 sites only. Issue is not affecting Class 3 sites due to the presence of daily read profiles within SAP-ISU. | 2018-08-28
0825 | 20/08/2018 | Paul Orsler to speak to the Operational teams to confirm frequency of QCL file delivery (based on challenge raised by Shanna Key - NGN representative) | Xoserve – Paul Orsler | Closed | 30/08 - The individual that raised the Contact will receive a QCL email on any day in which a Contact that they personally raised is closed. So it may be sporadic if their closures are sporadic. 03/09 - Carried forward to next DSG. 17/09 - Action closed following the update provided above. | 2018-09-03 | 2018-09-17
0826 | 20/08/2018 | Paul Orsler to raise a Change Proposal for the amendment of the QCL file. | Xoserve – Paul Orsler | Closed | /08 - CP has been drafted and will be presented at ChMC committee on the 12th September. Pending updates following resolution of actions 0825 and 0827. 03/09 - Closed as it has been raised | 2018-09-03
0827 | 20/08/2018 | Paul Orsler to find out if the QCL file can be/is currently sent over the IX. | Xoserve – Paul Orsler | Closed | 30/08 - All parties receive the QCL files via IX. This is sent on any day in which Contacts raised by that organisation have been closed | 2018-08-30
0828 | 20/08/2018 | Regarding the IX refresh, Michael Orsler to investigate charge types. | Xoserve - Michael Orsler | Closed | 31/08 - An update isn't available at this time as Michael is not in the office 04/09 - Action closed. Michael Orsler confirmed that there is no impact on Charge types. | 2018-09-04
0829 | 20/08/2018 | DSG to assess the considerations on slide 80 of the 20th August DSG presentation pack (XRN4650 – M-Number DVD Automation). | DSG | Closed | 03/09 - Closed as it was presented at DSG. | 2018-09-03
0830 | 20/08/2018 | Simon Harris to present the slides which justify the use of Huddle for the M-Number DVD Automation service | Xoserve - Simon Harris | Closed | 28/08 - Slides to be presented at DSG 03/09 - Closed as it was presented at DSG. | 2018-09-03
0831 | 20/08/2018 | DSG to consider requirments of the Smart Metering Report (XRN4686) | DSG | Closed | 03/09 - Carried forward to next DSG. 17/09 - Closed at DSG. | 2018-09-03
0832 | 20/08/2018 | Rachel Hinsley to find out if the latest version of the Change Proposal for XRN4686 (Smart Metering Report) is on the Joint Office Website. | Xoserve - Rachel Hinsley | Closed | 29/08 - Rachel completed this action on 20/08, and sent it to JO for publishing. | 2018-08-29
0833 | 20/08/2018 | Is the S75 file as described by James Barlow a defect or a change? The S75 file contains Meter Point Status Information, when it should contain Meter Status information instead. | Xoserve - Rachel Hinsley | Closed | 30/08 - Rachel Hinsley is currently looking into this and communicating with Npower. 17/09 - Closed as it is a duplicate of 0841. | 2018-08-30
0834 | 20/08/2018 | Simon Harris to clarify if inactive read is shown on DES. | Xoserve - Simon Harris | Closed | 28/08 - TBC 04/09 - Yes, Reads received in the UMR (and subsequently set as inactive in UKL) will be displayed on DES | 2018-09-04
0835 | 03/09/2018 | Timeline to show the critical dates for the AQ Defects. Michele Downes to add this timeline to the issue register, and present it at the next DSG occurrence. | Xoserve - Michele Downes | Closed | 17/09 - Presented and closed at DSG.
0836 | 03/09/2018 | Claire Roberts (Scottish Power) asked if defect 947 is missing from the issue register. Michele Downes to find out if it is an AQ defect, and should be presented on the issue register. | Xoserve - Michele Downes | Closed | 11/09 - Michele has confirmed that 947 is in the issue register. Action closed.
0837 | 03/09/2018 | Release 3 project team to publish the results of Market Trials on Xoserve.com | Xoserve - Padmini Duvvuri | Closed | Closed on 03/09
0838 | 03/09/2018 | Release 3 project team to upload the material for the training sessions to the Release 3 page on Xoserve.com | Xoserve - Padmini Duvvuri | Closed | 03/09 - Action completed on 03/09.
0839 | 03/09/2018 | Regarding XRN4650 (M-Number DVD Automation), Ellie Rogers to clarify the security protocols with the project team | Xoserve - Ellie Rogers | Closed | 13/09 - Ellie will provide a verbal update at the meeting 17/09 - The security protocals consist of a log in and password. A Unique ID sent to a mobile user will not be available. A user guide will be completed.
0840 | 03/09/2018 | Regarding XRN4650 (M-Number DVD Automation), Ellie Rogers to find out if testing will be conducted before transition to go-live | Xoserve - Ellie Rogers | Closed | 14/09 - To confirm, we have undertaken internal testing on the M Number download capability. The file will be zipped (with password protection) and uploaded to Huddle for customers to download. The zip file will be approx. 500MB. Once downloaded and unzipped, the file(s) are just under 4GB and its contents mirror what customers receive within the DVD or USB currently. From internal testing, it took approximately 5 minutes to download the zip file from Huddle. Please note this timing is dependent on individual organisations bandwidth. If customers wish to undertake testing of this using dummy files/data then please notify the uklink@xoserve,com box account by close of play Tuesday 18th September. | 2018-10-01
0841 | 03/09/2018 | Regarding [OPERATIONAL_STATUS] Transfer Scenario Discussion, Simon Harris to identify answers to the following question: If the [Operational_Status] field is left blank, would this infer that the status of the meter point is live | Xoserve - Simon Harris | Closed | 13/09 - Deferred to the DSG Meeting on 1st October. Discussions are ongoing with Xoserve SME 28/09 - No to answer the question. As presented on the slides on 3rd Septemeber meeting, if the Operational Status field is blank, it means there is a meter is installed. This does not indicate that the Meter Point is live as it can be capped or clamped; the Operational field cannot be used to determine if its live 19/10 - Submitted for industry consultation 05/11 - Closed: change proposal will be raised | 2018-11-05
0842 | 03/09/2018 | Richard to remember this one | Xoserve - Simon Harris | Closed | 13/09 - Deferred to the DSG Meeting on 1st October. Discussions are ongoing with Xoserve SME 17/09 - Carry forward to next DSG. 28/09 - There is an existing change allow a supplier to change the date of an installation, this would not be reflective in the Operational Status field as only data populated in this field is where an asset has been removed (removal effective date). Where an installation date has been amended, and an asset is currently installed, the Operational Status field would be blank. 19/10 - Submitted for industry consultation 05/11 - Closed - Change Proposal will be raied | 2018-11-05
0843 | 03/09/2018 | Regarding the Defect Dashboard, Mark Tullet to update the Amendment Invoice Impacting Defects slide with the following additions: defect description and primary process impacted | Xoserve - Mark Tullett | Closed | 11/09 - These changes will be presented in the DSG meeting on 17/09. 17/09 - Closed at DSG.
0844 | 17/09/2018 | When defects are identified during Release 3 Market Trials, the Release 3 project team are expected to categorise the nature of the defect e.g. functional, infrastructure, etc. | Xoserve - Padmini Duvvuri | Closed | 27/09 - The Release 3 team are currently working on this; it'll be published on the Tuesday MT Reports 10/10 - 10/10 – this action has been completed in Track 1 MT and recommended for closure | 2018-10-19 | 2018-10-15
0845 | 17/09/2018 | Padmini Duvvuri to present the file level transition plan at the next DSG meeting on 1st October. | Xoserve - Padmini Duvvuri | Closed | 01/10 - Closed at DSG | 2018-10-01 | 2018-10-01
0846 | 17/09/2018 | Release 3 project team to identify any additional engagement activities to ensure file level transfer plan is confirmed by 1st October, in preparation for ChMC on 10th October. | Xoserve - Padmini Duvvuri | Closed | 01/10/18 - Carried forward 10/10 – this was presented at DSG on 17th September and approval received for Implementation plan on 2nd October at E-CHMC – recommended to close | 2018-10-19 | 2018-10-01
0848 | 17/09/2018 | DSG to find out if their organisations foresee any increase in file traffic as a result of Release 3 Implementation. | DSG | Closed | 01/10/18 - Carried forward 10/10/18 - Carried forward | 2018-11-19 | 2018-11-19
0849 | 17/09/2018 | DSG members are requested to go through the Implementation plan published and low level File level transition plan to be published shortly and feedback to box.xoserve.UKLRelease3@xoserve.com by 28th September. | DSG | Closed | 01/10/18 - Closed at DSG | 2018-10-01 | 2018-09-28
0850 | 17/09/2018 | DSG (Shippers) to identify the quantity of sites, within their portfolios, that are impacted by the issue associated with XRN4645: The rejection of incrementing read submitted for an Isolated Supply Meter Point (RGMA Flows) | Xoserve | Closed | 01/10/18 - CARRIED FORWARD TO NEXT DSG 19/11/18 - Passed back to Operations to describe scenarios. EL said that Shippers were going to receive an extract of portfolios impacted - action amended. 17/12 - moved back to Xoserve for Extracts 03/01/19 - DA has asked Ops to send report 31/01/19 - Meeting with Ops team planned for next week. 04/02/19 - Action merged with 0851 | 2019-02-04 | 2019-02-18
0851 | 17/09/2018 | David Addison to identify scenarios associated with each of the solution options associated with XRN4645: The rejection of incrementing read submitted for an Isolated Supply Meter Point (RGMA Flows). These solution options can be found on slides 30 to 31 | Xoserve - David Addison | Closed | 27/09 - This will take some time, but is in progress 12/10 - Still outstanding 05/11 - Carried forward 13/11 - Action Ongoing 03/12 - Xoserve operations team are still working on this. 03/01/19 - Ongoing 17/01/19 - DA has passed to Ops and are still working on this 31/01/19 - Meeting Ops team planned for next week 15/02/19 - Slides provided by Ops.&nbsp; DA to prepare for next DSG. 21/02 - Added to DSG on 4th march 04/03/19 - Slides need adjusting by OP's. Added to DSG on 18th March 18/04/19 - Add to DSG agenda in May 20/05/19 - Members would like scenarios 13/06/19 - Added onto the agenda for 17th June 24/06/19 - Scenarios included in slides presented on 17th June | 2019-06-13 | 2019-06-17
0852 | 17/09/2018 | Regarding XRN4725 (New Read Reason Type for LIS Estimate) David Addison to consider if we could use an existing read reason type as a solution option | Xoserve - David Addison | Closed | 27/09 - Solution option will consider this, and it has been submitted for impact assessment. Action closed | 2018-10-01 | 2018-10-01
0853 | 17/09/2018 | DSG to think of any solution options for XRN4738: Shipper Portfolio Update of Proposed Formula Year AQ/SOQ | DSG | Closed | 01/10/18 - Carried forward to next DSG 10/10/18 - Carried forward 05/11/18 - Carried forward | 2018-11-19 | 2018-11-19
1001 | 01/10/2018 | Customer Change Team to develop a consistent implementation/cutover approach to be used in future releases | Xoserve - Customer Change Team | Closed | 10/10 - Using a standard process already | 2018-10-19
1002 | 01/10/2018 | Customer Change Team to include an indication of whether there will be a functional impact on customers. | Xoserve - Customer Change Team | Closed | 05/11/2018 - Xoserve to find the context for this action. 13/11/2018 - The question was whether Xoserve should include functional impacts within Change Packs | 2018-11-19 | 2018-12-03
1003 | 01/10/2018 | find out where the AML/ASP defects are presented and report back to James Barlow (Npower) | Xoserve - Richard Johnson | Closed | 11/10/18 - Information provided to James Barlow. | 2018-10-19 | 2018-10-15
1004 | 01/10/2018 | DSG members to consider joining the JMDG (Joint MIS Development Group) | DSG | Closed |  | 2018-11-19 | 2018-11-19
1005 | 01/10/2018 | DSG members to consider solution options to Defect 838 - 838 RGMA on Transfer Date (AML Impacting), and to recommend the elimination of any known solution options they consider to be inappropriate. | DSG | Closed | 05/11/2018 - Carried forward | 2018-11-19 | 2018-11-19
1006 | 01/10/2018 | Richard Johnson and Simon Harris to consider how the Change Pack process would work using alternative mechanisms of distribution, including Huddle, SharePoint and OneDrive. | Xoserve - Richard Johnson and Xoserve | Closed | 10/10 - To be discussed at the DSG on Monday; where we suggest we remain status quo until the website is implemented in January 07/11 - Take an action to consider whether a Change Proposal may be required for this. 17/12 - Bring the look of the new website to January DSG and invite Andy Poolton. 03/01/19 - Email consultation went out. No response received. Recommend closure. | 2019-01-07 | 2019-01-07
1007 | 01/10/2018 | Xoserve to investigate how we announce the approval of a solution option to the industry following ChMC. | Xoserve - Emma Smith | Closed | 10/10 - Will provide confirmation to proposer 05/11 - Still in progress 19/11 - Regular comms or on the back of solution options being agreed 17/12 - Will send out in circular or update from ChMC meeting | 2018-12-17 | 2018-12-17
1008 | 01/10/2018 | Richard Johnson to add more information to the DSG agenda, specifically expectations for DSG to provide a recommendation | Xoserve - Richard Johnson | Closed | 11/10/18 - This is a work in progress. 18/10/18 - No feedback received on 15/10 meeting 05/11 - 05/11 - Changes to be made to how we file DSG meeting documentation following feedback from Blanka Caen and Eleanor Laurence 13/11/2018 -&nbsp; All documentation will now be on Xoserve.com; feedback will be sought at the DSG meeting on 19/11; feedback was good. 03/12 - No feedback received. | 2018-12-03
1009 | 01/10/2018 | Emma Smith to provide an update on RAASP for the next DSG | Xoserve - Emma Smith | Closed | 18/10 - Deferred due to tight timescales during the meeting on 15th October. 10/10 - Verbal on day 07/11 - Carried forward 03/12 - No update yet; No decision on the MODs. Action remains 03/01/19 - No update yet; No decision on the MODs. Action remains open 23/01 - Discussed at Mod panel and will make a decision by end of week 04/02/19 - We have received no update from Ofgem yet 18/03/19 - CP to be raised | 2019-03-18 | 2019-02-18
1010 | 01/10/2018 | Include Major Release and API timetables on future DSG agendas | Xoserve - Emma Smith | Closed | 10/10 - Major release update as part of POAP 29/10 - Replaced by 1016 | 2018-10-19
1011 | 15/10/2018 | UIG Update to be added to future DSG meetings as an agenda item | Xoserve - UIG Team | Closed | The update will be provided after the ChMC meeting. | 2018-10-29 | 2018-11-05
1012 | 15/10/2018 | Xoserve to create Release Circular documents for minor releases. | Xoserve - Customer Change Team | Closed | 05/11/ - RCs for Drop 1 and 2 have been published. 13/11/2018 - Release Circular created for June 2019; Change Packs will be added after Design 19/11/2018 - In Progress 03/12 - Xoserve have begun producing Release Circulars; therefore the action is closed. | 2018-12-03
1013 | 15/10/2018 | Minor Releases to be added to the Major Release POAP agenda item. | Xoserve - Customer Change Team | Closed | 13/11/2018 - Action in progress, and content is expected to include this 19/11/2018 - In progress 17/12 - Completed | 2018-11-19 | 2018-12-17
1014 | 15/10/2018 | David Addison and Simon Harris to investigate whether XRN4772 – Composite Weather Variables (CWV) Improvements will have an impact on AQ. | Xoserve - David Addison and Simon Harris | Closed | 05/11 - Closed at DSG meeting on 5th November | 2018-11-05 | 2018-11-05
1015 | 15/10/2018 | DSG to review the Simplified Change Register concept on slide 91 of the DSG meeting pack from 15th October 2018. | DSG | Closed | 05/11 - No comments received; action closed. | 2018-10-29 | 2018-11-19
1016 | 15/10/2018 | Shipper attendees at DSG to consider a limit per file for the UPD File – Please refer to 12c Irrelevant Datasets for Onjob of the 15th October DSG meeting. | DSG (Shippers Only) | Closed | 05/11 - Carried forward 19/11 - Closed as its gone through Change Pack | 2018-11-19 | 2018-11-19
1101 | 05/11/2018 | David Addison to provide an update on the CNC Batch Timings Change to Eleanor Laurence; EL wanted to know when the change will be implemented. | Xoserve - David Addison | Closed | 13/11/2018 - This is an agenda item on the agenda (agenda item 10b.) | 2018-11-19 | 2018-11-19
1102 | 05/11/2018 | Padmini Duvvuri to present a plan for the delivery of XRN4534 at the DSG meeting on 19th November. | Xoserve - Padmini Duvvuri | Closed | 13/11/2018 - This will be presented on 3rd December instead 03/01 - Update given | 2018-11-19 | 2018-12-03
1103 | 05/11/2018 | DSG to review the high level solution options associated with XRN4753 (Increase Information provided in .QCL Response File). | DSG | Closed | 19/11/2018 - ongoing | 2018-12-17 | 2018-12-03
1104 | 05/11/2018 | In relation to XRN4780 (Inclusion of Meter Asset Provider in the UK Link System – CSS Consequential Change), David Addison to find out how IGT MAP id flows would be mandated. | Xoserve - David Addison | Closed | 13/11/2018 - Action is in progress 19/11/2018 - carried forward 03/12 - Dave Addison is waiting for review comments from the iGTs about how they will mandate MAP IDs. 03/01/19 - Ongoing 17/01/19 - Ongoing communication between DA and IGT's. 31/01/19 - Still in conversation with IGTs 15/02/19 - IGT's recognise that they need to provide MAP id and no objections raised when flagged by them. | 2019-01-31 | 2019-03-04
1105 | 05/11/2018 | In relation to XRN4780 (Inclusion of Meter Asset Provider in the UK Link System – CSS Consequential Change), DSG to review the requirements and to support Xoserve in the development of solution options. | DSG | Closed | 19/11/2018 - Closed as it'll be covered in CSS | 2018-11-19 | 2018-11-19
1106 | 05/11/2018 | Linda Whitcroft to look into how detailed investigation regarding Xoserve defects can be facilitated at DSG or a new forum. | Xoserve - Linda Whitcroft | Closed |  | 2018-12-17
1107 | 05/11/2018 | Simon Harris to write a Change Proposal for the Operational Status Issue. James Barlow from Npower has agreed to sponsor the change. | Xoserve - Simon Harris | Closed | 13/11/2018 - In progress with proposal and sponsor 03/12 - Simon has drafted the CP, and will send it to James Barlow for his review. 03/01/19 - Completed | 2019-01-07 | 2018-12-03
1108 | 05/11/2018 | Simon Harris to include MIS related Releases, including XRNs, within the Change POAP section for DSG meetings. | Xoserve - Simon Harris | Closed | 13/11/2018 - This will be presented at the DSG meeting on 19th November 19/11/2018 - Carried forward 03/12/2018 - In progress, and we expect this to be presented at the next DSG. | 2018-12-17 | 2018-12-17
1109 | 05/11/2018 | Simon Harris to indicate individual use cases on the JMDG Overview agenda item for DSG. | Xoserve - Simon Harris | Closed | 13/11/2018 - This will be presented at the DSG meeting on 19th November, but can DSG members consider if the electricity slides are not needed? | 2018-11-19 | 2018-11-19
1110 | 05/11/2018 | DSG to review the solution options for the provision of Class 1 Meter Readings by Shipper Users | DSG | Closed |  | 2018-11-19 | 2018-11-19
1111 | 19/11/2018 | Xoserve Customer Change Team and CIO Office to create a POAP for DSG which includes changes from all delivery platforms | Xoserve - CIO Office and Customer Change Team | Closed | 03/12 - Presented for the first time. DSG wanted to see a glossary, and an implmentation milestones. Action therefore completed as it this agenda item will reoccur at each DSG. | 2018-12-03 | 2018-12-03
1112 | 19/11/2018 | Richard Johnson or Julie Bretherton to provide Swetta Coopamah from Centrica with a contact for the external Change Register. | Xoserve - Richard Johnson / Julie Bretherton | Closed |  | 2018-12-17 | 2018-12-03
1113 | 19/11/2018 | DSG to support Xoserve with the development of requirements for XRN4790 (Introduction of winter read consumption reports and associated obligation). | DSG | Closed | 03/12 - Closed as this action was replaced by 1123. | 2018-12-03 | 2018-12-03
1114 | 19/11/2018 | DSG to support Xoserve with the development of requirements for XRN4801 – Additional Information to be made available on DES. | DSG | Closed | 03/12 - Closed as additional requirements were provided via the initial review change pack process. | 2018-12-03 | 2018-12-03
1115 | 19/11/2018 | DSG to support Xoserve with the development of requirements for XRN4789 Updating Shipper Reporting Packs | DSG | Closed | 03/12 - Closed as additional requirements were provided via the initial review change pack process. | 2018-12-03 | 2018-12-03
1116 | 19/11/2018 | DSG to support Xoserve with the development of requirements for XRN4806 - Additional data at National Level to support UIG Allocation validation. | DSG | Closed |  | 2018-12-17 | 2018-12-03
1117 | 19/11/2018 | Xoserve to work with the Change Proposer (Npower), to refine requirements and bring these back to DSG for discussion. | DSG | Closed | 03/12 - Closed as this is a duplicate of 1118. | 2018-12-03 | 2018-12-03
1118 | 19/11/2018 | Paul Orsler and Npower to meet to discuss requirements and solutions for XRN4747 – Smart Meter Upgrade Notification Report | Paul Orsler from Xoserve and James Barlow from Npower | Closed | 29/11 - Action Ongoing 03/01/19 - Discussed and closed at DSG meeting on 17th December as confirmed that this change progressing as a Commercial Service. | 2019-01-07 | 2019-01-07
1119 | 19/11/2018 | David Addison to write a Change Pack for the solution options associated with MOD647 Provision of Class 1 Meter Reading by Shipper Users | Xoserve - David Addison | Closed | 29/11 - Action Ongoing | 2018-12-17 | 2018-12-14
1120 | 03/12/2018 | DSG to view the New Xoserve.com slide on the presentation pack and provide any comments to contactxoserve@xoserve.com | DSG | Closed |  | 2019-01-07 | 2018-12-17
1121 | 03/12/2018 | Xoserve to clarify the approval process for Design Change Packs at ChMC. | Xoserve - Emma Smith | Closed | 03/01/19 - Completed. Update given at December ChMC | 2019-01-07 | 2019-01-07
1122 | 03/12/2018 | David Addison to write a Change Pack for 11b. UNC Validation Rules amendment to round the clock derivation | Xoserve - David Addison | Closed | 17/12 - Carried Forward 20/12 - Completed and went out 14/12/18 | 2019-01-07 | 2019-01-07
1123 | 03/12/2018 | Regarding agenda item 13a. XRN4790 (Introduction of winter read consumption reports and associated obligation), DSG to consider any additioanl Data Items they would like to see in the reports. | DSG | Closed |  | 2018-12-17 | 2018-12-17
1124 | 03/12/2018 | Regarding agenda item 13c. XRN4634 – Xoserve Data Catalogue, David Addison to write a Change Pack. | Xoserve - David Addison | Closed |  | 2018-12-17 | 2018-12-17
1201 | 17/12/2018 | Create a seperate line on the R&N DeliveryTimeline for CSS Consequential | Xoserve - Richard Hadfield | Closed | 02/01/19 - Completed. Added into slides for January meeting | 2019-01-07 | 2019-01-07
1202 | 17/12/2018 | Indicate in another colour where milestones completed on R&N Governance slide and on the Portfolio POAP. | Xoserve - Richard Hadfield | Closed | 02/01/19 - Completed for R&N governance Slide- January meeting.&nbsp; Need to update on Portfolio POAP. 17/01/19 - Debi Jones to investigate how best to gather the data and display this. | 2019-01-17 | 2019-02-18
1203 | 17/12/2018 | XRN4789 – Updating Shipper Reporting Pack - DSG shipper representatives to review the existing Shipper reporting packs against the Change Proposal requirements and forward any feedback or additional requirements to uklink@xoserve.com | DSG | Closed | 07/03/19 - Action description updated to be more specific. | 2019-01-07 | 2019-01-21
1204 | 17/12/2018 | XRN4801 – Which requested data items should be higher priority? Can any proposed data items be de-scoped?What considerations or system impacts do you foresee as a result of these data items to be added to DES? Is DSG in support of additional requirements? | DSG | Closed | 07/03/19 - Action description updated to be more specific. 04/02/2019 -We have asked the individuals within the industry, who asked for additional data item to be included in DES during the initial change pack process, to provide justification for the data items they requested. We're currently working on prioritisation for each data item 18/02/19 - 2 additional questions added for DSG members. Propose to close after next meeting | 2019-02-18 | 2019-03-04
1205 | 17/12/2018 | XRN4686 Smart Metering Report Decision needed In what location would DSG prefer this report to be published monthly | DSG | Closed |  | 2018-12-17 | 2019-01-21
1206 | 17/12/2018 | XRN4665 - New End User Categories decision on REC Variance Code | DSG | Closed | 18/12 - Due to the urgency of response needed a separate communication went out on 18/12 | 2019-01-07 | 2018-12-20
1207 | 17/12/2018 | Xoserve to supply James Barlow with details of defect 1161 | Xoserve | Closed | 03/01/19 - Completed. Email forward onto James barlow from Mark Tullet | 2019-01-07 | 2019-01-07
0101 | 07/01/2019 | XRN4803 - Removal of validation for AQ Correction Reason 4 - DSG to make a decision on what option to use and any feedback | DSG | Closed | 04/02/19 - Discussed at the DSG meeting on 4th February, and therefore this action was closed. ChMC will be asked next week to approve our approach to proceed this to Design Change Pack. | 2019-02-04 | 2019-01-21
0102 | 07/01/2019 | Simon to find out more information regarding the CSEP logic and if there are any risks associated with the proposals. | Xoserve - Simon Harris | Closed |  | 2019-01-07 | 2019-01-21
0103 | 07/01/2019 | Simon to speak with DA to ensure this scenario has been fed into the RTC work | Xoserve - Simon Harris | Closed |  | 2019-01-07 | 2019-01-21
0104 | 07/01/2019 | Simon to look at renaming the title as this is not consistent with the change | Xoserve - Simon Harris | Closed |  | 2019-01-07 | 2019-01-21
0105 | 07/01/2019 | LW to look at the internal process of how changes are documented and kept up to date. | Xoserve - Linda Whitcroft | Closed |  | 2019-01-07 | 2019-02-04
19 - 0106 | 07/01/2019 | Have an extraordinary DSG meeting to discuss the website a couple of months after go live. | Xoserve - Rachel Taggart | Closed | 04/02/19 - DSG attendees said they were pleased with the new website. 04/03/19 - Propose a date in April 14/03/19 - Extraordinary DSG not needed and will add to next DSG meeting on 1st April. | 2019-03-14 | 2019-03-18
19 - 0107 | 21/01/19 | Emma Smith to look into the Prioritisation Scoring for XRN4833 to include Personal Data. | Xoserve - Emma Smith | Closed | 04/02/19 - Closed; the Prioritisation Scoring has been updated. | 2019-02-04
19 - 0108 | 21/01/2019 | XRN4777 - DSG to review the Change Pack which requests the Industry support for the decision to go into a Minor Release. | DSG | Closed | 04/02/19 - Closed; this will be presented at ChMC in February for approval of a solution option. | 2019-02-04
19 - 0109 | 21/01/2019 | Gain more information as to what data will be shown in the new Business Intelligence Tool. This may evolve into Capture. | Xoserve - Jane Goodes | Closed | 31/01/19: Jane is looking to raise a new Change proposal to rationalise all reports.14/02/19 - On hold pending the reporting review with Data. Linked to XRN4857. 28/02/19 - Jane to speak with Jason McLeod 04/04/19 - Verbal update given.&nbsp; Will add onto Agenda when required. 07/05/19 - Closed at DSG as will bring and options to DSG in the future. | 2019-04-07 | 2019-05-20
19 - 0110 | 21/01/2019 | Business Intelligence Tool - How feasible it is to have Individual logins at the start. Also to look on how Individual logins can be allocated different access permissions. | Xoserve - Jonathan Heard | Closed | 04/02/19 - In progress; we believe individual logins are possible but will check with the Xoserve data office. 14/02/19 - Update for DSG on 18th Feb | 2019-02-14
19 - 0111 | 21/01/2019 | XRN4801 - Updatethe slides relating to rational to then move forward with what responses received into formal capture. | Xoservre - Simon Harris | Closed | 31/01/19 - Completed | 2019-01-31
19 - 0112 | 21/01/2019 | XRN4801 - Engage this week with individuals who responded to the Change Pack concerning the rationale behind the additional data items. | Xoserve - Simon Harris | Closed | 31/01/19 - Completed | 2019-01-31
19 - 0113 | 21/01/2019 | Paul Orsler to write to DSG members who wanted another solution on XRN4753 to advise them to raise a CP if this was still needed. | Xoserve - Paul Orsler | Closed | 31/01/19 - Completed | 2019-01-31 | 2019-02-04
19 - 0201 | 04/02/2019 | Find out when CSSC will be presented at DSG again following the completion of the extraordinary meetings. | xoserve - Richard Johnson | Closed | 15/02/18 - Update to be included at DSG meeting on 4th March 04/03/19 - Completed | 2019-03-04
19 - 0202 | 04/02/2019 | Regarding XRN 4713 (Actual Read Following Estimated Transfer Read Calculating AQ of 1 Enduring Solution), DSG members to consider the solution options on slide 28 and report back at the next DSG meeting | DSG | Closed | 18/02/19 - DSG agreed to proceed with option 3. | 2019-02-18
19 - 0203 | 04/02/2019 | Xoserve to provide an update regarding the Shipper Reporting Packs at the next DSG meeting. | Xoserve - Jane Goodes | Closed | 14/02/19 - Update for DSG on 18th Feb with solution options. Propose to close | 2019-02-14
19 - 0204 | 04/02/2019 | Xoserve to find out the CSSC impacts on Gemini and report back to the next DSG meeting | Xoserve - David Addison | Closed | 15/02/19 - DA will update within DSG meeting on 18th Feb 04/03/19 - Completed | 2019-03-04
19 - 0205 | 18/02/2019 | Clarify if changes relating to GB charging will continue (EUC change may affect) | Xoserve - Emma Smith | Closed | 28/02/19 - Work will continue at Risk unless told otherwise. 04/03/19 - Completed | 2019-03-04 | 2019-03-04
19 - 0206 | 18/02/2019 | Clarify what Ofgem DCC change on the Portfolio POAP is. | Xoserve - Debi Jones | Closed | 15/03/19 - DCC is Data Communication Company. This is being looked at to see if it should be on the POAP.&nbsp; 18/03/19 - Still need to understand what the change is. 15/04/19 - Change owner to Debi Jones | 2019-03-18 | 2019-03-04
19 - 0207 | 18/02/2019 | On the R&N unallocated changes slide change the word 'Proposed' to 'Indicative' R&N release and add in dates. | Xoserve - Julie Bretherton | Closed | 04/03/19 - Completed | 2019-02-04 | 2019-03-04
19 - 0208 | 18/02/2019 | Change's to CR XRN4853 - Change from All market participants to multiple and all more to the description. Change's to CR XRN4853 - Change from All market participants to multiple | Xoserve - Emma smith | Closed | 04/03/19 - Completed | 2019-03-04 | 2019-03-04
19 - 0209 | 18/02/2019 | DSG to review XRN4853 and feedback if impacted where a read has been rejected and include in the reps for Change Pack dated 15th February. | DSG | Closed | 28/02/19 - Change Pack due to close on 1st March. Propose to close. 04/03/19 - Completed | 2019-03-04
19 - 0210 | 18/02/2019 | XRN4738 - Review the slides presented at DSG (18th Feb) and provide input into proposed solution, include additional/redundant data items. | DSG | Closed | 04/03/19 - Completed | 2019-03-04 | 2019-03-04
19 - 0211 | 18/02/2019 | Confirm the licence arrangement in regards to the shipper short codes and how the access per individual works. | Xoserve - Jason McLeod | Closed | 28/03/19 - Verbal update on DSG agenda on 01/04 - Propose to close 01/04/19 - license arrangements not covered. Keep open. | 2019-02-18
19 - 0212 | 18/02/2019 | Agenda item 10b. Reconciliation following a Site Visit Read (Check Read) over the period of a Class Change. DSG members to consider the options on slide and report back at the next DSG meeting | DSG | Closed | 04/03/19 - Completed | 2019-03-04 | 2019-03-04
19 - 0213 | 18/02/2019 | Contact Kirsty to gather requirements for XRN4789 Part B to add into the new XRN raised with Data. | Xoserve - Jane Goodes | Closed | 28/02/19 - Waiting for Kirsty to give her views on the requirements. 14/03/19 - Kirsty confirmed happy. Propose to close. | 2019-03-14 | 2019-03-04
19 - 0214 | 18/02/2019 | DSG to review slides linked to Action Ref: 0407 and consider if this is a priority and if not can this be put on hold. Feedback to be given at the next meeting. | DSG | Closed | 04/03/19 - Completed | 2019-02-04 | 2019-03-04
19 - 0215 | 18/02/2019 | Give a Website update at next meeting on Change Packs and Mail Chimp. | Xoserve - Richard Johnson | Closed | 14/03/19 - Will be presented on 1st April. | 2019-03-14 | 2019-03-04
19 - 0216 | 18/02/2019 | DSG to review the slides for XRN4867 & XRN4868 and feedback any items missing by COP on 22/02/19 | DSG | Closed | 04/03/19 - Completed | 2019-03-04 | 2019-02-22
19 - 0217 | 18/02/2019 | create a timeline with reports for XRN4790 | Xoserve - Emma smith | Closed | 28/02/19 - Completed and will go the DSG on 4th March | 2019-03-04 | 2019-03-04
19 - 0301 | 04/03/2019 | Create an extraordinary Change Pack with Xoserve's recommended solution for Defect -Reconciliation following a Site Visit Read (Check Read) over the period of a Class Change. | Xoserve - Michele Downes | Closed | 18/03/19 - Was included in the Change Pack on 15th March. | 2019-03-18
19 - 0302 | 04/03/2019 | Can allocated Change on the R&N slides be put in Release order. | Xoserve - Julie Bretherton | Closed | 15/03/19 - Completed. Propose to close | 2019-03-15
19 - 0303 | 04/03/2019 | Can DSG review the Glossary format and give feedback for next meeting. Related to XRN4789 - Updating Shipper Reporting Packs and glossary | DSG | Closed |  | 2019-03-04
19 - 0304 | 04/03/2019 | Send out the Guidance Document for MOD0682 | Xoserve - David Addison | Closed | 15/03/19 - Added to documentation on DSG web page 4th March. Propose to close | 2019-03-15
19 - 0305 | 18/03/19 | Change MOD0661 to MOD0678 on the R&N timeline | Xoserve - Richard Hadfiels | Closed | 28/03/19 - Slide updated. Propose to close | 2019-03-28
19 - 0306 | 18/03/19 | DSG to respond to the Extraordinary Change Pack for RN4871 - Modification 0665 – Changes to Ratchet Regime | DSG | Closed | 28/03/19 - Change Pack closed out. Propose to close | 2019-03-28
19 - 0307 | 18/03/19 | Look at how the prioritisation scoring is calculated and whether it needs amending. | Xoserve - Paul Orsler | Closed | 28/03/19 - We are undergoing a cleansing exercise in readiness for the new PPM tool and this will feed into that piece of work. The Govenance Sub Group starting in May have also flagged this as an agenda item. Propose to close. | 2019-03-28
19 - 0308 | 18/03/19 | XRN4803 - Get clarification if only removing for scenario or all validations. Needed for the next DSG before going to ChMC. | Xoserve - Emma Smith | Closed | 28/03/19 - Added to DSG agenda on 1st April - Propose to close | 2019-03-28
19 - 0309 | 18/03/19 | Add XRN4833 – Business Intelligence Tool to the next DSG agenda. | Xoserve - Jason McLeod | Closed | 28/03/19 - Verbal update on 1st April.- propose to close | 2019-03-28
19 - 0310 | 18/03/2019 | Data Office to produce a Delivery Timeline POAP and feed into the Portfolio Delivery Overview Agenda Item at DSG | Xoserve - Rebecca Roden | Closed | 28/03/19 - Meeting with Data team on 28/03 and may have a POAP fro DSG on 01/04. | 2019-03-28
19 - 0401 | 01/04/2019 | XRN4780 - To find out what codes the Map ID will use and how will it be communicated to the Industry | Xoserve - Simon Harris | Closed | 20/05/19 - RT to chase Simon for an answer | 2019-05-20 | 2019-06-03
19 - 0402 | 01/04/2019 | To get a timeline for when Cloud based system will come into business | Xoserve - Richard Hadfield | Closed | 02/05/19 - Cloud is still only on the Roadmap at the moment. We don’t have any dates proposed or otherwise 07/05/19 - DSG agreed to close
19 - 0403 | 01/04/2019 | XRN4803 - Update the Change Proposal, relating paperwork and title to reflect the removal of validation isn't limited to Reason code 4 | Xoserve - Emma Smith | Closed | 18/04/19 - Completed and uploaded onto the Website
19 - 0404 | 01/04/2019 | On the JMDG Roadmap slide the UKRPA Access to Gas data needs to be changed to amber. | Xoserve - Simon Harris | Closed
19 - 0405 | 15/04/2019 | Highlight CSS changes within the Retail & Network slides, so DSG can identify them easily. | Xoserve - Julie Bretherton | Closed | 07/05/19 - still to be highlighted in the R&N slides. | 2019-05-20
19 - 0406 | 15/04/2019 | Colour code changes on the change index slides. | Xoserve - Julie Bretherton | Closed | 02/05/19 - All Changes within R&N Change Log are now colour coded - Close
19 - 0407 | 15/04/2019 | ook at AML defects in regards to EUC Release | Xoserve - Matt Rider | Closed | 02/05/19 - The EUC release are not making any changes to or looking at AML. Tata Consultancy Services delivery lead has confirmed that, of existing production defects this has been checked and there are no AML defects impacting our EUC release. - Close
19 - 0408 | 15/04/2019 | Update slides to add implementation dates for MiR 4 and June 20 | Xoserve - Bali Bashir / Tara Ross | Closed | 02/05/19 - Implementation dates have been updated in the slide - Close
19 - 0409 | 15/04/2019 | Add to next DSG for score ratification and Reps discussion | Xoserve - Rachel Taggart | Closed | 29/04/19 - Added to the agenda. Propose to close
19 - 0410 | 15/04/2019 | DSG to bring recommendation if Shippers/Suppliers benefit from receiving this detail and transfer of RGMA flows | DSG | Closed |  | 2019-05-20
19 - 0411 | 15/04/2019 | Speak with CSS team and see consultation period for CSS Change Packs can be extended and Pack resent out | Xoserve - Richard Johnson | Closed | 23/04/19: RJ and the CSS team concluded that if the consultation period was extended, we may miss approval of the BRDs in May’s meeting. To seek approval in June’s meeting wouldn’t be feasible as the CSS team intend to start the Build stage in June. Propose to close
19 - 0412 | 15/04/2019 | Identify any improvements to the search function on the website home page to search for Change Proposals. | Xoserve - Chan Singh | Closed | 02/05/19 - Meet with website development manager by end of this week. 07/05/19 - This is now being worked on. 20/04/19 - Raised with Origin. Will get an indicative date | 2019-05-20 | 2019-06-03
19 - 0501 | 07/05/2019 | Add a colour key on the R&N unallocated External change slide | Xoserve - Richard Hadfield | Closed | 20/05/19 - Completed | 2019-05-20 | 2019-06-17
19 - 0502 | 07/05/2019 | Put CSSC indicator on XRNs related to CSSC. Speak with Portfolio Governance Team | Xoserve - Richard Hadfield | Closed | 01/07/19 - Paul Provided DSG an update that all CSS Changes will be prefixed in the title. 01/08/19 - Our current database is restricting us from inclusing the CSSC indicator, however this is being explicitly called out on various slide packs and Industry communications. | 2019-08-01 | 2019-08-19
19 - 0503 | 07/05/2019 | Present the outputs of the KPMG report at mid-June DSG | Xoserve - Jane Goodes | Closed | 13/06/19 - KPMG report not yet available 17/06/19 - Outputs/Timings/Cost to be presented at DSG on 15th July 17/06/19 - Outputs/Timings/Cost to be presented at DSG on 15th July | 2019-06-13 | 2019-07-15
19 - 0504 | 07/05/2019 | DSG to feedback views that they can cope with Change and timescales in regards to CSSC, to help create a delivery plan | DSG | Closed | 20/05/19 - Parties not raised concerns and will monitor change demand
19 - 0505 | 20/05/2019 | Add Minor Release Drop 5 update onto DSG agenda | Xoserve - Richard Hadfield | Closed |  |  | 2019-06-03
19 - 0506 | 20/05/2019 | What is the trigger for the Link Code to change and how do we notify customers (RE: XRN4930) | Xoserve - Simon Harris | Closed | 30/05/19 - Simon is hoping to get the answer for 3rd June DSG 17/06/19 - Completed |  | 2019-06-03
19 - 0507 | 20/05/2019 | How many files to date, have been affected (RE: XRN4931). Check which files have been affected and who is submitting theses. | Xoserve - Simon Harris | Closed | 30/05/19 - Investigating and will update on 17/06/19 - Completed |  | 2019-06-03
19 - 0508 | 20/05/2019 | What was the rationale of running the MDN data mid-month and implications of moving it for Winter Consumption Calc. | Xoserve - Paul Orsler | Closed | Assume this is associated to the running of the winter consumption job mid month? If so the job is scheduled to co-inside with the AQ calc job, in order the informaiton is notifified in the AQ files. The job would be required to move to June each year if it was felt the right solution to account for the 20 business day close out on class 4 reads |  | 2019-06-03
19 - 0509 | 20/05/2019 | Bring KVI survey responses to next DSG meeting | Xoserve - Rachel Taggart | Closed | 30/05/2019 - Will update DSG after ChMC meeting 13/06/19 - Added onto agenda for 17th June | 2019-06-13 | 2019-06-03
19 - 0601 | 03/06/2019 | Will IGT's/GT's want to receive MAP ID? | BUUK - John Cooper | Closed | 17/06/19 - Completed
19 - 0602 | 03/06/2019 | Regarding XRN4857 Report Review, Xoserve to provide an update for DSG in early July | Xoserve - Jane Goodes | Closed | 13/06/19 - Added to agenda on 17th June | 2019-06-13 | 2019-06-17
19 - 0603 | 03/06/2019 | Xoserve to confirm to EDF whether the JMDG group is still running | Xoserve - Simon Harris | Closed | 17/06/19 - The next meeting is in July
19 - 0604 | 17/06/2019 | Bring the questions and answers asked within the Detailed Design change pack for November 19 Release to the next DSG meeting. | Xoserve - Tom Lineham | Closed | 01/07/19 - Questions and answers have been provided in the DSG Slide Pack for 1st July 2019 Meeting. Tom Lineham to circulate assumptions. | 2019-07-01 | 2019-07-15
19 - 0605 | 17/06/2019 | Confirm whether Shippers receive the conversion factor in SPA files and provide guidance in how Shipper can identify if a site has a meter currently working in conversion mode. | Xoserve - Simon Harris | Closed | 06/09/2019 - The Conversion Factor (Correction Factor in files) is provided to the incoming Shipper within the S75 record. The S75 record is sent within the Nomination Response (NMR/NRF), Confirmation Response (CFR) and the Transfer of Ownership file. We also provide the value in the Meter Read Instructions (MRI) file. Proposing to close this action in meeting on 16th September. |  | 2019-07-15
19 - 0606 | 17/06/2019 | To raise at SPAA - Confirm the release and implementation date of gas industry compared to electricity (XRN4955) | Xoserve - Paul Orsler/ Ellie Rogers | Closed | 01/07/19 - Paul has reassigned this action for himself and Ellie Rogers to address. 01/08/19 - The alignment of implementation dates will be considered within the REC. Action Closed | 2019-08-01 | 2019-08-19
19 - 0607 | 17/06/2019 | DSG to consider what information would need to be available to Users in order to support their processes and submit adjustments. | DSG | Closed | 01/07/2019 - CDSP to provide the Shippers with the number of MPRN’s in relation to the consumptions being adjusted and share the meter points in their portfolios where there has been an exception. 19/08/2019 - MPRNs have been shared. Action closed in meeting | 2019-08-19
19 - 0608 | 17/06/2019 | Add XRN4850 to DSG on 1st July so DSG members get a view, discuss and agree on the recommended option. |  | Closed | 01/07/19 - This was discussed at DSG meeting 1st July, where this was agreed to be sent via a Change Pack to seek industry views. 15/07/19 - Presented Options and Change Pack sent out | 2019-07-01 | 2019-07-15
19 - 0701 | 7/01/2019 | In regards to XRN4621 - DSG to provide a response regarding the whether they want the CDSP to show the unconverted as the inconsistency can be misleading. | DSG | Closed | 15/07/19 - Presented to DSG and Change Pack sent out | 2019-07-01 | 2019-07-15
19 - 0702 | 7/01/2019 | In regards to XRN4621 - What are DSG planning to do in regards to reporting. Comm Ref 2364 went out to for feedback to be discussed at DSG on 15/07/19 | DSG | Closed | 02/07/19 - Comm 2364&nbsp; – RJ – PO - For Action: Industry Consideration Required on Requirements for XRN4621 sent out. 15/07/19 - Presented to DSG and Change Pack sent out | 2019-07-01 | 2019-07-15
19 - 0703 | 7/01/2019 | DSG members to provide a view on the CDSP raising a Change to amend the timescale of the winter read consumption. | DSG | Closed | 15/07/19 - No views have been received and DSG members agreed to close. If needed in future then will be raised. | 2019-07-01 | 2019-07-15
19 - 0704 | 15/07/2019 | DSG to provide a response for approval of Proof of Concept function requirements presented and non – functional requirements - relating to XRN4914 MOD 0651 Retrospective Data Update Provision | DSG | Closed | 09/08/2019 - Proposing to close this action as the POC excersise is voluntary for Shippers and Xoserve will be working in an agile way to collaboratively deliver a solution and outputs 19/08/2019 - Closed in meeting | 2019-08-19
19 - 0705 | 05/08/2019 | CDSP to share the Industry wide migration plans for the large scale utilisation of Class 3 | Xoserve | Closed | 09/08/2019 - CDSP can confirm that the Industry Wide Migration plan will be created/shared as part of the development of the CP 02/09/2019 - We are currently in the process of collating the plan for migration. 03/10/2019 - JB to provide a verbal update |  | 2019-10-07
19 - 0706 | 19/08/2019 | DSG to take away the information presented at latest DSG meeting in relation to XRN4980 (Change Supply Point Enquiry API to add in extra fields and make certain other fields visible) and assess if there are any other additional data items that would be of benefit to be added to the S.P.E API to aid in business processes and promote more reliable switching. | DSG | Closed | 02/09/2019 - We did not formally receive any data items to be fed into the development of this CP. Decision was taken to close this action and continue with the proposer's requirements. |  | 2019-09-02
19 - 0707 | 19/08/2019 | Xoserve to update XRN4980 CP appendix by including the Customer switching option element, and to clarify and outline which service area relates to this Change (Currently this is service area 1 but clarity is needed as to whether Service Area 22 is better suited) | Xoserve | Closed | 03/10/2019 - This has been updated on the CP and xoserve.com |  | 2019-10-07
19 - 0708 | 19/08/2019 | Xoserve to update XRN4991 Appendix to show the number of impacted service areas from two to five, and the number of primary impacted applications as currently only BW, ISU and AMT are selected. | Xoserve | Closed | 03/10/2019 - This has been updated on the CP and xoserve.com |  | 2019-10-07
19 - 0709 | 19/08/2019 | In relation to the EUC File format description amendments, Xoserve to clarify within the text the amendments to the descriptions - DSG to confirm if they believe these description amendments are required. | Xoserve / DSG | Closed | 02/09/2019 - A change pack will be issued asking for views on the method of making amendments to the EUC descriptions and whether these amendments will go ahead that will be issued in the September change pack. Proposing to close action from a DSG perspective. |  | 2019-10-07
19 - 0710 | 19/08/2019 | Class 3 FAQ page to be created. | Xoserve | Closed | 02/09/2019 - FAQ page has now been created, action can be closed. |  | 2019-09-02
19 - 0710 | 16/09/2019 | In relation to XRN4896, the primary impacted DSC service area listed in Appendix 1 is service area 16, this does not align to the aforementioned service area 7 within A6 (Service Lines and Funding) of the change proposal. | Xoserve | Closed | 03/10/2019 - This has been updated on the CP and xoserve.com |  | 2019-10-07
19 - 0711 | 16/09/2019 | In relation to XRN4896 PO raised an action on behalf of SH to add in Shipper impact within the known impact systems and processes section. | Xoserve | Closed | 03/10/2019 - This has been updated on the CP and xoserve.com |  | 2019-10-07
19 - 0712 | 16/09/2019 | In relation to XRN4923, ensure section A6 (Service Lines and Funding) are populated. | Xoserve | Closed | 03/10/2019 - This has been updated on the CP and xoserve.com |  | 2019-10-07
19 - 0713 | 07/10/2019 | DSG to review which changes of the June 2020 release would require testing market trials. | DSG | Closed |  |  | 2019-10-21
19 - 0714 | 07/10/2019 | Confirm the considerations have been of AML/ASP relating to potential regression impacts on AML/ASP in regards to MOD700 | Xoserve | Closed | 18/11/2019 - DSG - Xoserve have confirmed this has been actioned, now closed |  | 2019-10-21
19 - 0715 | 07/10/2019 | DSG to review the design considerations for XRN4932 and provide steer and recommendations for each at the next DSG meeting 21st October 2019. | DSG | Closed |  |  | 2019-10-21
19 - 0716 | 16/09/2019 | Xoserve to review whether any other forms of estimated reads may exist that are not included within the AQ calculation process. If so these should also be considered as part of this change. | Xoserve | Closed |  |  | 2019-10-21
19 - 0717 | 21/10/2019 | DSG to review the slides and confirm the report is still required in regard to XRN4738 | DSG | Closed | 04/11/2019 - DSG confirmed the report is still needed |  | 2019-11-04
19 - 0718 | 21/10/2019 | DSG to confirm the above data items will meet customer requirements in regard to XRN4738 | DSG | Closed | 04/11/2019 - DSG confirmed the data items are needed and will meet the requirements of the change |  | 2019-11-04
19 - 0719 | 21/10/2019 | DSG to confirm the requirements discussed are still needed in regards to XRn4738 proposed data items. | DSG | Closed | 04/11/2019 - DSG confirmed the data items are needed and will meet the requirements of the change |  | 2019-11-04
19 - 0720 | 21/10/2019 | In regards to XRN4932, this is to be brought back further consideration on this point specifically for the 4th November DSG. | DSG | Closed | 04/11/2019 - This was discussed and the outcome is reflected in the minutes for this meeting. |  | 2019-11-04
19 - 0720 | 04/11/2019 | In regard to February 2020 release, confirm what Xoserve is planning to implement in terms of documentation for this release. | Xoserve | Closed | 11/12/2019 - The confirmed scope was presented at ChMC 11/12/2019. The MiR Drop 6 Scope includes XRN4955 & XRN4997 |  | 2019-12-16
19 - 0721 | 04/11/2019 | Action: Regarding XRN4941, considerations need to be made regarding RGMA flow and S1/NS meters. | Xoserve | Closed | 11/12/2019 - Considerations for identification of SMART assets specifically outlined in the modification. This change will ensure these rules are utilised in a solution implemented |  | 2019-12-16
19 - 0722 | 18/11/2019 | Action: Xoserve to provide an update on when the next update for the AQ issues will be provided. | Xoserve | Closed | 11/12/2019 - DSG 18th December - Michele Downes provided an update to DSG which can be seen in the meeting minutes under agenda item 2 |  | 2019-12-02
19 - 0723 | 18/11/2019 | Regarding XRN4923, By allowing estimated readings to feed AQ, do we know I this will not have an inadvertent impact on the AQ calculation? | Xoserve | Closed | 11/12/2019 - SH - This will not have a detrimental impact to the AQ calculation and will occur more regularly. |  | 2019-12-02
19 - 0724 | 18/11/2019 | In regard to agenda item 3a.iii. - Supplier details not accurately presented within primary billing supporting information files - DSG reps to feed in whether this is the correct approach for this change. DSG to be prepared to ratify the at next DSG | DSG | Closed | 23/12/2019 - CS - DSG approved this change to go forward with the cancellation of the Change. |  | 2019-12-16
19 - 0725 | 16/12/2019 | In regard to XRN5038, Xoserve to attach the appendix and prioritisation score for ratification from DSG members at the next DSG meeting. | Xoserve | Closed | 31/01/2020 - This was presented at DSG on the 27th January 2020 | 2020-01-31 | 2020-01-27
20 - 0726 | 27/01/2020 | Xoserve to add AQ Taskforce Update as a standing agenda item. | Xoserve | Propose to close | CS - This has been added to the DSG agenda February as a standing agenda item. | 2020-02-11
20 - 0727 | 27/01/2020 | Xoserve to add R&N Change Overview as standing agenda item. | Xoserve | Propose to close | CS - This has been added to the DSG agenda February as a standing agenda item. | 2020-02-11