## POAP
PORTFOLIO-PLAN-ON-A-PAGE
Week Commencing 06 Feb 2023
|  |  | June 2021 |  |  |  | July 2021 |  |  |  | August 2021 |  |  |  |  | September 2021 |  |  |  | October 2021 |  |  |  |  | November 2021 |  |  |  | December 2021 |  |  |  | January 2022 |  |  |  |  | February 2022 |  |  |  | March 2022 |  |  |  | April 2022 |  |  |  | May 2022 |  |  |  |  | June 2022 |  |  |  | July 2022 |  |  |  |  | August 2022 |  |  |  | September 2002 |  |  |  | October 2022 |  |  |  |  | November 2022 |  |  |  | December 2022 |  |  |  | January 2023 |  |  |  |  | February 2023 |  |  |  | March 2023 |  |  |  | April 2023 |  |  |  |  | May 2023 |  |  |  | June 2023 |  |  |  | July 2023
 | time axis 2021-05-30 to 2023-07-30
Gemini & Integration | Auction BID Parameters | 2021-08-01: [M745] Build complete; 2021-08-29: [Gemini 1] Imp. Go Live; 2021-12-26: [Gemini M728B] PIS complete
[8 empty] | [M745] Design complete ** | [5 empty] | [UKL] Imp. Go Live |  |  |  | [Gemini 2] Imp. Go Live |  | [Gemini M745] PIS complete | [7 empty] | [UKL M728B] PIS complete | [17 empty] | Closedown complete
Gemini Sustain Programme | bar: 2021-05-30
[20 empty] | Inititation complete | [5 empty] | Design complete | [9 empty] | Build complete | [12 empty] | Test complete |  |  |  |  | Implementation Go Live | [34 empty] | Closedown complete
| Gemini Autumn 22 Release | 2022-01-16: Capture**; 2022-03-27: Start Up**; 2022-06-05: Design; 2022-07-03: Build**; 2022-09-04: Test; 2022-11-27: PIS; 2023-02-19: Closedown
Implementation Go Live
NTS Capacity Related UNC Modifications | bar: 2021-05-30
[26 empty] | Start Up complete |  |  |  |  | Design complete | [5 empty] | Build complete | [6 empty] | Test complete |  |  |  |  | Implementation Go Live | [8 empty] | PIS complete |  |  |  | Closedown complete
UK Link | November 2021 Major Release | 2021-11-14: Implementation Go Live [release 1]; 2022-02-27: Test complete (Deferred changes - release 2)
|  |  |  | Design complete | [18 empty] | Build complete |  |  |  | Test complete | [10 empty] | Implementation Go Live [ - release 2] | [23 empty] | PIS complete | [20 empty] | Closedown complete
(UKCLOUD) - UK Link Move to Cloud | bar: 2021-05-30
[17 empty] | Build complete | [80 empty] | Closedown Complete
| Xoserve Production Microsoft Azure Enterprise Hub | 2022-02-20: Test complete; 2022-05-15: PIS
Implementation Go Live [1]
| Cloud Operating Model | 2022-08-07: Test Complete P1; 2022-10-09: Test Complete P2; 2022-12-04: PIS P1
[35 empty] | PIS - EH & SN ** |  |  | Build ** | [9 empty] | Implementation Go Live - UKL Portal ** | [25 empty] | Implementation Go Live P2 | [7 empty] | PIS P2
| Flow Weighted Average CV | 2021-10-24: Initiation complete; 2022-07-10: Design - from Scope Change **; 2022-08-14: Dual Run & Market Trials Completed; 2022-09-25: Test Complete; 2023-02-19: Closedown
[23 empty] | Start Up complete |  | Design complete | [11 empty] | Build complete | [23 empty] | Build - from Scope Change ** | [6 empty] | Implementation Go Live | [18 empty] | PIS complete
Dec-21 Design Bundle | bar: 2021-05-30
[58 empty] | Start up complete ** | [5 empty] | Design complete**
| February 23 Major Release | 2023-01-15: Build; 2023-02-19: Implementation; 2023-04-09: PIS Complete; 2023-06-25: Closedown Complete
[70 empty] | Start Up & Initiation ** | [21 empty] | Test
| CSS Consequential Programme | 2022-03-20: Implementation Go Live [1]; 2023-01-22: Closedown complete
[42 empty] | Test complete | [18 empty] | Implementation Go Live [2] | [14 empty] | PIS complete
| UKL March-23 | 2023-02-05: Build; 2023-04-02: Implementation Go Live
[89 empty] | Start Up & Initiation exit | [6 empty] | Test | [5 empty] | PIS Exit | [7 empty] | Closedown exit
| UKL June-23 Major Release | 2023-02-05: Start Up & Initiation exit; 2023-06-25: Implementation Go Live
[101 empty] | Build | [7 empty] | Test |  |  |  | PIS Exit
Version: 59
Week Commencing 06 Feb 2023
Uncontrolled when printed
TODAY
Blue = Complete
Green = On Track Low Risk
Red = High Risk/In Replan
Amber = Medium Risk
Milestone RAG Key:
** = Milestone Date Provided is Provisional Pending Baseline