## Slide 1: DSC Delivery Sub-Group
26th August 2025

## Slide 2
1b
1.1 Lorem ipsum
Action Updates
REC Change
NESO – Verbal Update
Previous DSG Meeting Minutes
1. General Meeting Administration

## Slide 3: 1b

## Slide 4
SECTION 2:
Change Development
02
2a. New Change Proposals
2b. Change Proposal Initial View
2c. Undergoing Solution Options Impact Assessment Review

## Slide 5
SECTION 2:
Change Development
2ai. XRN 5955 Private networks duplicate MPRNs – options for long-term fix
2a. New Change Proposals
2b. Change Proposal Initial View
None for this meeting
2c. Undergoing Solution Options Impact Assessment Review
2ci. XRN 5914 - Mod0886 - Amend the Code Cut-Off Date to a Rolling Period and XRN 5922 - Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years
2ciii. XRN 5805 - Alternative solution to address scenarios where macro formulas are present in templates and reporting dataset
2cii. XRN 5906 - Mod0884 – Extending the PC4 Read Submission Window

## Slide 6: XRN 5955 Private networks duplicate MPRNs - options for long-term fix
Customer Parties | Impacted parties
Shipper | 
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non-Regulatory
Priority | Medium
Proposer | Cadent
Change Proposal | Link to CP
Change Description
Xoserve require a mechanism to record and track private networks sites to ensure no central activities can affect the private supplied properties, for example supply switching, meter exchanges, found meter processes. Creation of a system to identify and record potential private network addresses, utilising the minimum data provided (full address and postcode) but and exclude these from all BAU processing.
DSC Service Area Associated Funding Split | N/A
Proposed Funding split from Proposer | 100% DNO

## Slide 7: 2ci. XRN5914 – Amend the Code Cut-Off Date to a Rolling Period (Mod0886) and XRN5922 -Shorten the current code cut-off date (or Line in the Sand) from a 3 to 4-year period to a 2 to 3-year period (Mod0896)
Solution Pack

## Slide 8: XRN5922 (MOD0896) Change summary
Background
This Change Proposal has been raised to deliver the Central System changes required as set out within UNC Modification 0896.
Modification 0896 seeks to Shorten the current Code Cut-Off Date (or Line in the Sand) from a three to four (3 to 4) year period to a two to three (2 to 3) year period. This will mean there will be a 2-year jump in the Code Cut-Off Date (or Line in the Sand) in the initial year of implementation.
NB: Subsequent Code Cut-Off Date (or Line in the Sand) updates will revert to a 1-year jump post the initial year’s transition.
The Modification is seeking an April 2026 implementation date, to allow time for industry participants to prepare for the 2-year jump in Code Cut-Off Date (or Line in the Sand).
Notes: Add bullets

## Slide 9: XRN5922 (MOD0896) Change summary
As-Is:
Business Operational Processes support the annual LIS date change that commence in January to allow industry engagement, exception resolution and internal CDSP planning and processing until end of April.
In the AS-IS process the Code Cut-off date is rolled on annually effective 1st April of each year. This process commences within UK Link systems around the 10th of April to allow for monthly processes relating to March to complete. For CMS, the date change happens on 1st calendar day of April.
To-Be:
Changes to the existing systems and processes to reflect the new Code Cut-Off Date (or Line in the Sand/LIS) date (set to D-2 years) which is effective as of the 1st calendar day of April
Changes to existing operations reports impacted the Code Cut-Off (LIS) date changes
New reports where applicable to monitor the existing BAU processes (e.g. GSR) impacted due to the Code Cut-off date Changes
New Transitional report to support existing RFA process impacted due to Code Cut-off date changes
Resolve any exceptions impacting the code cut-Off (LIS) date changes by 31st March.
Notes: Add bullets

## Slide 10: XRN5922 TO BE Process Timeline
© Xoserve
Notes: Add bullets

## Slide 11: XRN5914 (MOD0886) Change summary
Background
This Change Proposal has been raised to deliver the requirements outlined in Modification 0886 Amend the Code Cut-Off Date to a Rolling Period. Modification 0886 seeks to amend the Code Cut Off date from an annual change on the 1st of April every year, to a monthly rolling date which is effective on the 1st calendar day of each month.
Other than a move to a monthly rolling Code Cut-Off date, all other existing rules are to remain the same. In particular:
  The LIS Read estimation process outlined in TPD M 5.4.5 will remain as an annual process .
  The Customer Settlement Error Claims process outlined in TPD E 1.3.8 will continue to apply as it does now.
Transactions with Code Cut-Off date dependencies will require due dates to be set in the UK Link Manual. Examples of such transactions include; DMQs, RFAs and DUPs. It is anticipated that Shippers will submit their transactions as per the new proposed submission dates as updated into the UK Link Manual.
Notes: Add bullets

## Slide 12: XRN5914 (MOD0886) Change summary
As-Is:
Business Operational Processes to support the annual LIS date change commence from the beginning of the current year to allow industry engagement and internal CDSP planning and processing until end of April.
In the AS-IS process the Code Cut-off date is rolled on annually effective 1st April of each year. This process commences within UK Link system around the 10th of April to allow for monthly processes relating to March to complete. For CMS, the date change happens on 1st calendar day of April.
To-Be:
Changes to the existing systems and processes to reflect the new Code Cut -Off Date(LIS) set to a monthly rolling Code Cut -Off Date which is effective as of the 1st calendar day of each month.
Changes to existing operations reports impacted by the Code Cut -Off Date(LIS) changes
New reports where applicable to monitor the existing BAU processes (e.g. GSR) impacted due to the Code Cut -Off Date(LIS) Changes
New annual calendar with Code Cut -Off Date(LIS) change activities for each month published to customers
As Shipper submission trends are currently unknown, it is anticipated that the level of business resource required to support the process will need to be reviewed and, as such, any change to this may need to be factored in post go live of the modification. This review should also include any technical resource that currently support the annual process but, post implementation, will be required on a monthly cycle.
Notes: Add bullets

## Slide 13: XRN5914 TO BE Process Timeline
Notes: Add bullets

## Slide 14: High Level Solution Overview
# | Description | Systems and Process impacts | Estimated cost range
1 | Code cut off (LIS) date change – Monthly/Annual | UK Link (SAP ISU): Code cut off date (LIS date) is a configuration parameter that is amended annually at present There are 4 parameters maintained within the UKLink system at business process level – Meter reads, Reconciliation , Amendments Billing and UIG smear The code cut off date is amended on 12th calendar day following the monthly Amendments billing cut off date (10th calendar day) except for the UIG smear parameter which is amended post the UG smear process runs (~18th-20th calendar day). The current process for parameter update will continue as per the existing process i.e. As a code update that is applied to all environments meaning that all non–production systems/environments are updated automatically prior to applying the changes in Production system with relevant audit trails with limited manual intervention LIS read estimation process will continue to remain as an annual process. LIS read estimation runs in June every year and will use the latest rolling LIS date for the read estimation. This would mean that the MPRN read validation and reconciliation process will go back past the actual LIS date in the absence of an estimated read on the LIS date as per existing business principles. CMS: Update the Code cut off (LIS) date parameter on the User Interface (UI) for the applicable contact types on 1st April 2026 with the initial 2-year jump Enhancements to the existing process to automatically update the LIS date parameter on the UI for the applicable contact types on a rolling monthly basis on 1st calendar day of every month For RFA contacts only, new functionality will be introduced to automatically perform a monthly system sweep. This process will identify any open RFA contacts that are pending action from Shippers where the entire adjustment period falls prior to the current LIS date and will automatically close these contacts as invalid. Currently this process is manual and relies on the CDSP contact handler to manually pull the contact back from the Shipper queue prior to closure. | £47k - £90k
2 | Operational reports | Unresolved Exceptions report: Enables tracking of unresolved exceptions by the month end prior to LIS date change to ensure timely resolution of the exceptions thereby avoiding any offline adjustments Prime & Sub report : Enables identifying P&S sites that requires offline adjustments to be initiated prior to/after LIS date change happens GSR report : Enables identifying MPRNs within the GSR process impacted due to the LIS date changes RFA report : One off report for the transition period to understand the volumes of Shipper submissions of the RFAs. | 

## Slide 15
Proposed Delivery Plan
Schedule shown is the longest among the proposed options.
Efficiencies in schedule may be realised if Correla reporting team is delivering the new BO reports or delivered via Discovery.
Regression testing is recommended to ensure critical UK Link/CMS processes are tested for the monthly rolling LIS date changes
Market trials is not considered for this change as there are no customer impacts identified. There will be additional cost/efforts If market trials is required to support any integrated customer testing.

## Slide 16
Market Trials
Schedule shown is the shortest timeline proposed that a Market trials environment could be built and tested, this has no contingency if any defects are found during the testing phases.
The timeline shown is for the provision of a new QAS environment (SAP ISU & CMS ) environment to facilitate market trials on, as to not impact inflight and planned change
Data cut for this Market trials phase would be a 2% of the full UKLink estate.
Conducting Market Trials would remove the 5914/5922 from February 26 release as 3 months would be required to test all the processes impacted by the changes.
The Market Trials environment would not connect to any external industry systems.
Assumption is that BAU resource would be available to support a 3 month Market Trials phase.
Assumption we have a Correla team to support during weekdays 9-5 to utilise the current processes, if the environment goes it will be at a best endeavours basis.
Assumptions that commercials would be complete by the start of October.
Assumption is that no reporting will be conducted as part of the Market Trials activity
There is risk that are additional costs can be incurred for additional efforts to share data securely.
Market Trials estimated cost: 155 - 165k (this includes a months contingency)
Total project cost: 215k – 255k

## Slide 17
Thank you
Q&A?

## Slide 18: 2cii. XRN5906 – UNC MOD0884 Extending the PC4 Read Submission Window
Solution Pack

## Slide 19: XRN5906 Change summary
Background
Shippers have 25 Supply Point System Business Days (SPSBD), after a meter read date, to submit a read to the CDSP for settlement.
Where there is an issue preventing the read from being validated, and that issue is not resolvable within the 25-day timeframe, the meter read becomes unusable, as the CDSP systems will reject the meter read for being outside read submission window.
Enabling more valid reads, by extending the 25-day read submission window, would decrease settlement imbalance, and repeated costs for additional site visits, as well as time and money spent on Must Reads.
Notes: Add bullets

## Slide 20: XRN5906 Change summary
Change Overview
A change to the Product Class 4 (PC4) read submission window is required to facilitate the implementation of MOD 0884.
This MOD will extend the current window of 25 SPSBD, depending on the Market Sector Code of the meter point, to 80 SPSBD for ‘Domestic’ premises and 45 SPSBD for ‘Industrial and Commercial’ premises.
Notes: Add bullets

## Slide 21: XRN5906 Change summary
Process areas impacted
Any process where there is a current 25 SPSBD read submission window rule for a PC4 meter point. Depending on the Market Sector Code of the meter point on the date of the meter read, the CDSP will extend the submission window to 45 or 80 SPSBD.
Processing areas that use the current 25 SPSBD rule:
The cyclic PC4 Meter Read validation process.
The process of pausing Check to Check reconciliation to allow time (i.e., the read submission window) for Meter Reads to load, before reconciling over the period.
Notes: Add bullets

## Slide 22: XRN5906 Change summary
Impact on existing reporting
PAC have required no new reporting, or changes to existing PAC reporting
Existing PAC Meter Read Performance Reports on the 25 SPSBD submission window will not be changed
Impacts to DDP Dashboards expected to be minimal and cosmetic only
New reporting
New internal reports will be developed to show accepted monthly PC4 Meter Read submissions by age, and by Shipper. These will help show what, if any, change in Meter Read submission behaviour happens after the MOD is implemented.
Notes: Add bullets

## Slide 23: XRN5906 AS IS Process overview
PC4 Meter Read validation
End
CDSP
Shipper
Meter Read process
Start
1. Validate Meter Read
3. Reject
Meter Read
Meter Read passes all other standard validations?
> 25 SPSBD since Meter Read Date?
No
Yes
No
2. Load
Meter Read
Yes
4. Notify submitter Accepted / Rejected
Notes: Add bullets

## Slide 24: XRN5906 TO BE Process overview
PC4 Meter Read validation
End
CDSP
Shipper
Meter Read process
Start
1. Validate Meter Read
3. Reject
Meter Read
Meter Read passes all other standard validations?
> 80 SPSBD since Meter Read Date?
No
2. Load
Meter Read
Yes
4. Notify submitter Accepted / Rejected
What was the Market Sector Code on Meter Read date?
I & C
> 45 SPSBD since Meter Read Date?
Domestic
Yes
Yes
No
No
Notes: Add bullets

## Slide 25: XRN5906 High Level Solution
# | Description | Systems and Process Impacts | Total Cost Estimate Range
1 | XRN5906 aims to extend the read submission window for PC4 cyclic reads based on market sector code. The new proposed read submission window is 80 SPSBDs for Domestic and 45 SPSBDs for I&C sites. | SAP ISU: PC4 read interface changes to amend read submission validation based on market sector code (MSC). Configuration changes for storing the new read submission window based on MSC and SPSBD benchmarks for reporting. Site Visit interface changes to extend the current wait period for processing check to check reconciliation in line with extended read submission window Reporting: A new monthly report to generate the rolling 12-month view of the PC4 read submission percentage per Shipper for Domestic and I&C sites. Performance Testing: PT will be considered in scope for the read and downstream processes (AQ and reconciliation) as this XRN may bring about a possible increase in the read submissions and consequently accepted reads, currently being rejected due to the 25 SPSBD submission window. | £70k to £105k
Receive read response
Shipper
New Reporting
New report to generate the 12-month rolling view of PC4 read submissions
Shipper
Submit Class 4 cyclic reads
Xoserve
PC4 Read submission trend report
UKLink (SAP ISU)
2 batch interface changes
1 Internal read screen change

## Slide 26: XRN5906 – Proposed delivery timeline
Notes: Add bullets

## Slide 27
Thank you
Any questions?

## Slide 28: 2ciii. XRN5805 – Alternative solution to address scenarios where macro formulas are present in templates and reporting dataset
Solution Pack

## Slide 29: XRN5805 Change summary
Background
DN customers have identified issues with their ability to supply agreed templates to CDSP due to the presence of Macros embedded within related spreadsheets.
The below templates are in scope of this change
RTB - Request to Bill
Site Visit
FSG - Failure to Supply Gas (FSG)
BCL - Bulk Contact Logging (BCL)
MBG - MPRN Creation File/MBG
TOG - Theft of Gas
LSEC - LDZ Entry Commodity Charge
PCD - Pricing Template
ORD - LDZ Energy Adjustment
DNW_LPGpricing_rates_v0 6 Approved
Notes: Add bullets

## Slide 30: XRN5805 Solution Overview
The options currently being assessed are:
Option 1 – DN accessing Power Platform to upload the template (All templates)
Option 2 – DN accessing UK Link Portal to upload the template (All templates)
Option 3a – Require DN to provide data in appropriate format
Option 3b – Alternative Excel Template
Option 4 – Expansion of the manual workaround to all templates
Notes: Add bullets

## Slide 31: As Is Process Overview
AMT
Validations
UK Link
Validations
Stores data
Templates
Cell Validations
Macro validations
Distribution Networks

## Slide 32: Solution Option 1 Overview Power Platform
A screen will be built using the power platform. The networks will have the ability to upload the templates into the screen.
The templates will remain as-is including cell validations.
The macro validations will be removed from the templates and completed using the power platform
If the template is rejected in the power platform, the rejection reason/s would be displayed on the screen to DN user.
File generated would be processed by AMT and UK Link as per the current functionality and hence no changes are required in these applications.
AMT
Validations
UK Link
Validations
Stores data
Templates
Cell Validations
Distribution Networks
Power Platform
Replace macro Validations
Notes: Add bullets

## Slide 33: Solution Option 2a Overview UK Link Portal – As-Is Validations
A screen will be built in the existing UK Link Portal that the Networks already have access to. The networks will have the ability to upload the templates on the new screen.
The templates will remain as-is including cell validations.
If the template is rejected in the portal, the rejection reason/s would be displayed on the screen to DN user.
Upon acceptance of the template, the data will be stored in UK Link.
As the file is no longer sent to AMT, the validations that take place in AMT will be moved to Portal.
The validations that take place in UK Link will remain as is.
UK Link
As-Is Validations
Stores data
Templates
Cell Validations
Distribution Networks
UK Link Portal
Replace macro validations
Replace AMT validations
Notes: Add bullets

## Slide 34: Solution Option 2b Overview UK Link Portal – Enhanced Validations
A screen will be built in the existing UK Link Portal that the Networks already have access to. The networks will have the ability to upload the templates on the new screen.
Revised templates to reduce DN data inputs by creating new UK Link processes.
If the template is rejected in the portal, the rejection reason/s would be displayed on the screen to DN user.
Upon acceptance of the template, the data will be stored in UK Link.
As the file is no longer sent to AMT, the validations that take place in AMT will be moved to Portal.
The validations and data lookups that take place in UK Link will be enhanced to minimise DN data inputs.
UK Link
Enhanced Validations
Stores data
Templates
Cell Validations
Distribution Networks
UK Link Portal
Replace macro validations
Replace AMT validations
Notes: Add bullets

## Slide 35: Solution Option 3b Overview Alternative Excel template
Population on Excel template (without macros), with as-is cell validation.
Creation of the required submission file content within the template,
Requires DN manual process to create the required submission file format.
File submitted to the CDSP via the BAU route.
AMT
Validations
UK Link
Validations
Stores data
Templates
Cell Validations
Distribution Networks
Notes: Add bullets

## Slide 36: Solution Option 4 Overview Expand manual workaround
Distribution Networks provide the data required in the as-is template with macros removed.
The Business ops team create the csv. using the macros.
The Business ops team would then email the templates into AMT.
File generated would be processed by AMT and UK Link as per the current functionality and no changes in these applications.
UK Link
Validations
Stores data
Business ops run macros and email to AMT
AMT
Validations
Distribution Networks provide spreadsheet
Notes: Add bullets

## Slide 37: Option Comparison

## Slide 38: Option Comparison

## Slide 39: Discounted Option

## Slide 40
SECTION 3:
Detailed Design
03
3a. Design Considerations
3b. Requirements Clarification
Project Updates

## Slide 41
SECTION 3:
Detailed Design
None for this meeting
3a. Design Considerations
3b. Requirements Clarification
None for this meeting

## Slide 42
Section 4: Release/Project Updates
04
4a. June 25 Major Release
4c. DDP
4b. Minor Release drop 15

## Slide 43: XRN5868 – June 25 Major Release - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope & BER of June 25 Major Release were approved at the ChMC Meetings on 08/01/25 & 12/03/25 respectively. Overall release is tracking to target; project implemented as scheduled on 27/06. Progress Update: PIS on track to complete - 15/08/25 Communications Update: Successful Implementation – 27/06/25 PIS Exit – 15/08/25 CCR to be shared at ChMC – 10/09/25 | Implementation date 27th June, contingency date 4th July | 
Risks and Issues | 69676 - June 25 PIS Extension - PIS may be extended because of a request for an additional UIG smear and AMS invoice run |  | 
Costs | Forecast to complete against approved BER |  | 
Scope | XRN5846 – New allowable value (M - Thermal Mass) for Meter Type Code (H100) XRN5784 – Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements |  | 
Complete
On Track
At Risk
Overdue

## Slide 44: Minor Release 15 Scope
Release | Minor Release Drop 15
Implementation Date | 8th December (Indicative Date)
XRN | Title | Proposer | Benefitting | Funded by
XRN5732 | Inclusion of IGT MPRNs into Existing DSC Processes | Xoserve | IGTs, Shippers | Service & Operate
XRN5890 | Proactive Reporting of MAP ID Population | Xoserve | Xoserve | Service & Operate
Notes | XRN5732 Ensure IGT customers have an equivalent level of interaction and involvement in the DSC specified processes where necessary, to enable mutualised service coverage across DN and IGT customers. This covers UKL elements only; CMS delivery to be confirmed at a later date. XRN5890 Currently, there is no standard reporting tracking the population of MAP ID against sites in the Central Switching Service; population of this attribute in CSS is controlled from the CDSP on behalf of Transporters, whose obligation is to pass the information that they hold. Currently, there is no standard reporting tracking this process, consequently the CDSP cannot escalate potential poor performance or make recommendations for improvement to the Retail Energy Code Company (RECCo).
Decision | None required, update for information only
Notes: Add bullets

## Slide 45: 2025-26 DDP Roadmap: Release Timeline
Roadmap | Apr-May ‘25 | Jun-Jul | Aug-Sep | Oct-Nov | Dec’25-Jan’26 | Feb-Mar
Release 1 2025/26: Read Enhancements & Shipper Portfolio | Complete |  |  |  |  | 
Release 2 2025/26: Shipper No Meter, Portfolio Gains/Losses & Plot Addresses |  | Complete |  |  |  | 
Release 3 2025/26: Shipper Portfolio Enhancements (UPRN, RMP, MPR Installer) Networks 150 & 60 Pricing reports IGT New Connection Process |  |  | Scope Refinement |  |  | 
Release 4 2025/26: TBC |  |  |  | Not Started |  | 
Release 5 2025/26: TBC |  |  |  |  | Not Started | 
Release 6 2025/26: TBC |  |  |  |  |  | Not Started

## Slide 46: Release 2: Update
Update:
Release 2 deployed during DDP Maintenance hours in 2 stages on 27th and 31st July 2025
All core and stretch features delivered
Data Discovery Platform | Release 2 2025 - 2026 |  |  | 
Goals: |  | Shippers | Networks | IGTs
Core |  | Portfolio: | Portfolio: | 
 |  | •Portfolio Gains & Losses | upgrade dashboard increasing download limit | 
 |  | •Meter Read Rejections Enhancements (from R1) |  | 
 |  | Asset |  | 
 |  | •Market Sector Code by No Meter Recorded |  | 
 |  | •No Meter by EUC |  | 
Stretch |  | Portfolio |  | 
 |  | •Plot Address Correction |  | 
 |  | Asset |  | 
 |  | •No Meter By Dataflow/Class & Meters with Open/Closed Bypass Flag |  | 

## Slide 47: Release 3
Data Discovery Platform | Release 3 2025 - 2026 |  |  | 
Goals: |  | Shippers | Networks | IGTs
Core |  | Portfolio Enhancements: | Charging Simulation: | Portfolio:
 |  | •Unique Property Reference Number addition | 150 & 60 Day Pricing Notice reports | XRN 5614 Improving IGT SMP New Connections Process
 |  | •RMP Status addition |  | 
 |  | •MPRN Installing Shipper addition |  | 
Stretch |  | Asset | Charging Simulation: | 
 |  | •Portfolio Matrix report for MAM & MAP combinations | Usability Improvements to Aggregated MPRN Summary dashboard | 

## Slide 48: DDP Assurance Workgroup
For all DDP Releases we would like to request volunteers from the DDP User community to sponsor planned features
The objective is to increase engagement in new Release features and help ensure we deliver features that meet the needs of our users
This would involve:
  Contributing and supporting the relevant User Stories that sit behind proposed features, to promote benefits to wider industry
  Testing and First Usage assurance of new/updated dashboard features, to confirm satisfaction with the delivered content
Should you be able to support please contact the team via our operational email box account (ddp@xoserve.co.uk)

## Slide 49: DDP Team Contact Details
DDP Issues:
If you have an issue relating to DDP which you require support with, please raise a ticket via ‘help and support’ on Xoserve.com here. This will ensure the issue is dealt with promptly and provides an audit trail
DDP Queries / Development / Shipper Forum:
If you have any queries, ideas or suggestions for future DDP features or questions relating to the DDP Shipper Forum please drop an email to the DDP Operational team via our box account: ddp@xoserve.co.uk
For avoidance of doubt, if you have an issue with DDP, the quickest way for a resolution is to raise a ticket

## Slide 50: 2024-25 DDP Roadmap: Release Timeline
Roadmap | Apr-May ‘25 | Jun-Jul | Aug-Sep | Oct-Nov | Dec’25-Jan’26 | Feb-Mar
Release 1 2024/25: Hydrogen Trials | Complete |  |  |  |  | 
Release 2 2024/25: Hydrogen Trails |  | Complete |  |  |  | 
Release 3 2024/25: Vacant Sites/AQ At Risk |  |  | Complete |  |  | 
Release 4 2024/25: Vacant Sites |  |  |  | Complete |  | 
Release 5 2024/25: Shipper pack, DN AQ Tracking, IGT Reads |  |  |  |  | Complete | 
Release 6 2024/25: Shipper AQ, DN Charging Enhancements, IGT MDD |  |  |  |  |  | Complete

## Slide 51
Section 5:
Change Pipeline
05
5a. Change Pipeline Update

## Slide 52: 2025 Forward View - Change Delivery Plan
January 25 – December 2025
Jan-25
June-25
February 25 – Major Release
XRN5614
March-25
Sep-25
Dec-25
June 25 – Major Release
XRN5784, XRN5846
Minor Release 15
(TBC)
Slide produced 29h July 2025
November 25 – Major Release
February 26 - Major Release
XRN5702 | XRN5872 | XRN5906 | XRN5914 | XRN5922
Adhoc Project
XRN5851 – Procurement and Service Activities
XRN5892 – Ring Fenced Budget for AUGE Value Add Services
Minor Release 14
XRN5888
XRN5933
XRN5885
XRN5941 – Performance Assurance Committee
Audit PAT
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Implemented Change / Release
Delivery Key
Slide produced 29th July 2025

## Slide 53: Change Delivery Plan – January 2025 – December 2025
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | *£120k revised following design | 28th February 2025 | Major | Firm
5885 | Cease Provision of SC9 Files to Distribution Networks (DNs) | Cadent | DN | N/A | N/A | 28th April 2025 | Adhoc | Firm
5549 | Automation of the UK Link and Gemini mismatch analysis and correction process | Xoserve | CDSP | N/A | N/A | 30th May 2025 | Minor | Firm
5769 | Changes required to Broadcast Service (minor changes | Xoserve | DN IGT | N/A | N/A | 30th May 2025 | Minor | Firm
5784 | Mod0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN | Shipper | £115k | 27th June 2025 | Major | Firm
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | £100k | 27th June 2025 | Major | Firm
5851 | Mod0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | TBC | June/July 2025 | Adhoc | Firm
5892 | Ring-fenced DSC Budget to support Allocation of Unidentified Gas Value-Add Activities | SEFE | Shipper | Shipper | TBC | June/July 2025 | Adhoc | Firm
5933 | Business Plan Information Rules Independent Assurance | Xoserve | All | All | £80k | September 2025 | Adhoc | Firm
5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Cadent | DN IGT | DN | N/A | November 2025 | Minor | Indicative
5732 | Inclusion of IGT MPRNs into specified existing DSC Processes | BUUK | IGT | IGT | £40k | November 2025 | Minor | Indicative
5941 | Performance Assurance Committee – Audit PAT | Xoserve | Shipper DN IGT | Shipper DN IGT | £300K | TBC | Adhoc | Indicative

## Slide 54: Change Delivery Plan – January 2026 – June 2026
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £230k *ROM est. | 27th February 2026 | Major | Firm
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | Shipper | £190k | 27th February 2026 *subject to modification approval | Major | Indicative
5906 | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | Shipper DN | £100k *ROM est. | 27th February 2026 *subject to modification approval | Major | Indicative
5914 | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period | SSE | Shipper DN IGT | Shipper | £100k *ROM est. | 1st April 2026 *subject to modification approval | Adhoc / Major | Indicative
5922 | Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE | Shipper DN IGT | Shipper | £50K *ROM est. | 1st April 2026 *subject to modification approval | Adhoc / Major | Indicative
5940 | Mod0890 – Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation | Centrica | Shipper DN | TBC | £200K *ROM est. | 26th June 2026 * Subject to modification approval | Major | Indicative
5924 | Physical Information Exchange (PIX) Ongoing Support Options | Xoserve | All | TBC | TBC | 31st June 2026 | Adhoc | Indicative

## Slide 55: Change Backlog – ‘In Progress’ Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | August ‘25 - ChMC Update
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target Q2 2025 update for DSC customers at DSG
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Requirements | Solution Option issued for consultation in May ‘25 Change Pack – next steps to be confirmed following change pack decision and agreement on how to progress.
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | Analysis | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Requirements | Protype solution being trialled with one DN party ahead of finalising functionality and sharing with all DN parties.
5949 | New Priority Consumer Category related to Community Heating | NGT | All DSC Customers | TBC | Requirements | New Change Proposal raised in July – entering development phase with ongoing discussions taking place between Ofgem, NGT, DNs and DESNEZ to agree scope and requirements.
5950 | DSC Invoice Number generation review | CDSP | Shipper DN NGT | TBC | Requirements | New Change Proposal raised in July – Impact Assessment taking place across DSC Invoices to clarify which invoices are within scope of the change.
5955 | Private networks duplicate MPRNs - options for long-term fix | Cadent | DN | DN | Requirements | New Change Proposal to support introducing a solution that enables sites on Private Networks to be recorded and used in CDSP validation processes.

## Slide 56: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | August ‘25 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | TBC | Agreed following September ChMC that change would be placed on hold whilst data cleansing activities were progressed – change to be revisited in January with DNs / IGTs
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | N/A | N/A | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | TBC | TBC | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | TBC | TBC | Continue to support regulatory development and provide update to ChMC once status of Modification changes
5923 | Updates to the suite of Performance Assurance Report Register (PARR) | CDSP | Shipper DN IGT | Shipper | TBC | TBC | Placed on hold and awaiting conclusion of PAC Audit PAT before this will be revisited.

## Slide 57: DSC Change Pack Consultation Plan (two month view)
Aug – 25
Sep - 25
Oct – 25
XRN5914 - Mod0886 - Amend the Code Cut-Off Date to a Rolling Period
XRN5922 - Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years
XRN5906 - Mod0884 – Extending the PC4 Read Submission Window
XRN5940 - Mod0890 – Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation
XRN5732 - Inclusion of IGT MPRNs into specified existing DSC Processes
Delivery Key
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Slide produced 29th July 2025

## Slide 58
Section6: AOB
06
Any Other Business –
None for this meeting

## Slide 59
Section 7:
Annex
07
7a. ChMC Update - Link here.
7b. Rec Update - Link here.
7c. POAP - Link here.