## Slide 1: DSC Delivery Sub-Group
Monday 24th March 2025

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Change Development

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
2a.i. XRN 5892 Ring-fenced DSC Budget to support Allocation of Unidentified Gas Value-Add Activities

## Slide 6: XRN5892 Ring-fenced DSC Budget to support Allocation of Unidentified Gas Value-Add Activities
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | 
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Description
The purpose of this Change Proposal is to allocate a ring-fenced budget for AUG Value-Add Activities which are a new activity assigned to the AUGE because of Modification 0868. Without a ring-fenced budget, the AUGE will not have the funds to carry out new activities (please see the Change Proposal for more detail) which fall into three areas: Market Engagement, Discovery Activities and UIG Reduction Initiatives which could help meet net zero objectives.
DSC Service Area Associated Funding Split | N/A
Proposed Funding split from Proposer | Funding of AUGE and associated Value Add Activities has been confirmed to be a 100% Shipper responsibility.
Change Type | Regulatory
Priority | High
Proposer | SEFE Energy
Change Proposal | Link to CP

## Slide 7: 2b. Change Proposal Initial View Representations

## Slide 8: 2b. Change Proposal Initial View Representations
None for this meeting.

## Slide 9: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 10: 2c. Undergoing Solution Options Impact Assessment Review
2c.i. XRN 5808 Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action

## Slide 11: XRN5808 – Providing Notification to DNs/ IGTs for Referrals Awaiting Action
High Level Solution Options

## Slide 12
XRN5808 - Change Summary
Requests by Shippers are referred through the UK Link Portal for Distribution Network Operators (DNOs)/ Independent Gas Transporters (IGTs) to action. Currently there is no notification (e.g. email) sent to the DNO to inform them that there is a Referral within the UK Link Portal that is awaiting assessment and action. IGTs currently receive the IGR file which details new referrals only.
The UK-Link Portal is not checked daily and as a result, DNO/IGT referrals are only known when a DNO/IGT either:
  ad-hoc reviews the portal
  is chased for a response (usually by email outside of the portal)
  The IGR file is sent to IGTs only. (Nomination, Capacity & Priority consumer only)
The creation of a specific notification to the DNO/IGT will reduce the potential of undue delay in responding to Shippers and their customers when a referral decision is required.
New Referrals will be sent on one occasion in the report sent following referral submission.
Referrals approaching their SLA will be sent 3 days prior to their SLA on one occasion in the report following referral submission.

## Slide 13
XRN5808 - Change Summary
The Referral Status – NW(New) will be considered for any new referrals sent out and Referral Status of PR(In Progress) and IN(In-Use) will be considered for any Chaser Notifications to be sent out.
Requests referred to multiple parties such as for an IGT site or Nested CSEP sites, the report will be sent out to all approval parties where action is pending.
Selection criterion to be configurable – SLA timeline, Referral types, LDZ etc.
Performance testing is not required for Option 1 as the referral request volume
totalled 227 in 2024.
Daily Referral Notification Summary Report Format
Notification Type
CSEP Reference
Associated MPRN
REFERENCE NUMBER
Source
Type Of Referral
LDZ
GT SHORT CODE
SHIPPER
IGT SHORT CODE
REFERRAL SUBMISSION DATE
REFERRAL ACTION BY DATE
REFERRAL PENDING WITH

## Slide 14: Customer Requirements
Ref No. | Actor (As) | Requirement Description (I want to...) | Rationale (So that…) | Acceptance Criteria |  | Priority |  | Comments | 
EPIC | DN/IGT | To receive Nomination, Capacity and LDZ Optional Capacity Tariff ('shorthaul') referral notifications from the CDSP | I can use the notifications to trigger internal processes to facilitate adherence to my UNC obligations relating to actioning of Shipper referrals | Only nominal and understood instances exist where referrals remain outstanding for review/action |  | Must |  | The solution assessment should consider that not all DNs/IGTs may wish to receive this information; as it is already held in the UK-Link Portal | 
Requirement Framework |  |  |  |  |  |  |  |  | 
CR1.0 | CDSP | Referral Notification mechanism/process: I want to establish a mechanism/process to provide those participating DNs/IGTs with 'Daily Referral Notification Summary(ies)' ('DRNS') | So that participating DNs/IGTs can easily identify new and/or outstanding shipper referrals held within the UK-Link Portal | The CDSP will: 1) Provide DRNS of new / outstanding referrals held within the UK-Link Portal 2) Maintain a Distribution List of contacts for each participating DN/IGT to which DRNS will be sent | The CDSP will: 1) Provide DRNS of new / outstanding referrals held within the UK-Link Portal 2) Maintain a Distribution List of contacts for each participating DN/IGT to which DRNS will be sent | Must | Must |  | 
CR2.0 | DN/IGT | Referral Notification: I want to be notified that a Shipper Capacity, Nomination or Shorthaul referral has been submitted into the UK Link Portal | So that the Shippers' referrals can be reviewed and actioned by the DN/IGT upon submission | Please see CR3.1, CR3.2, CR3.3 and CR4.0 Acceptance Criteria | Please see CR3.1, CR3.2, CR3.3 and CR4.0 Acceptance Criteria | Must | Must |  | 
CR2.1 | DN/IGT | Referral Notification: I want to be notified of all Shippers' Capacity, Nomination and Shorthaul referrals that still require review/action within the UK-Link Portal [3] SPSBDs prior to Referral SLA expiry date | So that the Shippers' referrals can be reviewed and actioned by the DN/IGT prior to the Referral SLA expiry date | Please see CR3.0 and CR4.0 Acceptance Criteria | Please see CR3.0 and CR4.0 Acceptance Criteria | Must | Must |  | 
CR3.0 | DN/IGT | Distribution List Contacts/Routing: I want to receive the DNRS to an agreed list of business/operational support contacts within my organisation | So that the DNRS is routed to the correct business/operational support contacts for review and action | Please see CR3.1, CR3.2, CR3.3 and CR4.0 Acceptance Criteria | Please see CR3.1, CR3.2, CR3.3 and CR4.0 Acceptance Criteria | Must | Must | The solution should assess the DRNS being separated into individual (3) summaries e.g. by Referral Type | The solution should assess the DRNS being separated into individual (3) summaries e.g. by Referral Type
CR3.1 | CDSP | Distribution List Contacts/Routing: I want to hold and maintain a Distribution List (DL) containing business /operational support contacts that will receive the DRNS | So that the DNRS is routed to the correct DN/IGT business/operational support contacts within that organisation for review/action | 1) The CDSP holds an agreed DL of organisation contacts that will receive the DRNS 2) The CDSP will support the option for the DN/IGT to route to specific DL contacts based on Referral Type i.e. Nomination, Capacity, Shorthaul | 1) The CDSP holds an agreed DL of organisation contacts that will receive the DRNS 2) The CDSP will support the option for the DN/IGT to route to specific DL contacts based on Referral Type i.e. Nomination, Capacity, Shorthaul | Must | Must | Addition/removal of DL contacts will be BAU with the DN/IGT raising an Xoseve Service Ticket to effect the change | Addition/removal of DL contacts will be BAU with the DN/IGT raising an Xoseve Service Ticket to effect the change
CR3.2 | DN/IGT | Distribution List Contacts/Routing: I want DRNS 'Routing' options (based on Referral Type) within the DL/mechanism | So that the DNRS is routed to the correct business/operational support contacts within my organisation for review/action | 1) Nomination and/or Capacity DRNS sent to all or, to specific DL contacts 2) Shorthaul DRNS sent to all or, to specific DL contacts | 1) Nomination and/or Capacity DRNS sent to all or, to specific DL contacts 2) Shorthaul DRNS sent to all or, to specific DL contacts | Should | Should | The solution should assess the DRNS being separated into individual (3)summaries e.g. by Referral Type | The solution should assess the DRNS being separated into individual (3)summaries e.g. by Referral Type
CR3.3 | DN/IGT | Distribution List Contacts/Routing: I want a DRNS 'Routing' option based on the Shipper's Referral (MPRN) geographical location | So that the DNRS is routed to the correct business/operational support contacts within my organisation for review/action | DRNS is routed to specific DL contacts dependent on the Referral (MPRN) geographical location (DN Network) i.e. LDZ | DRNS is routed to specific DL contacts dependent on the Referral (MPRN) geographical location (DN Network) i.e. LDZ | Could | Could | For example, if a Nomination or Shorthaul Referral MPRN is located in Cadent's East Midlands (EM) LDZ, the DRNS would be routed to Cadent's 'EM' DL contact | For example, if a Nomination or Shorthaul Referral MPRN is located in Cadent's East Midlands (EM) LDZ, the DRNS would be routed to Cadent's 'EM' DL contact

## Slide 15: Customer Requirements
Ref No. | Actor (As) | Requirement Description (I want to...) | Rationale (So that…) | Acceptance Criteria | Priority | Comments | 
EPIC | DN/IGT | To receive Nomination, Capacity and LDZ Optional Capacity Tariff ('shorthaul') referral notifications from the CDSP | I can use the notifications to trigger internal processes to facilitate adherence to my UNC obligations relating to actioning of Shipper referrals | Only nominal and understood instances exist where referrals remain outstanding for review/action | Must | The solution assessment should consider that not all DNs/IGTs may wish to receive this information; as it is already held in the UK-Link Portal | 
Requirement Framework |  |  |  |  |  |  | 
CR4.0 | CDSP | Referral Notification: Daily Referral Notification Summary(ies) - DRNS: I want to compile and send DRNS to participating DNs/IGTs in accordance with the Acceptance Criteria* | So that DNs/IGTs can determine those new or outstanding shipper referrals that require review/action in accordance with existing SLAs/UNC obligations | The CDSP will report on: 1) Initial notifications for shipper Nomination, Capacity and/or Shorthaul referrals - on the day of referral i.e. shipper submission date into the UK-Link Portal 2) 'Chaser' notifications for those referrals that are awaiting review/action within the UK-Link Portal 3 SPSBDs prior to the Referral SLA expiry date - please see Referral SLAs Tab for information 3) For 1 & 2 above, the following information for each Referral: - Type of Referral, - MPRN / Location (LDZ), - [Shipper], - Referral submission date into UK-Link Portal - Referral 'Action by Date' (SLA) - additional information relevant to the Referral Type 4) UK-Link Portal url reminder(linky) for User to login and review/action the referral | Must | Must | The solution should assess the DRNS being separated into individual (3)summaries e.g. by Referral Type
CR5.0 | CDSP | I want data values used within the validation to be configurable | So that a functional change is not required should these values be changed in the future | 1) Parameterised Referral SLA values - please see the Referrals SLA Tab 2) Note: For each Referral Type, the trigger for the 'chaser' referral notification is effectively 3 SPSBDs however, parameterising the Referral SLAs Tab has the same effect. Therefore, the '3 day' SPSBD will not require being held in a parameter | Must | Must | The variables defined in the acceptance criteria are those known at this point however the hard coding of any potentially variable values should be avoided and, therefore, any other variables identified should be made configurable to reduce cost and impact of future change
CR5.1 | DN/IGT | I want the CDSP to provide a defined query and support request process to support any technical DRNS queries that I might have | So that if I have any issues I know how to make contact with the CDSP | Documented process for customers to raise queries and/or issues with any stage of the process where they interact with the CDSP - customers are informed of the process to follow should they experience an issue within the service defined within these Requirements | Must | Must | 

## Slide 16: Solution Overview
As-is steps
New step
Key

## Slide 17
Solution Option 1 Overview
A new daily report to provide a view of all the pending referral requests to the DNOs and IGTs. This could be split by referral types or LDZs if required.
The report is sent via email as an attachment and be split into tabs based on Referral types:
The Notification Summary will only be sent if there are any new referrals created post the
last job run or any pending referrals which require a chaser notification nearing the SLA timeline.
Distribution lists will be updated by raising a service request via SAP.
Referral Type | SLA Period | Chaser Notification
SLSP Signatory | 12 SPSBDs* | 9 SPSBDs after Referral Submission
Capacity - Increase | 21 SPSBDs | 18 SPSBDs after Referral Submission
Capacity – Decrease | 5 SPSBDs | 2 SPSBDs after Referral Submission
Distance Grid Ref | 12 SPSBDs | 9 SPSBDs after Referral Submission
Priority | TBD in Design | TBD in Design

## Slide 18
Solution Option 2 Overview
Allocate resources to manually log into the UK Link Portal each day, collate and inform relevant parties of outstanding referrals.
This option would maintain security of the data in the portal.
Ongoing Service costs absorbed into BAU. If existing volumes were to increase, we would need to revisit.

## Slide 19
Option Comparison
# | Description | Systems and process impacts | Cost Estimate Ranges | Option Pros | Option Cons
1 | New Daily Summary report delivered by Email | SAP ISU: A new daily report to provide a view of the referral requests Control-M: New process to schedule the report. SAP PO: Send out the files securely to the intended distribution lists via email. | Delivery: £145k to £180k | New development, no impact to existing processes Notification sent direct to users on managed distribution list | New process would require some information for end users on what to expect Email based solution which is not 100% secure
2 | Manual check process | Resource to monitor referrals and distribute as appropriate | Ongoing Service costs absorbed into BAU. If existing volumes were to increase, we would need to revisit. | No Delivery costs | Potential manual error Would still need to consider security requirements impacts when contacting external parties

## Slide 20
Category | Description
Assumptions | There is an assumption that National Gas Transmission are out of scope of this change
 | There is an assumption that IGTs are not willing to accept changes made to the IGR file.
 | There is an assumption there will be no market trials for any option
 | There is an assumption that PT will not be required for Option 1
 | Option 2: There is an assumption Xoserve will monitor the UK-Link Portal once, on a daily basis (timing tbc) and provide Referral Notifications to customers for new/outstanding (3 Day SLA) referrals for the previous day.
 | By providing proactive referral notifications to customers, Xoserve accepts no obligation to progress/action such referrals; this obligation remaining with customers
Risks | Option 1: There is a risk that email is not 100% secure even when attachments will be password protected.
Assumptions, Dependencies and Risks

## Slide 21: 3. Changes in Detailed Design

## Slide 22: 3a. Design Considerations
None for this meeting.

## Slide 23: 3b. Requirements Clarification
None for this meeting.

## Slide 24: 4. Release/Project Updates

## Slide 25: 4. Release/Project Updates
4a. XRN5818 – February 25 Major Release
4b. XRN5888 – Minor Release 14
4c. March 2025 DDP Update

## Slide 26: 4a. XRN 5818 – February 25 Major Release

## Slide 27: XRN 5818 – February 25 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 11/09. Progress Update: Detailed Design Change Pack approved at ChMC – 10/04/24. Build Completed – 17/01/25 Training Sessions (Online) Completed – 04/02/25 Testing Completed – 21/02/25 Onetime Reconciliation Reports (before Go-Live) generated and sent to IGTs on 26/02/25 Pre-Implementation Activities in progress; complete by 27/02 Upcoming Communications (Indicative): Confirmation of Planned Implementation (Email/Web) – 27/02 Successful/Unsuccessful Implementation (Email/Web) – 28/02 CCR (ChMC Deck) – 30/04 Decision in February ChMC: None |  | ​ Implementation date of 28th February, the contingency date is 07th March. | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5614 -Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 26th February 2025

## Slide 28: 4b. XRN 5888 – Minor Release 14

## Slide 29: XRN 5888 – Minor Release 14 - Status Update
Slide updated on 25th February 2025
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Overall release is tracking to a Green status. The 2 changes that form MiR 14 are due to commence Design by 28/02. The original scope of MiR 14 was presented for information in February ChMC.. The timeline to be confirmed for both XRNs associated to MiR 14 to be confirmed by 06/03, implementation is currently planned for May 2025. Progress update: Minor release 14 changes move into design by 28/02. Decision in March ChMC: None |  | 
Risks and Issues | N/A |  | 
Cost | Forecast to complete delivery against approved MTB funds |  | 
Scope | XRN 5769 – Changes required to Broadcast Service (Minor ones) XRN5549 – Automation of the UK Link and Gemini Mismatch analysis and correction process |  | 

## Slide 30: 4c. March 2025 DDP Update

## Slide 31: Agenda
Release Delivery
Latest focus
DDP Workgroup & Contact information

## Slide 32
Data Discovery Platform | Release 1 Proposals for 2025-2026
Suggested Features for Release 1 2025 – 2026. | 
Goals: | Shippers | DNs | IGTs
Core | Corrected & Uncorrected Reads display in relevant dashboards No Reads Industry Performance Analysis Industry Read Performance Analysis Shipper Portfolio Dashboard Enhancements | Further Charging Simulation Reporting Enhancements Charging and AQ insights: SOQ Trend Analysis | 
Stretch | AQ Scenario Analysis Reporting | Charging Simulation Overview: Longer Time Series Analysis | 

## Slide 33
Data Discovery Platform | Release 6
Update: Release delivery is underway following ChMC prioritization agreement last month. | 
Goals: | Shippers | DNs | IGTs
Core | AQ Data: AQ Trend Enhancements Portfolio Percentage Breakdown EUC Analysis improvements | DN Charging Improvements: AQ Load band Summary Enhancement Top 15 Invoicing Movements | IGT MDD Mismatch insight
Stretch | (From R5) Shipper Pack: Must read industry performance Meter Read Rejections Enhancements | Invoicing Data Refinements | 

## Slide 34: DDP Assurance Workgroup
For all DDP Releases we would like to request volunteers from the DDP User community to sponsor planned features.
The objective is to increase engagement in new Release features and help ensure we deliver features that meet the needs of our users.
This would involve:
  Contributing and supporting the relevant User Stories that sit behind proposed features, to promote benefits to wider industry
  Testing and First Usage assurance of new/updated dashboard features, to confirm satisfaction with the delivered content
For Release 5 we welcome all users to support first usage by assuring the new delivered features
For Release 6 onwards we will seek sponsors at the beginning of the process
Should you be able to support on Release 5 or 6 please contact the team via our operational email box account (ddp@xoserve.co.uk)

## Slide 35: DDP Team Contact Details
DDP Issues:
If you have an issue relating to DDP which you require support with, please raise a ticket via ‘help and support’ on xoserve.com here. This will ensure the issue is dealt with promptly and provides an audit trail
DDP Queries / Development / Shipper Forum:
If you have any queries, ideas or suggestions for future DDP features or questions relating to the DDP Shipper Forum please drop an email to the DDP Operational team via our box account: ddp@xoserve.co.uk
For avoidance of doubt, if you have an issue with DDP, the quickest way for a resolution is to raise a ticket

## Slide 36: 5. Change Pipeline

## Slide 37: 2025 Forward View - Change Delivery Plan January 25 – December 2025
Jan-25
June-25
February 25 – Major Release
XRN5614
March-25
Sep-25
Dec-25
June 25 – Major Release
XRN5784, XRN5846
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Implemented Change / Release
Delivery Key
Minor Release 14
XRN5888
Minor Release 15
(TBC)
Slide produced 27th February 2025
November 25 – Major Release
XRN5702 | XRN5872 | Mod0890
February 26 - Major Release
Adhoc Project
XRN5851 – Procurement and Service Activities
XRN5892 – Ring Fenced Budget for AUGE Value Add Services
Minor Release 16
(TBC)

## Slide 38: Change Delivery Plan – January 2025 – December 2025
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | *£120k revised following design | 28th February 2025 | Major | Firm
5549 | Automation of the UK Link and Gemini mismatch analysis and correction process | Xoserve | CDSP | N/A | N/A | May 2025 | Minor | Indicative
5769 | Changes required to Broadcast Service (minor changes | Xoserve | DN IGT | N/A | N/A | May 2025 | Minor | Indicative
5784 | Mod0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN | Shipper | £115k | 27th June 2025 | Major | Firm
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | £100k | 27th June 2025 | Major | Firm
5851 | Mod0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | TBC | June/July 2025 *subject to modification approval | Adhoc | Firm
5892 | Ring-fenced DSC Budget to support Allocation of Unidentified Gas Value-Add Activities | SEFE | Shipper | Shipper | TBC | June/July 2025 *subject to modification approval | Adhoc | Firm
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £230k *ROM est. | 7th November 2025 *options being presented @ Feb ChMC | Major | Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | TBC | £240k *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0890 – Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | Shipper DN | TBC | TBC | 7th November 2025 *subject to modification approval | Major | Indicative

## Slide 39
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | March ‘25 - ChMC Update
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target Q1 2025 update for DSC customers at DSG
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Requirements | Solution Options under development – Target February IGT consultation ahead of March ‘25 Change Pack
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | Analysis | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource
5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Cadent | DN IGT | DN | Requirements | Engagement with DNs and IGTs held. Requirements baselined October 2024, internal business requirements approved 9th December. Solutions and designs under development – Target March 2025 consultation
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Requirements | Change Proposal raised by Cadent – Solution analysis and ongoing collaboration taking place between CDSP and DN representatives Requirements signed off on 18th December with subject matter experts. Solution and designs under development – target March consultation.
5885 | Cease Provision of SC9 Files to Distribution Networks (DNs) | Cadent | DN | DN | Impact Assessment | Change Proposal raised by Cadent on behalf of DNs – seeking to prevent SC9 files being delivered to DNs as these are no longer required. Changes being impact assessed ahead of confirmation on next steps
XXXX | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | TBC | Mod Development | Added to change backlog for early visibility as potential that change will require development in 2025/26 Anticipated Major UK Link Delivery in 2026
XXXX | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period | SSE | Shipper DN IGT | TBC | Mod Development | Added to change backlog for early visibility as potential that change will require development in 2025/26 Anticipated Minor / Adhoc UK Link Delivery
XXXX | Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE | Shipper DN IGT | TBC | Mod Development £50K *ROM est. | Following analysis it has been confirmed that the Modification is now targeting a big bang implementation on 1st April 26 Anticipated Minor / Adhoc UK Link Delivery
Change Backlog – ‘In Progress’ Details

## Slide 40: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | March ‘25 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Tbc | Agreed following September ChMC that change would be placed on hold whilst data cleansing activities were progressed – change to be revisited in January with DNs / IGTs
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | N/A | N/A | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | Tbc | Tbc | Continue to support regulatory development and provide update to ChMC once status of Modification changes

## Slide 41: DSC Change Pack Consultation Plan (2 month view)
Mar – 25
April - 25
May – 25
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 27th February 2025
XRN5569 - Contact Data Provision for IGT Customers
XRN5808 - Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action
XRN5810 - Theft of Gas (ToG) DN Calculation Tool
XRN5872 - Mod0876S Updates to the Annual Quantity (AQ) amendment process

## Slide 42: 6. AOB

## Slide 43: Annex – For Information

## Slide 44: 7. DSC Change Management Committee Update
ChMC Wednesday 12th March Meeting

## Slide 45: Change Management Committee Update –12.03.25 ChMC Meeting
The Change Management Committee post meeting update can be found here. ​

## Slide 46: 8. REC Change Update

## Slide 47: 9. Portfolio Delivery

## Slide 48: 9. Portfolio Delivery Overview POAP
The POAP is available here.