## Change Register
Last Updated | Reference Number | Change Title | Status | Origination Date | Proposer | Customer Change Team Lead | Release Type | Implementation Date | DSC Service Area | Shipper Impact | DNO Impact | IGT Impact | NGT Impact | Supplier Impact | GT Impact | Comsumer Impact | DCC Impact | DMSP Impact | MAP Impact
2019-01-10 | XRN 3667a | Provision of Formula Year AQ/SOQ to Proposing Users | Implemented | 2019-01-10 | Npower | uklink@xoserve.com | Ad-hoc | 28/02/2019 | Service Area 22: Specific Services | Yes | No | No | No | No
2019-01-10 | XRN 4044 | Extension of ‘Must Read’ process to include Annual Read sites | Withdrawn | 2019-01-10 | National Grid | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | No | No
2020-10-07 | XRN 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | Implemented | 2019-01-10 | National Grid | uklink@xoserve.com | Ad-hoc | 08/09/2019 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2022-04-19 | XRN 4550 | Gemini Re-platform | Implemented | 2019-01-10 | National Grid | uklink@xoserve.com | Ad-hoc | 05/07/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2019-11-08 | XRN 4621 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | Implemented | 2019-01-11 | Orsted | uklink@xoserve.com | Major | 08/11/2019 | Service Area 22: Specific Services | Yes | No | No | No | No
2019-01-11 | XRN 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/11/2018 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | Yes | No | No
2019-01-11 | XRN 4653 | National Grid Transmission iConversion Project | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/03/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2019-10-01 | XRN 4665 | Creation of new End User Categories | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Major | 31/08/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | Yes | Yes | No
2019-12-08 | XRN 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No
2019-08-14 | XRN 4687 | PSR updates for large domestic sites | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Major | 28/06/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2019-02-18 | XRN 4690 | Actual read following estimated transfer read calculating AQ of 1 | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Minor | 16/02/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No
2020-06-03 | XRN 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No
2020-06-03 | XRN 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No
2019-01-11 | XRN 4693 | CSEPs: IGT and GT File Formats. Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No
2019-01-11 | XRN 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No
2019-03-30 | XRN 4695 | Investigating causes and contributors to levels and volatility of Unidentified Gas | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Ad-hoc | 30/03/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2019-01-11 | XRN 4777 | Acceptance of Contact Details Updates | Implemented | 2019-01-11 | EDF Energy | uklink@xoserve.com | Minor | 27/07/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-01-27 | XRN 4779 | UNC Modification 0657S - Adding AQ reporting to the PARR Schedule reporting suite | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Ad-hoc | 11/03/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2022-01-24 | XRN 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Implemented | 2019-01-11 | SSE | uklink@xoserve.com | Major | 22/01/2022 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2020-05-13 | XRN 4785 | SSN Error proofing | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2019-08-01 | XRN 4786 | Provision of Gemini data to Ofgem | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | No | No | No | Yes | No
2020-05-13 | XRN 4787 | Rescheduling of failed SSN | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2019-12-18 | XRN 4789 | Updating Shipper Reporting Packs and glossary | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Ad-hoc | 31/07/2019 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | Yes | No
2019-01-11 | XRN 4790 | Introduction of winter read/consumption reports and associated obligation (MOD0652) | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Ad-hoc | 12/07/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-01-20 | XRN 4795 | Amendments to the PARR (520a) reporting | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Ad-hoc | 15/11/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | No | No | No
2019-11-11 | XRN 4800 | TSO Visibility of System Balance at Interconnection Points | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2020-10-08 | XRN 4801 | Additional information to be made viewable on DES | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Major | 07/11/2020 | Service Area 22: Specific Services | Yes | No | No | No | No
2019-01-14 | XRN 4706 | National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | Implemented | 2019-01-14 | National Grid | uklink@xoserve.com | Ad-hoc | 31/10/2019 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2023-09-15 | XRN 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Ad-hoc | 27/06/2023 |  | Yes | No | No | No | No
2019-02-18 | XRN 4717 | Use of up to date Forecast weather data in first NDM Nominations | Implemented | 2019-01-14 | Total Gas and Power | uklink@xoserve.com | Minor | 16/02/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No
2019-11-08 | XRN 4725 | New Read Reason Type for LIS Estimate Readings | Implemented | 2019-01-14 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No
2019-01-14 | XRN 4738 | Shipper Portfolio Update of Proposed Formula Year AQ/SOQ | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Ad-hoc | 31/03/2020 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | Yes | Yes | No | No
2019-01-14 | XRN 4747 | Smart Meter Upgrade Notification Report | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Ad-hoc | 18/01/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2019-01-14 | XRN 4752 | Meter Read Performance | Implemented | 2019-01-14 | Xoserve | uklink@xoserve.com | Ad-hoc | 15/03/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | Yes | No
2019-01-14 | XRN 4753 | CMS - Increase Information Provided in QCL Response File | Withdrawn | 2019-01-14 | BU-UK | uklink@xoserve.com | Major | 08/11/2019 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | Yes | No | No
2019-01-14 | XRN 4770 | NDM Sample Data – Mod 0654 Delivery | Implemented | 2019-01-14 | E.ON | uklink@xoserve.com | Minor | 22/02/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No
2019-12-23 | XRN 4772 | Composite Weather Variable (CWV) Improvements | Implemented | 2019-01-14 | E.ON | uklink@xoserve.com | Major | 27/06/2020 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No
2019-01-14 | XRN 4803 | Amend AQI validation/processing | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Minor | 27/07/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No
2019-01-14 | XRN 4806 | Additional data at National Level to support UIG Allocation validation | Implemented | 2019-01-14 | Scottish Power | uklink@xoserve.com | Ad-hoc | 29/03/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No
2019-01-14 | XRN 4813 | Migration of Xoserve Interfaces | Implemented | 2019-01-14 | National Grid | uklink@xoserve.com | Ad-hoc | 29/04/2019 |  | No | No | No | Yes | No
2023-10-05 | XRN 4810 | Chat Bot Automated Gemini Assistant | Withdrawn | 2019-01-14 11:01 | National Grid | uklink@xoserve.com | Unallocated | TBC |  | No | No | No | Yes | No
2020-01-27 | XRN 4273 | Introducing IHD (In-Home Display) Installed Status of Failed MOD reference 614 | Implemented | 2019-01-15 | EDF Energy | uklink@xoserve.com | Major | 01/02/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2019-01-15 | XRN 4534 | Amendment to RGMA Validation Rules for Meter Asset Installation Date | Implemented | 2019-01-15 | Centrica | uklink@xoserve.com | Major | 01/02/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2019-01-15 | XRN 4572 | Release 3 Detailed Design Delivery | Implemented | 2019-01-15 | Xoserve | uklink@xoserve.com | Major | 01/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2019-11-08 | XRN 4828 | Nov-19 Release Delivery | Implemented | 2019-01-16 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | N/A: Not applicable | Yes | Yes | Yes | No | No
2019-01-16 | XRN 4833 | Roll Out of Business Intelligence and Data Discovery Capability | Implemented | 2019-01-16 | Xoserve | uklink@xoserve.com | Ad-hoc | 07/05/2019 |  | Yes | Yes | Yes | Yes | No
2019-01-17 | XRN 4453 | Amendment to JOB / UPD Hierarchies to show ‘Irrelevant Datasets’ - Confirmation of File Format Changes and clarification on Version Control | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Minor | 01/03/2019 | N/A: Not applicable | Yes | No | No | No | No
2019-01-17 | XRN 4626 | Provision of an alternative Consumer Enquiry Service (Mnumber) - PHASE TWO Non-Web Portal Implementation | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/07/2019 | N/A: Not applicable | No | No | No | No | No
2020-12-14 | XRN 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Ad-hoc | 29/10/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2019-01-17 | XRN 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 |  | Yes | No | No | No | No
2020-02-12 | XRN 4676 | Reconciliation issues with reads recorded between D-1 to D-5 | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 |  | Yes | No | No | No | No
2020-01-27 | XRN 4824 | National Grid Transmission Daily Gemini Report | Withdrawn | 2019-01-17 | National Grid Transmission | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2020-01-27 | XRN 4454 | National Grid and Cadent Enduring Invoicing Arrangements | Implemented | 2019-01-23 | National Grid | uklink@xoserve.com | Major | 02/02/2019 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | No | No | Yes | No
2019-02-05 | XRN 4686 | Smart Metering Report | Withdrawn | 2019-02-05 | CNG | uklink@xoserve.com | Ad-hoc | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-03-12 | XRN 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | Implemented | 2019-02-14 | E.ON | uklink@xoserve.com | Ad-hoc | 28/02/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | Yes | No | No
2019-02-14 | XRN 4853 | Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only (UIG Recommendation 3.1 option 5) | Implemented | 2019-02-14 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No
2019-02-14 | XRN 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | Withdrawn | 2019-02-14 | Cadent | uklink@xoserve.com | Unallocated | TBC | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No
2020-07-13 | XRN 4860 | National ‘Temporary’ UIG Monitoring (1) | Withdrawn | 2019-02-14 | Npower | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-05-18 | XRN 4716 | Increased Field Length – ‘Updated by’ data item | Withdrawn | 2019-02-15 | SGN | uklink@xoserve.com | Minor | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2020-05-15 | XRN 4850 | Notification of Customer Contact Details to Transporters | Implemented | 2019-02-18 | Wales & West Utilities | uklink@xoserve.com | Major | 27/06/2020 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | Yes | No | No
2019-02-18 | XRN 4852 | Amendments to the DSC Change Management Procedures – aligning the procedures to the change process | Withdrawn | 2019-02-18 | E.ON | uklink@xoserve.com | Ad-hoc | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2020-01-27 | XRN 4858 | Service Description Table updates February 2019 | Implemented | 2019-02-18 | Xoserve | uklink@xoserve.com | Ad-hoc | 28/02/2019 |  | Yes | Yes | Yes | Yes | No
2019-12-23 | XRN 4865 | Amendment to Treatment and Reporting of CYCL Reads | Implemented | 2019-03-05 | Xoserve | uklink@xoserve.com | Major | 27/06/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2021-07-13 | XRN 4876 | Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | Implemented | 2019-03-05 | Gemserv | uklink@xoserve.com | Ad-hoc | 02/06/2021 | N/A: Not applicable | Yes | No | No | No | No
2019-05-21 | XRN 4866 | Removal of validation on uncorrected read (UIG Recommendation) | Implemented | 2019-03-06 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No
2023-11-15 | XRN 4869 | DC Exit Programme | Implemented | 2019-03-06 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/12/2022 | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No
2020-09-22 | XRN 4871 | Modification 0665 - Changes To Ratchet Regime | Implemented | 2019-03-06 | Gazprom Energy | uklink@xoserve.com | Major | 07/11/2020 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | Yes | No | No
2020-04-09 | XRN 4887 | Service Description Table updates March 2019 | Implemented | 2019-03-06 | Xoserve | uklink@xoserve.com | Ad-hoc | 28/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2019-12-23 | XRN 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Implemented | 2019-03-06 | BU UK | uklink@xoserve.com | Major | 27/06/2020 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | Yes | No | No
2019-03-14 | XRN 4894 | Shipperless and Unregistered Pre-Payment Supply Points Reconciliation | Withdrawn | 2019-03-14 | SGN | uklink@xoserve.com | Unallocated | TBC | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | No | No | No
2019-01-01 | XRN 4542 | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | Implemented | 2019-03-21 | Gazprom | uklink@xoserve.com | Ad-hoc | 16/11/2018 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2023-11-14 | XRN 4914 | MOD 0651- Retrospective Data Update Provisions | Withdrawn | 2019-04-04 | Cadent | uklink@xoserve.com | Major | TBC |  | Yes | Yes | Yes | Yes | No
2022-08-23 | XRN 4920 | Review of the CSSC (Central Switching Service Consequential Changes) Gemini Business Requirements Document | Implemented | 2019-04-17 | Xoserve | uklink@xoserve.com | Major | 18/07/2022 | N/A: Not applicable | Yes | No | No | No | No
2022-08-23 | XRN 4921 | Review of the CSSC (Central Switching Service Consequential Changes) GT and IGT Business Requirements Document | Implemented | 2019-04-17 | Xoserve | uklink@xoserve.com | Major | 18/07/2022 | N/A: Not applicable | No | Yes | Yes | No | No
2022-08-23 | XRN 4922 | Review of the CSSC (Central Switching Service Consequential Changes) Shipper Business Requirements Document | Implemented | 2019-04-17 | Xoserve | uklink@xoserve.com | Major | 18/07/2022 | N/A: Not applicable | Yes | No | No | No | No
2019-12-23 | XRN 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Implemented | 2019-04-23 | E.ON | uklink@xoserve.com | Major | 27/06/2020 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | Yes | No | No
2019-07-04 | XRN 4732 | June -19 Release Delivery | Implemented | 2019-04-24 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 | N/A: Not applicable | Yes | No | No | No | No
2019-12-23 | XRN 4930 | Requirement to inform Shipper of Meter Link Code Change | Implemented | 2019-04-30 | Xoserve | uklink@xoserve.com | Major | 27/06/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2022-01-24 | XRN 4941 | Auto updates to meter read frequency (MOD0692) | Implemented | 2019-05-17 | Total Gas & Power | uklink@xoserve.com | Major | 22/01/2022 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2019-11-04 | XRN 4946 | Reporting on Installed Meters with Conversion Capability | Withdrawn | 2019-05-30 | SSE | uklink@xoserve.com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2020-03-03 | XRN 4955 | Amendment of MDD PSR Needs Codes and Needs Code Descriptions | Implemented | 2019-05-30 | Wales & West Utilities | uklink@xoserve.com | Minor | 29/02/2020 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | No | No
2019-10-16 | XRN 4954 | Minor Release Drop 5 | Implemented | 2019-06-05 | Xoserve | uklink@xoserve.com | Minor | 07/09/2019 | N/A: Not applicable | Yes | Yes | Yes | No | No
2019-07-04 | XRN 4977 | Amendments to DSC Change Management Guidelines | Implemented | 2019-07-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 07/08/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-03-23 | XRN 4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | Implemented | 2019-07-08 | British Gas | uklink@xoserve.com | Major | 25/02/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2020-01-16 | XRN 4980 | Change Supply Point Enquiry API to add in extra field and make certain other fields visible | Implemented | 2019-07-12 | Total Gas & Power | uklink@xoserve.com | Ad-hoc | 12/12/2020 | Service Area 22: Specific Services | Yes | No | No | No | No
2020-09-08 | XRN 4896 | Failure to Supply Gas System and Template Amendment | Implemented | 2019-07-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 14/08/2020 | Service Area 4 (Previous Dec 18 – Mar 21): Interruption Auction Services in accordance with UNC | Yes | Yes | No | No | No
2020-05-05 | XRN 4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Withdrawn | 2019-07-30 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No
2023-03-23 | XRN 4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | Implemented | 2019-08-01 | SSE | uklink@xoserve.com | Major | 25/02/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2019-09-18 | XRN 4991 | Enabling large scale utilisation of Class 3 – MOD0700 | Implemented | 2019-08-01 | Gazprom | uklink@xoserve.com | Ad-hoc | 28/09/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No
2023-03-28 | XRN 4992 | Modification 0797 (Urgent) - Last Resort Supply Payments Volumetric Charges | Implemented | 2019-08-01 | Total Gas and Power | uklink@xoserve.com | Major | 25/02/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | Yes | No | No | No
2019-09-04 | XRN 4993 | DSC Service Description Table cosmetic change to service line table as of April 2019 | Implemented | 2019-08-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 28/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2019-08-02 | XRN 4994 | PAFA Contract Extension 2019/20 | Withdrawn | 2019-08-02 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2022-07-18 | XRN 4995 | Procurement of a Laboratory Study of within-pipe gas temperatures | Withdrawn | 2019-08-02 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-01-27 | XRN 4996 | June 2020 Release Delivery | Implemented | 2019-08-12 | N/A - Parent XRN | uklink@xoserve.com | Major | 27/06/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No
2019-11-27 | XRN 5003 | Data Access Platform DN Dashboard | Implemented | 2019-09-03 | Northern Gas Networks | uklink@xoserve.com | Ad-hoc | 25/10/2019 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | No | No | No
2019-12-13 | XRN 5004 | Golden Bullet Report | Implemented | 2019-09-03 | Wales & West Utilities | uklink@xoserve.com | Ad-hoc | 01/10/2020 | Service Area 18: Provision of User Reports and Information | No | Yes | No | No | No
2020-03-03 | XRN 4997 | Introducing new charge codes for GSoP3, GSoP13 and GT Voluntary Consumer Payments | Implemented | 2019-09-12 | Northern Gas Networks | uklink@xoserve.com | Minor | 29/02/2020 | Service Area 21: Data Flows and Services to Network Operators | Yes | Yes | No | No | No
2022-08-23 | XRN 4627 | CSS Consequential Central Switching Services | Implemented | 2019-09-18 | Ofgem | uklink@xoserve.com | Major | 18/07/2022 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2020-01-14 | XRN 5027 | UK Link Data Cleanse of Conversion Factor in line with MOD0681S | Withdrawn | 2019-10-01 | E.ON | uklink@xoserve.com | Ad-hoc | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2020-04-09 | XRN 5029 | Service Description Table updates October 2019 | Implemented | 2019-10-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 24/10/2019 | N/A: Not applicable | No | Yes | Yes | No | No
2020-09-11 | XRN 4897 | Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event | Implemented | 2019-10-14 | Xoserve | uklink@xoserve.com | Major | 07/11/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2020-05-15 | XRN 4899 | Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event | Implemented | 2019-10-14 | Xoserve | uklink@xoserve.com | Major | 07/11/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2020-01-27 | XRN 5013 | Performance Assurance Framework Administrator Access to Data Discovery Platform | Implemented | 2019-10-14 | SSE | uklink@xoserve.com | Ad-hoc | 31/01/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-01-27 | XRN 5033 | Addition of low-level data to EUC Report | Implemented | 2019-11-06 | British Gas | uklink@xoserve.com | Ad-hoc | 16/12/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2020-07-03 | XRN 5036 | Updates to must read process | Implemented | 2019-11-06 | Cadent Gas | uklink@xoserve.com | Minor | 04/07/2020 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | No | Yes | No | No | No
2021-04-30 | XRN 5038 | Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691) | Implemented | 2019-11-06 | British Gas | uklink@xoserve.com | Ad-hoc | 01/04/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2020-07-13 | XRN 5053 | Single Sided Nominations Improvements | Implemented | 2019-12-04 | National Grid | uklink@xoserve.com | Ad-hoc | 05/04/2020 | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No
2020-08-12 | XRN 5054 | Negative Implied Flow Rates | Implemented | 2019-12-04 | National Grid | uklink@xoserve.com | Ad-hoc | 05/04/2020 | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No
2020-01-27 | XRN 5057 | Minor Release Drop 6 | Implemented | 2019-12-18 | CDSP | uklink@xoserve.com | Minor | 29/02/2020 | N/A: Not applicable | Yes | Yes | No | Yes | No
2020-03-31 | XRN 5064 | Meter Asset Enquiry API Enhancements | Implemented | 2019-12-18 | CDSP | uklink@xoserve.com | Ad-hoc | 28/03/2020 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | No | No
2020-08-17 | XRN 5065 | Addition of Email Address to DES Last Accessed Report | Implemented | 2019-12-18 | Scottish Power | uklink@xoserve.com | Minor | 04/07/2020 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2021-01-11 | XRN 5014 | Facilitating HyDeploy2 Live Pilot | Implemented | 2020-01-02 | Northern Gas Network | uklink@xoserve.com | Major | 07/11/2020 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No
2020-02-03 | XRN 5048 | Make an indicator available where a Supply Meter Point form part of a Network Trial | Withdrawn | 2020-01-02 | Northern Gas Network | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | No | No
2020-01-17 | XRN 5070 | Amendment to Isolation Flag | Withdrawn | 2020-01-02 | E.ON | uklink@xoserve.com | Ad-hoc | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2022-01-24 | XRN 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | Implemented | 2020-01-02 | Xoserve | uklink@xoserve.com | Major | 22/01/2022 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2021-04-06 | XRN 5080 | Failure to Supply Gas (FSG/GSOP1) – System Changes | Implemented | 2020-01-30 | Scotland and Southern Gas Networks SGN | uklink@xoserve.com | Minor | 20/03/2021 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | Yes | No | No
2023-09-15 | XRN 5091 | Deferral of creation of Class change reads at transfer of ownership | Implemented | 2020-01-31 | EDF | uklink@xoserve.com | Major | 24/06/2023 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | No | No | No | No
2020-11-05 | XRN 5092 | iConversion Phase 2 | Implemented | 2020-01-31 | National Grid - Gas | uklink@xoserve.com | Ad-hoc | 22/08/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2021-06-25 | XRN 5093 | Update of AUG Table to reflect new EUC bands | Implemented | 2020-01-31 | Gazprom | uklink@xoserve.com | Major | 25/06/2021 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No
2020-08-12 | XRN 5097 | DSC Service Description Table cosmetic change to service line table v9 | Implemented | 2020-02-03 | CDSP - Xoserve | uklink@xoserve.com | Ad-hoc | 28/02/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2021-07-13 | XRN 5110 | November 20 Release Delivery | Implemented | 2020-02-27 | Xoserve | uklink@xoserve.com | Major | 07/11/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No
2021-06-11 | XRN 5120 | MAP to UKL Monthly Comparison Service | Withdrawn | 2020-02-27 | E.ON | uklink@xoserve.com | Ad-hoc | TBC | Service Area 18: Provision of User Reports and Information | No | No | No | No | No
2020-08-13 | XRN 5116 | Domestic Report - Must Read Prenotification | Withdrawn | 2020-02-28 | British Gas | uklink@xoserve.com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2020-03-19 | XRN 5121 | Supplier Portfolio Service | Withdrawn | 2020-02-28 | CDSP | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | No | No | No | No
2021-12-09 | XRN 5122 | Gemini System Enhancements - Delivery | Implemented | 2020-03-02 | National Grid | uklink@xoserve.com | Ad-hoc | 25/07/2021 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No
2020-08-12 | XRN 5123 | DSC Service Description Table cosmetic change to Service Line Table | Implemented | 2020-03-02 | Xoserve | uklink@xoserve.com | Ad-hoc | 23/03/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2021-11-15 | XRN 5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | Implemented | 2020-03-27 | Northern Gas Networks | uklink@xoserve.com | Major | 05/11/2021 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | No | No | No | No
2023-07-14 | XRN 5143 | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP | Implemented | 2020-03-27 | Cadent Gas | uklink@xoserve.com | Ad-hoc | 01/04/2023 | TBC: To be confirmed | Yes | Yes | No | No | No
2021-01-18 | XRN 5145 | DSC Service Description Table cosmetic change to Service Line Table v11 | Implemented | 2020-03-30 | CDSP - Xoserve | uklink@xoserve.com | Ad-hoc | 14/10/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-11-20 | XRN 5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Withdrawn | 2020-03-31 | CDSP | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | Yes | Yes | No
2021-03-16 | XRN 5146 | Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | Implemented | 2020-03-31 | Northern Gas | uklink@xoserve.com | Ad-hoc | 15/02/2021 | Service Area 11 (Previous Dec 18 – Mar 21): NExA Supply Meter Points | Yes | Yes | Yes | No | No
2020-04-15 | XRN 5147 | Optimising the Must Read process for IGT Customers | Withdrawn | 2020-03-31 | BUUK | uklink@xoserve.com | Ad-hoc | TBC | Service Area 22: Specific Services | No | No | Yes | No | No
2020-07-13 | XRN 5156 | REC121 Report Amendment | Implemented | 2020-04-29 | NGN - Northern Gas Networks | uklink@xoserve.com | Ad-hoc | 24/04/2020 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | No | No | No
2020-05-21 | XRN 5161 | UIG_Additional_National_Data_YYYYMM Frequency Change | Implemented | 2020-04-29 | Inspired Energy | uklink@xoserve.com | Ad-hoc | 22/05/2020 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No
2021-08-12 | XRN 4931 | Submission of a Space in Mandatory Data on Multiple SPA Files | Withdrawn | 2020-04-30 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2020-11-09 | XRN 5167 | Report Product Class 4 Read Performance (MOD 672) | Implemented | 2020-05-04 | Scottish Power | uklink@xoserve.com | Ad-hoc | 28/08/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No
2020-05-05 | XRN 5164 | CSEP Data Assurance Performance Monitoring Capability | Implemented | 2020-05-05 | Wales & West Utilities | uklink@xoserve.com | Ad-hoc | 09/10/2020 | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No
2020-11-09 | XRN 5168 | MOD0721 (Urgent) - Shipper submitted AQ Corrections during COVID-19 | Withdrawn | 2020-05-05 | Gaz Prom | uklink@xoserve.com | Ad-hoc | TBC | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | Yes | Yes | No | No
2021-05-27 | XRN 5169 | UNMOD0722 (Urgent): Allow Users to submit Estimated Meter Reading during COVID-19 | Implemented | 2020-05-05 | Gaz Prom | uklink@xoserve.com | Ad-hoc | 12/05/2020 | TBC: To be confirmed | Yes | No | No | No | No
2021-05-27 | XRN 5170 | MOD0723 (Urgent): Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | uklink@xoserve.com | Ad-hoc | 12/05/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2021-05-27 | XRN 5171 | MOD0724 (Urgent): Amendment to Ratchet charges during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | uklink@xoserve.com | Ad-hoc | 12/05/2020 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | Yes | No | No
2020-09-24 | XRN 5172 | Urgent Mod - Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | Withdrawn | 2020-05-11 | Gazprom | uklink@xoserve.com | Unallocated | TBC |  | Yes | Yes | Yes | No | No
2023-11-06 | XRN 5186 | Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | Implemented | 2020-06-01 | NGN | uklink@xoserve.com | Major | 04/11/2023 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | No | No | No
2023-10-04 | XRN 5187 | Modification 0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Withdrawn | 2020-06-01 | Gazprom | uklink@xoserve.com | Major | TBC | Service Area 11 (Previous Dec 18 – Mar 21): NExA Supply Meter Points | Yes | Yes | No | No | No
2023-03-28 | XRN 4989 | Online end to End Credit Interest process - Defect 1063 | Implemented | 2020-06-02 | CDSP | uklink@xoserve.com | Minor | 20/11/2020 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | No | No | No | No
2021-07-13 | XRN 5188 | Interim Data Loads of MAP Id into UK Link | Implemented | 2020-06-04 | CDSP | uklink@xoserve.com | Minor | 04/09/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No
2022-01-24 | XRN 5007 | Correction in the reconciliation process when volume is zero | Implemented | 2020-06-29 | Xoserve | uklink@xoserve.com | Major | 22/01/2022 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No
2020-07-03 | XRN 5192 | CMS Reference Number in Amendment Invoice Supporting Data | Withdrawn | 2020-06-29 | N Power | uklink@xoserve.com | Unallocated | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | No | No
2020-06-29 | XRN 5193 | Stop MUR Generation of GT SMPs | Withdrawn | 2020-06-29 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | No | No | No
2021-01-19 | XRN 5195 | Ceased Responsibility Date Following Shipper Withdrawal (IDL) | Withdrawn | 2020-06-29 | Indigo Pipelines | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | No | No | Yes | No | No
2020-06-29 | XRN 5196 | Address Amendments Validation | Withdrawn | 2020-06-29 | BU-UK | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | Yes | No | Yes | No | No
2020-07-23 | XRN 5197 | QMP File Validation in CMS – Current Address field | Withdrawn | 2020-06-29 | Indigo Pipelines | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | Yes | No | Yes | No | No
2020-06-29 | XRN 5199 | Amendments to V12 of the SDT Service Description Table | Implemented | 2020-06-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/07/2020 | Service Area 21: Data Flows and Services to Network Operators | Yes | Yes | Yes | Yes | No
2025-09-10 | XRN 5200 | Shipper Pack Transition to Data Discovery Platform | Implemented | 2020-07-01 | E.ON | uklink@xoserve.com | Ad-hoc | 12/08/2025 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No
2021-01-12 | XRN 5206 | TPI/PCW Access | Implemented | 2020-07-08 | ENGIE | uklink@xoserve.com | Ad-hoc | 15/01/2021 | Service Area 24: Additional Service Request or Third Party Request | No | Yes | No | No | No
2021-06-10 | XRN 5153 | iConversion Phase 2 | Implemented | 2020-07-15 | Xoserve | uklink@xoserve.com | Ad-hoc | 07/08/2020 | Service Area 20: UK Link Gemini System Services | No | Yes | No | No | No
2021-01-19 | XRN 5209 | Amendments to the CDSP Service Document - Budget & Charging Methodology v4 | Implemented | 2020-07-16 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2021 | N/A: Not applicable | No | No | No | No | No
2021-02-11 | XRN 5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | Implemented | 2020-07-23 | Wales & West Utilities | uklink@xoserve.com | Minor | 20/03/2021 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | Yes | No
2022-01-24 | XRN 5180 | Inner Tolerance Validation for replacement reads and read insertions | Implemented | 2020-07-28 | CDSP | uklink@xoserve.com | Major | 22/01/2022 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No
2021-07-06 | XRN 5218 | CDSP provision of Class 1 read service | Withdrawn | 2020-08-03 | Wales and West Utilities | uklink@xoserve.com | Ad-hoc | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | Yes | No
2021-01-19 | XRN 5181 | Acceptance of Consumption Adjustment where meter removed after meter point set to Dead | Implemented | 2020-08-11 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 | Service Area 4 (Previous Dec 18 – Mar 21): Interruption Auction Services in accordance with UNC | Yes | Yes | No | No | No
2021-12-09 | XRN 5183 | Access to Daily Biomethane Injections | Implemented | 2020-08-19 | Inspired Energy PLC | uklink@xoserve.com | Ad-hoc | 09/11/2021 | Service Area 18: Provision of User Reports and Information | Yes | Yes | No | No | No
2020-12-22 | XRN 5225 | Minor Release Drop 8 | Implemented | 2020-08-27 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | Yes | Yes | Yes | No | No
2023-02-13 | XRN 5231 | Provision of a FWACV Service | Implemented | 2020-08-28 | SGN | uklink@xoserve.com | Ad-hoc | 27/08/2022 |  | Yes | Yes | No | Yes | No
2020-09-16 | XRN 5118 | Change to how ‘Actual MR date’ field is populated in UK Link | Implemented | 2020-09-02 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | No | No | No | No | No
2021-01-19 | XRN 5174 | Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | Implemented | 2020-09-02 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | No | No | No | No | No
2020-09-11 | XRN 5152 | Minor Release Drop 7 | Implemented | 2020-09-03 | CDSP | uklink@xoserve.com | Minor | 04/07/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No
2020-11-03 | XRN 5210 | Daily CV Determination Interim Service: DN Invoicing Options | Withdrawn | 2020-09-09 | National Grid Gas | uklink@xoserve.com | Minor | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | Yes | No | Yes | No
2021-01-27 | XRN 5237 | Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736) | Implemented | 2020-09-24 | CDSP | uklink@xoserve.com | Ad-hoc | 14/01/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2022-02-16 | XRN 5235 | Request for access to SOQ data & capacity figures which influence transportation charges. | Implemented | 2020-09-25 | Gazprom Energy | uklink@xoserve.com | Ad-hoc | 17/12/2021 | Service Area 18: Provision of User Reports and Information | Yes | Yes | No | No | No
2023-10-04 | XRN 5236 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | Implemented | 2020-09-25 | Gazprom Energy | uklink@xoserve.com | Ad-hoc | 01/04/2023 | N/A: Not applicable | Yes | No | No | No | No
2022-05-04 | XRN 5238 | New Distribution Network Report – Forecast Invoice Values | Withdrawn | 2020-09-25 | Northern Gas Networks | uklink@xoserve.com | Ad-hoc | TBC | TBC: To be confirmed | No | Yes | No | No | No
2020-10-12 | XRN 5244 | Shared IGT Deeds of Undertaking and CDSP Administration | Withdrawn | 2020-09-25 | BUUK | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | No | No | Yes | No | No
2021-07-13 | XRN 5246 | Confirmation File (.CNF) Processing Capacity Improvement | Implemented | 2020-09-25 | CDSP | uklink@xoserve.com | Minor | 04/09/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2020-10-06 | XRN 5203 | Perspective Supply Metering Point AQ and EUC | Withdrawn | 2020-10-06 | Gazprom Energy | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | Yes | No | No | No | No
2020-10-12 | XRN 5252 | Amending the Formula Year AQ approach for 2021/2 Formula Year (Urgent MOD 0740) | Withdrawn | 2020-10-12 | EON | uklink@xoserve.com | Ad-hoc | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No
2021-11-15 | XRN 5251 | Gemini Exit Zone Change | Implemented | 2020-10-29 | National Grid | uklink@xoserve.com | Ad-hoc | 26/09/2021 | Service Area 20: UK Link Gemini System Services | Yes | No | No | No | No
2022-04-21 | XRN 5253 | June 21 Release | Implemented | 2020-10-29 | CDSP | uklink@xoserve.com | Major | 25/06/2021 | N/A: Not applicable | Yes | Yes | Yes | No | No
2021-01-19 | XRN 5273 | Amendments to V14 of the Service Description Table | Implemented | 2020-10-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 18/11/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No
2021-03-24 | XRN 5285 | COVID-19 Capacity Retention Process (Mod 0730V) | Withdrawn | 2020-11-30 | CDSP | uklink@xoserve.com | Ad-hoc | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | Yes | No
2020-12-14 | XRN 5286 | Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) | Withdrawn | 2020-11-30 | CDSP | uklink@xoserve.com | Ad-hoc | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No
2021-05-18 | XRN 5294 | Minor Release Drop 9 | Implemented | 2020-12-22 | CDSP | uklink@xoserve.com | Minor | 20/03/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-07-18 | XRN 5289 | November 21 Major Release | Implemented | 2020-12-31 | Xoserve | uklink@xoserve.com | Major | 22/01/2022 | N/A: Not applicable | Yes | Yes | Yes | No | No
2021-12-09 | XRN 5290 | CNC Bulk Network Report | Withdrawn | 2020-12-31 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | Yes | No | No
2021-01-05 | XRN 5307 | Amendments to V15 of the Service Description Table | Implemented | 2021-01-05 | CDSP | uklink@xoserve.com | Ad-hoc | 20/01/2021 | N/A: Not applicable | Yes | Yes | Yes | No | No
2023-03-28 | XRN 5298 | H100 Fife Project - Phase 1 (Initial Assessment) | Implemented | 2021-01-18 | SGN | uklink@xoserve.com | Major | 25/02/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | Yes | Yes | No | No
2022-04-27 | XRN 5299 | Future Billing Methodology (analysis only) | Withdrawn | 2021-01-21 | Cadent | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | Yes | No
2021-07-13 | XRN 5309 | FSG - Automating the FSR ‘Standard Liability’ process | Implemented | 2021-01-21 | SGN | uklink@xoserve.com | Minor | 04/09/2021 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | Yes | No | No | No
2022-01-10 | XRN 5318 | Assessing Supplier MPID Reassignment | Implemented | 2021-02-01 | E.ON | uklink@xoserve.com | Ad-hoc | 08/12/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-01-10 | XRN 5319 | Assessing MPID Reassignment for All Party Types | Implemented | 2021-02-01 | E.ON | uklink@xoserve.com | Ad-hoc | 08/12/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-05-16 | XRN 5321 | PAC Ring-Fenced DSC Change Budget 21/22 | Implemented | 2021-02-25 | CDSP | uklink@xoserve.com | Ad-hoc | 29/03/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-05-10 | XRN 5327 | Xoserve Change Fund 2021/22 | Withdrawn | 2021-02-25 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2021-03-23 | XRN 5329 | Amendments to V16 of the Service Description Table | Implemented | 2021-02-25 | CDSP | uklink@xoserve.com | Ad-hoc | 17/03/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-08-15 | XRN 5343 | CMS Rebuild | Withdrawn | 2021-03-29 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-05-01 | XRN 5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at transfer of ownership | Withdrawn | 2021-03-29 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No
2022-05-16 | XRN 5341 | UNC745 - Mandatory Setting of Auction Bid Parameters | Implemented | 2021-04-29 | National Grid | uklink@xoserve.com | Ad-hoc | 19/09/2021 | Service Area 14 (Current Apr 21): Gemini Services | Yes | Yes | No | No | No
2021-07-21 | XRN 5352 | Development of the REC Performance Assurance reporting structure | Implemented | 2021-04-29 | RECCo | uklink@xoserve.com | Ad-hoc | 18/07/2022 | TBC: To be confirmed | Yes | No | Yes | No | No
2021-05-20 | XRN 5362 | Amendments to Service Description Table V17 | Implemented | 2021-04-29 | CDSP | uklink@xoserve.com | Ad-hoc | 19/05/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-10-04 | XRN 5365 | Request impact assessment on aligning Major Releases to the REC Release Schedule (Thursday release and 3 Major Releases per year) | Implemented | 2021-05-19 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2023 | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2023-02-13 | XRN 5368 | Gemini Change Programme - Sustain | Implemented | 2021-05-27 | National Gas Transmission | uklink@xoserve.com | Ad-hoc | 29/05/2022 | Service Area 14 (Current Apr 21): Gemini Services | Yes | Yes | No | Yes | No
2022-02-16 | XRN 5377 | Addition of ‘Class’ field to supply point data reports | Implemented | 2021-06-18 | Wales and West Utilities | uklink@xoserve.com | Ad-hoc | 19/11/2021 | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | No | Yes | No | No | No
2023-06-14 | XRN 5379 | Class 1 Read Service Procurement Exercise - MOD 0710 | Implemented | 2021-06-24 | Xoserve | uklink@xoserve.com | Ad-hoc | 25/03/2023 | TBC: To be confirmed | Yes | Yes | Yes | No | No
2021-07-22 | XRN 5380 | Introduction of a Micro Business identifier in Central Systems (Mod 0733) | Withdrawn | 2021-06-24 | Xoserve | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | No | No | No
2021-07-23 | XRN 5381 | Amendments to Service Description Table V18 | Implemented | 2021-06-25 | Xoserve | uklink@xoserve.com | Minor | 21/07/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2021-07-19 | XRN 5382 | FWACV: PRCMS validation/processing - analysis v1.0 | Withdrawn | 2021-06-28 | National Grid | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | Yes | No
2021-07-19 | XRN 5383 | LDZ Stock Change and Embedded LDZ Unique Sites - new service | Withdrawn | 2021-06-28 | National Grid | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | Yes | No
2023-03-28 | XRN 4900 | Biomethane Sites with Reduced Propane Injection | Implemented | 2021-07-29 | Scotland and Southern Gas Networks (SGN) | uklink@xoserve.com | Major | 25/02/2023 | N/A: Not applicable | Yes | Yes | No | No | No
2022-08-15 | XRN 5393 | Implementation of NTS Capacity related UNC Modifications 0752S, 0759S & 0755S | Implemented | 2021-07-29 | National Gas Transmission | uklink@xoserve.com | Ad-hoc | 24/04/2022 | TBC: To be confirmed | Yes | Yes | No | Yes | No
2023-10-04 | XRN 5402 | Request impact assessment on proposed REC Change Management Impact Assessment | Implemented | 2021-07-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2023 | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2021-12-09 | XRN 5371 | Minor Release Drop 10 | Implemented | 2021-08-18 | Xoserve | uklink@xoserve.com | Minor | 04/09/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | No | No | No
2021-10-25 | XRN 5419 | Amendments the DSC Service Description Table to support REC | Implemented | 2021-09-03 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/10/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2021-12-09 | XRN 5431 | Temporary community access to pre-COVID AQ values for Shippers | Implemented | 2021-10-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 02/11/2021 | Service Area 22: Specific Services | Yes | No | No | No | No
2022-02-16 | XRN 5443 | Urgent Modification 0788 - Minimising the market impacts of ‘Supplier Undertaking’ operation | Implemented | 2021-10-27 | National Grid NTS | uklink@xoserve.com | Ad-hoc | 01/11/2021 | TBC: To be confirmed | Yes | No | No | Yes | No
2022-04-21 | XRN 5450 | Demand tool to support Urgent Modification 0788 - Minimising the market impacts of ‘Supplier Undertaking’ operation | Implemented | 2021-11-25 | National Grid | uklink@xoserve.com | Ad-hoc | 18/02/2022 | TBC: To be confirmed | Yes | No | No | Yes | No
2021-12-20 | XRN 5452 | Amendments to v20 of the Service Description Table | Implemented | 2021-11-25 | Xoserve | uklink@xoserve.com | Ad-hoc | 15/12/2021 | N/A: Not applicable | Yes | Yes | No | Yes | No
2024-06-13 | XRN 5453 | GSOS 2, 3 & 13 Payment Automation | Withdrawn | 2021-11-26 | SGN | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | No | No
2022-06-10 | XRN 5458 | Urgent Modification 0791 - Contingency Gas Procurement Arrangements when a Supplier acts under a Deed of Undertaking | Implemented | 2021-12-08 | National Grid NTS | uklink@xoserve.com | Ad-hoc | 31/03/2022 | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | Yes | No | No | Yes | No
2024-04-30 | XRN 5454 | Supplier of Last Resort (SoLR) Reporting Suite CP | Withdrawn | 2021-12-30 | EDF | uklink@xoserve.com | Unallocated | TBC |  | Yes | No | No | No | No
2022-11-14 | XRN 5463 | Technical Debt reduction- Prime and Sub process enhancement | Implemented | 2022-01-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/09/2022 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | No | No | No | No
2022-11-14 | XRN 5464 | Technical Debt reduction – Enhancement to asset exchange process for Class 1 and 2 Meter Points | Implemented | 2022-01-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/09/2022 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | No | No | No | No
2022-03-01 | XRN 5470 | New Service Line for SDT v21 | Implemented | 2022-01-31 | CDSP | uklink@xoserve.com | Ad-hoc | 16/02/2022 | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2023-10-04 | XRN 5471 | Services to release data to UNC parties | On Hold | 2022-01-31 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No
2023-04-03 | XRN 5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation processes | Withdrawn | 2022-01-31 | CDSP | uklink@xoserve.com | Ad-hoc | 25/03/2023 | Service Area 5 (Current Apr 21): Demand Estimation obligations | Yes | Yes | Yes | Yes | No
2023-10-04 | XRN 5473 | Meter Asset Detail Proactive Monitoring Service | Current | 2022-01-31 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | No | No | No
2023-11-06 | XRN 5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Implemented | 2022-02-23 | Scottish Power | uklink@xoserve.com | Major | 04/11/2023 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | No | No | No | No
2022-03-16 | XRN 5484 | New Service Line for SDT v22 | Implemented | 2022-02-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/03/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-08-15 | XRN 5485 | Resource to support the Retail Energy Code (REC) | Implemented | 2022-03-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 15/08/2022 | N/A: Not applicable | Yes | No | Yes | No | No
2022-04-25 | XRN 5495 | Changes to Third Party and Additional Service Policy | Implemented | 2022-04-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/04/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-04-25 | XRN 5496 | Change to Service Description Table | Implemented | 2022-04-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/04/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-10-18 | XRN 5469 | Increasing the Frequency of FSG Payments | Implemented | 2022-04-13 | Cadent Gas | uklink@xoserve.com | Ad-hoc | 30/09/2022 | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | No | No
2022-07-21 | XRN 5505 | Amendments to v24 of the Service Description Table | Implemented | 2022-04-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 15/06/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2022-09-13 | XRN 5515 | Hydeploy close down | Implemented | 2022-05-25 | Northern Gas | uklink@xoserve.com | Ad-hoc | 18/07/2022 | TBC: To be confirmed | Yes | Yes | No | No | No
2022-11-11 | XRN 5517 | Hydrogen checker website | Withdrawn | 2022-05-25 | Cadent | uklink@xoserve.com | Ad-hoc | TBC | TBC: To be confirmed | No | Yes | No | No | No
2023-03-01 | XRN 5455 | Implementation of Entry Capacity Assignments Process (UNC0779/779A) | Withdrawn | 2022-05-26 | National Grid | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | No | Yes | No
2023-09-22 | XRN 5316 | Rejecting a replacement read with a pre-Line in the Sand (LIS) read date | Implemented | 2022-05-31 | Xoserve | uklink@xoserve.com | Ad-hoc | 22/09/2023 | N/A: Not applicable | Yes | No | No | No | No
2023-01-05 | XRN 5529 | UNC Derogation process – MOD 0800 | Implemented | 2022-06-29 | Northern Gas Networks | uklink@xoserve.com | Ad-hoc | 01/10/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-02-01 | XRN 5531 | Hydrogen Village Trial | Withdrawn | 2022-06-29 | SGN | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2022-07-15 | XRN 5532 | Hydrogen Town Trial | Withdrawn | 2022-06-29 | Wales & West Utilities | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2023-03-28 | XRN 5535A | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Implemented | 2022-07-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 06/03/2023 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | Yes | Yes | No
2023-01-18 | XRN 5541 | Amendment to the UIG Additional National Data Reporting | Implemented | 2022-07-19 | Scottish Power | uklink@xoserve.com | Ad-hoc | 23/12/2022 | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | No | No | No | No
2023-01-16 | XRN 5545 | Hydrogen Trial Visualisation Dashboard | Withdrawn | 2022-07-29 | Northern Gas | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2023-06-19 | XRN 5533 | February 23 Major Release | Implemented | 2022-08-01 | Xoserve | uklink@xoserve.com | Major | 24/02/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | Yes
2025-02-20 | XRN 5546 | Resolution of Address Interactions between DCC and CDSP | Current | 2022-08-02 | Xoserve | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No
2023-09-22 | XRN 5547 | Updating the Comprehensive Invoice Master List and INV template | Implemented | 2022-08-03 | Eon | uklink@xoserve.com | Minor | 22/09/2023 | N/A: Not applicable | Yes | Yes | No | No | No
2022-11-11 | XRN 5554 | Allocation of Unidentified Gas Expert (AUGE) Management – Independent Review | Withdrawn | 2022-08-30 | Xoserve | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | No | No | No
2023-03-10 | XRN 5555 | Amend existing Large Load Site Reporting | Implemented | 2022-08-30 | Scotia Gas Networks | uklink@xoserve.com | Ad-hoc | 10/02/2023 | TBC: To be confirmed | No | Yes | No | No | No
2024-04-29 | XRN 5556 | CMS Rebuild parent XRN | Implemented | 2022-08-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 27/04/2024 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-01-18 | XRN 5556A | New CMS Version 1 | Implemented | 2022-08-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 26/10/2022 | N/A: Not applicable | Yes | Yes | Yes | No | No
2022-11-16 | XRN 5561 | Reform of Gas Demand Side Response (DSR) Arrangements (Modification 0822) | Implemented | 2022-09-07 | National Grid | uklink@xoserve.com | Ad-hoc | 17/10/2022 | TBC: To be confirmed | Yes | Yes | No | Yes | No
2023-09-15 | XRN 5562 | June 23 Major Release | Implemented | 2022-09-12 | Xoserve | uklink@xoserve.com | Major | 24/06/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-01-18 | XRN 5556B | New CMS - Version 1.1 | Implemented | 2022-09-13 | Xoserve | uklink@xoserve.com | Ad-hoc | 12/12/2022 | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2025-08-18 | XRN 5564 | Gemini Sustain Plus Programme | Implemented | 2022-09-28 | National Gas Transmission | uklink@xoserve.com | Ad-hoc | 23/03/2025 | Service Area 14 (Current Apr 21): Gemini Services | Yes | Yes | Yes | Yes | No
2023-11-10 | XRN 5565 | Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824) | Implemented | 2022-09-28 | NGN | uklink@xoserve.com | Ad-hoc | 31/03/2023 |  | Yes | No | No | No | No
2022-09-30 | XRN 5566 | Amendments to v25 of the Service Description Table | Implemented | 2022-09-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 19/10/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-05-14 | XRN 5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Implemented | 2022-10-03 | Xoserve | uklink@xoserve.com | Ad-hoc | 09/12/2023 |  | Yes | Yes | Yes | No | No
2025-07-07 | XRN 5569 | Contact Data Provision for IGT Customers | Current | 2022-10-03 | Brookfield Utilities UK | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | No | No | Yes | No | No
2025-05-08 | XRN 5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) - Urgent | Implemented, Current | 2022-10-10 | Xoserve | uklink@xoserve.com | Major | 27/06/2024 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | Yes | Yes | No
2023-11-06 | XRN 5556C | CMS Rebuild Version 1.2 | Implemented | 2022-10-12 | Xoserve | uklink@xoserve.com | Ad-hoc | 06/11/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-07-14 | XRN 5575 | March 23 Adhoc Release | Implemented | 2022-10-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2023 | N/A: Not applicable | Yes | Yes | Yes | No | No
2022-11-22 | XRN 5581 | Amendments to v26 of the Service Description Table | Implemented | 2022-10-31 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/11/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-02-13 | XRN 5584 | Procurement of Climate Change Methodology for Demand Estimation Purposes | Withdrawn | 2022-11-04 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 5 (Current Apr 21): Demand Estimation obligations | Yes | Yes | No | No | No
2025-03-17 | XRN 5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Implemented | 2022-11-04 | Xoserve | uklink@xoserve.com | Major | 12/11/2024 |  | No | Yes | No | No | No
2023-01-06 | XRN 5597 | Amendments to v27 of the Service Description Table | Implemented | 2022-11-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 14/12/2022 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-07-06 | XRN 5579 | Regulatory Change FY22 | Implemented | 2022-11-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 19/03/2023 | Service Area 14 (Current Apr 21): Gemini Services | No | No | No | Yes | No
2023-04-12 | XRN 5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Implemented | 2022-11-28 | Xoserve | uklink@xoserve.com | Major | 25/02/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2023-04-26 | XRN 5602 | Releasing of unused capacity under a specific set of circumstances (Modification 0818) | Withdrawn | 2022-12-22 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | No | No | No
2024-02-26 | XRN 5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | Implemented | 2022-12-22 | SEFE | uklink@xoserve.com | Major | 24/02/2024 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | Yes | No | No | No
2024-02-26 | XRN 5605 | Amendments to the must read process (IGT159V) | Implemented | 2022-12-22 | Xoserve | uklink@xoserve.com | Major | 24/02/2024 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | No | Yes | No | No
2023-07-20 | XRN 5606 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813) | Withdrawn | 2022-12-23 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | Yes | No | No | Yes | No
2024-02-26 | XRN 5607 | Update to the AQ correction processes (Modification 0816S) | Implemented | 2022-12-23 | EON | uklink@xoserve.com | Major | 24/02/2024 | Service Area 2 (Current Apr 21): Monthly AQ Processes | Yes | Yes | No | No | No
2023-03-14 | XRN 5556D | CMS Rebuild Version 1.3 | Implemented | 2022-12-23 | Xoserve | uklink@xoserve.com | Ad-hoc | 24/04/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-04-19 | XRN 5610 | New Service Lines to support the FWACV Service | Implemented | 2023-01-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2025-05-12 | XRN 5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | Implemented | 2023-01-30 | BUUK | uklink@xoserve.com | Major | 28/02/2025 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | No | Yes | No | No
2024-09-16 | XRN 5616 | CSEP Annual Quantity Capacity Management | On Hold | 2023-01-30 | WWU | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | Yes | No | Yes
2023-03-31 | XRN 5579A | Long-Term Flow Swap Automation | Implemented | 2023-02-09 | National Gas Transmission | uklink@xoserve.com | Ad-hoc | 19/03/2023 | Service Area 14 (Current Apr 21): Gemini Services | No | Yes | No | Yes | No
2025-03-17 | XRN 5615 | Establishing/Amending a Gas Vacant Site Process (Modification 0819) | Implemented | 2023-02-23 | Centrica | uklink@xoserve.com | Major | 08/11/2024 | Service Area 2 (Current Apr 21): Monthly AQ Processes | Yes | Yes | Yes | No | No
2023-04-03 | XRN 5622 | Amendments to v28 of the Service Description Table | Implemented | 2023-02-27 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/04/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-03-24 | XRN 5635 | H100 (UNC Mod799) Consequential Gemini Change | Implemented | 2023-03-23 | National Gas Transmission | uklink@xoserve.com | Ad-hoc | TBC | N/A: Not applicable | No | Yes | No | Yes | No
2023-08-18 | XRN 5556E | CMS Rebuild Version 1.4 | Implemented | 2023-03-31 | Xoserve | uklink@xoserve.com | Ad-hoc | 14/08/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-11-06 | XRN 5556F | CMS Rebuild Version 1.5 | Implemented | 2023-03-31 | Xoserve | uklink@xoserve.com | Ad-hoc | 06/11/2023 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-03-21 | XRN 5629 | November 23 Major Release | Implemented | 2023-04-27 | Xoserve | uklink@xoserve.com | Major | 04/11/2023 | N/A: Not applicable | Yes | Yes | No | No | No
2023-11-10 | XRN 5641 | Addition of Market Sector Code to specific Supply Point Data Reports | Implemented | 2023-04-27 | NGN | uklink@xoserve.com | Ad-hoc | 06/10/2023 | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | No | Yes | No | No | No
2023-06-14 | XRN 5634 | Gemini Regulatory Change FY23/24 | Implemented | 2023-05-23 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/03/2024 | N/A: Not applicable | No | No | No | Yes | No
2023-09-22 | XRN 5651 | Updates to Class 3 and 4 Inner Tolerance Ranges used in Meter Read validation process | Implemented | 2023-05-25 | Centrica | uklink@xoserve.com | Minor | 22/09/2023 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | No | No | No | No
2023-06-14 | XRN 5653 | Amendments to v29 of the Service Description Table | Implemented | 2023-05-25 | Xoserve | uklink@xoserve.com | Ad-hoc | 14/06/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2023-11-10 | XRN 5652 | Enabling Direct Contractual Arrangements with Consumers for Demand Side Response (Modification 0844) | Implemented | 2023-05-25 | National Gas | uklink@xoserve.com | Ad-hoc | 04/08/2023 | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | Yes | Yes | No | Yes | No
2024-02-07 | XRN 5658 | Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method (Mod 0831) and Allocation of LDZ UIG to Shippers (Class 2, 3 and 4) Based on a Straight Throughput Method (Mod 0831A) | Withdrawn | 2023-06-15 | SSE (Mod0831) / Brook Green (Mod 0831A) | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | No | No | No
2023-12-11 | XRN 5556G | CMS Rebuild Version 1.6 | Implemented | 2023-06-21 | Xoserve | uklink@xoserve.com | Ad-hoc | 25/11/2023 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-04-29 | XRN 5556H | CMS Rebuild – Delivery of GSR and MUS | Implemented | 2023-06-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 27/04/2024 | N/A: Not applicable | Yes | Yes | Yes | No | No
2023-11-10 | XRN 5647 | Minor Release Drop 11 | Implemented | 2023-07-21 | Xoserve | uklink@xoserve.com | Minor | 22/09/2023 | N/A: Not applicable | Yes | Yes | No | No | No
2024-02-01 | XRN 5665 | Default New Connection AQ values - Annual Review | Implemented | 2023-07-21 | SGN | uklink@xoserve.com | Ad-hoc | 31/01/2024 | N/A: Not applicable | No | Yes | No | No | No
2023-10-16 | XRN 5668 | Production Data Back up | Implemented | 2023-08-02 | RTS - REC Technical Services | uklink@xoserve.com | Ad-hoc | 19/08/2023 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | Yes | Yes | No | No
2024-11-13 | XRN 5675 | Implementation of 0836S - Resolution of Missing Messages after CSS implementation and integration with R0067 and 0855 - Settlement Adjustments for SMPs impacted by the Central Switching System P1 incident | Implemented | 2023-08-04 | SEFE | uklink@xoserve.com | Major | 27/06/2024 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | Yes | Yes | No | No
2023-10-30 | XRN 5689 | Updates to the CDSP Service Description Table (v30)New Service Lines to support XRN 5562 Enabling Direct Contractual Arrangements with Consumers for Demand Side Response | Implemented | 2023-09-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 19/10/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-05-14 | XRN 5682 | February 24 Major Release | Implemented | 2023-09-29 | Xoserve | uklink@xoserve.com | Major | 24/02/2024 | N/A: Not applicable | Yes | Yes | No | No | No
2024-02-08 | XRN 5690 | Creating a loadable Billing Calendar File for DSC Customers | Implemented | 2023-09-29 | E.ON | uklink@xoserve.com | Ad-hoc | 18/01/2024 | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | Yes | No
2024-07-17 | XRN 5695 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0854) | Implemented | 2023-10-03 | National Grid NTS | uklink@xoserve.com | Ad-hoc | 22/05/2024 | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | No | Yes | No | Yes | No
2023-11-28 | XRN 5700 | Updates to the CDSP Service Description Table (v31) | Implemented | 2023-10-26 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/11/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2024-02-01 | XRN 5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | On Hold | 2023-10-26 | OVO Gas Limited | uklink@xoserve.com | Unallocated | TBC | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | Yes | No | No
2026-03-16 | XRN 5702 | Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) | Current | 2023-10-26 | NGT | uklink@xoserve.com | Major | 26/06/2026 | Service Area 13 (Current Apr 21): Managing Change | Yes | Yes | Yes | Yes | No
2023-12-20 | XRN 5714 | Updates to CDSP Service Description Table V32 | Implemented | 2023-11-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/12/2023 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2025-03-17 | XRN 5720 | Gateway delivery for RPC backing data (IGT173) | Implemented | 2023-12-28 | EON | uklink@xoserve.com | Major | 08/11/2024 | TBC: To be confirmed | Yes | No | Yes | No | No
2024-07-17 | XRN 5719 | Provision of consolidated Specific Services Invoice and Supporting Information | Withdrawn | 2023-12-28 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 22: Specific Services | Yes | Yes | Yes | Yes | No
2024-02-26 | XRN 5556I | CMS Rebuild – Delivery of XRN5604 and XRN5605 | Implemented | 2023-12-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 24/02/2024 | N/A: Not applicable | Yes | No | Yes | No | No
2024-03-04 | XRN 5556J | CMS Rebuild Version - Delivery of Must Reads | Implemented | 2023-12-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 04/03/2024 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-04-29 | XRN 5556K | CMS Rebuild Version - Delivery of DMQ and Generic Workflows | Implemented | 2023-12-28 | Xoserve | uklink@xoserve.com | Ad-hoc | 27/04/2024 | N/A: Not applicable | Yes | Yes | Yes | No | Yes
2024-07-17 | XRN 5727 | Minor Release 12 | Implemented | 2024-02-22 | Xoserve | uklink@xoserve.com | Minor | 10/05/2024 | N/A: Not applicable | No | No | No | No | Yes
2024-11-15 | XRN 5711 | June 24 Major Release | Implemented | 2024-02-22 | Xoserve | uklink@xoserve.com | Major | 27/06/2024 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-03-21 | XRN 5746 | Updates to the CDSP Service Description Table (v33) | Implemented | 2024-02-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 21/03/2024 | N/A: Not applicable | Yes | Yes | Yes | Yes | Yes
2026-01-21 | XRN 5732 | Inclusion of IGT MPRNs into specified existing DSC Processes | Implemented | 2024-02-29 | BUUK | uklink@xoserve.com | Minor | 05/12/2025 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2024-09-16 | XRN 5748 | DDP Release 1 BP2024/2025 | Implemented | 2024-03-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/05/2024 | N/A: Not applicable | No | Yes | No | No | No
2024-09-16 | XRN 5771 | Amendments to Demand Side Response (DSR) Arrangements (Modification 0866) | Implemented | 2024-03-26 | Xoserve | uklink@xoserve.com | Ad-hoc | 10/06/2024 | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | Yes | Yes | Yes | Yes | No
2025-10-13 | XRN 5781 | Gemini Regulatory Change FY24/25 | Implemented | 2024-04-24 | National Gas | uklink@xoserve.com | Ad-hoc | 23/03/2025 | Service Area 14 (Current Apr 21): Gemini Services | No | No | No | Yes | No
2025-10-13 | XRN 5784 | Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | Implemented | 2024-04-24 | SEFE Energy | uklink@xoserve.com | Major | 27/06/2025 | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | Yes | No
2024-09-16 | XRN 5785 | DDP Release 2 2024/2025 | Implemented | 2024-04-24 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/07/2024 | N/A: Not applicable | Yes | Yes | No | No | No
2025-03-17 | XRN 5778 | November 24 Major Release | Implemented | 2024-05-29 | Xoserve | uklink@xoserve.com | Major | 08/11/2024 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-10-11 | XRN 5793 | Platform to support Performance Assurance Committee (PAC) | Implemented | 2024-05-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 05/07/2024 | Service Area 15 (Current Apr 21): Value Added Services | Yes | Yes | Yes | No | No
2024-06-16 | XRN 5795 | Business Plan Information Rules Independent Assurance | Implemented | 2024-06-03 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/01/2025 |  | Yes | Yes | Yes | Yes | No
2024-10-28 | XRN 5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | On Hold | 2024-06-26 | National Gas Transmission | uklink@xoserve.com | Unallocated | TBC | Service Area 8 (Current Apr 21): Energy Balancing (Credit Risk Management) | Yes | Yes | Yes | Yes | No
2025-12-04 | XRN 5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Implemented | 2024-06-28 | Cadent Gas | uklink@xoserve.com | Ad-hoc | 01/10/2025 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | No | Yes | Yes | No | No
2024-10-28 | XRN 5809 | DDP Release 3 2024/2025 | Implemented | 2024-07-01 | Xoserve | uklink@xoserve.com | Ad-hoc | 30/09/2024 | N/A: Not applicable | No | No | Yes | No | Yes
2024-07-12 | XRN 5810 | Theft of Gas (ToG) DN Calculation Tool | Current | 2024-07-12 | Cadent | uklink@xoserve.com | Unallocated | TBC |  | No | Yes | No | No | No
2024-09-16 | XRN 5815 | New Performance Framework Administrator (PAFA) Service Contract Procurement 2024 | Implemented | 2024-07-26 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/07/2024 | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | Yes | Yes | Yes | No
2024-08-29 | XRN 5824 | Updates to the CDSP Service Description Table (v34) | Current | 2024-08-29 | Xoserve | uklink@xoserve.com | Ad-hoc | 20/03/2024 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2025-01-20 | XRN 5825 | Minor Release Drop 13 | Implemented | 2024-09-26 | Xoserve | uklink@xoserve.com | Minor | 06/12/2024 |  | No | No | No | No | Yes
2025-05-13 | XRN 5818 | February 25 Major Release | Implemented | 2024-09-30 | Xoserve | uklink@xoserve.com | Major | 28/02/2025 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-12-11 | XRN 5835 | Extending the scope of existing ring fenced DSC Change Budget funds to cater for Performance Assurance Committee discretional activities | Implemented | 2024-09-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 05/07/2024 | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | Yes | Yes | Yes | No
2024-12-16 | XRN 5832 | DDP Release 4 2024/2025 | Implemented | 2024-09-30 | xoserve | uklink@xoserve.com | Ad-hoc | 30/11/2024 | N/A: Not applicable | Yes | Yes | Yes | No | No
2024-10-30 | XRN 5848 | Updates to the CDSP Service Description Table (v35) | Current | 2024-10-30 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | Yes | Yes | Yes | No
2025-10-13 | XRN 5846 | New allowable value (M - Thermal Mass) for Meter Type Code (H100) | Implemented | 2024-10-30 | Xoserve | uklink@xoserve.com | Major | 27/06/2025 |  | Yes | Yes | Yes | Yes | No
2025-11-13 | XRN 5851 | Modification 0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | Implemented | 2024-10-31 | SEFE Energy | uklink@xoserve.com | Ad-hoc | 01/10/2025 | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2025-02-24 | XRN 5858 | DDP Release 5 2024/2025 | Implemented | 2024-11-27 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/01/2025 | N/A: Not applicable | Yes | Yes | Yes | No | No
2025-01-30 | XRN 5781.1 | UNC Modification 0872s Single-sided Nominations for clearing houses of gas exchanges | Implemented | 2024-11-28 | National Gas | uklink@xoserve.com | Ad-hoc | 23/03/2025 | N/A: Not applicable | Yes | No | No | Yes | No
2025-06-11 | XRN 5937.1 | Change to EIC Code(s) within Gemini | Implemented | 2024-12-11 | National Gas | uklink@xoserve.com | Ad-hoc | 09/09/2025 | Service Area 14 (Current Apr 21): Gemini Services | Yes | No | No | Yes | Yes
2026-03-19 | XRN 5872 | Updates to the Annual Quantity (AQ) amendment process (Modification 0876S) | Implemented | 2024-12-12 | SEFE Energy | uklink@xoserve.com | Major | 27/02/2026 | Service Area 2 (Current Apr 21): Monthly AQ Processes | Yes | Yes | Yes | No | No
2025-01-20 | XRN 5881 | Updates to the CDSP Service Description Table (v36) | Implemented | 2024-12-23 | Xoserve | uklink@xoserve.com | Ad-hoc | 16/01/2025 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2025-06-16 | XRN 5885 | Cease Provision of SC9 Files to Distribution Networks (DNs) | Implemented | 2025-01-13 | Cadent | uklink@xoserve.com | Ad-hoc | 29/04/2025 | Service Area 17: Distribution Network wholly funded activities | No | Yes | No | No | No
2025-10-13 | XRN 5868 | June 25 Major Release | Implemented | 2025-01-27 | Xoserve | uklink@xoserve.com | Major | 27/06/2025 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2025-07-11 | XRN 5888 | Minor Release Drop 14 (Parent Change) | Implemented | 2025-01-29 | Xoserve | uklink@xoserve.com | Minor | 30/05/2025 |  | No | Yes | Yes | No | No
2025-01-30 | XRN 5887 | DDP Release 6 2024/2025 | Implemented | 2025-01-30 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/03/2025 | TBC: To be confirmed | Yes | Yes | Yes | No | No
2025-03-17 | XRN 5892 | Ring-fenced DSC Budget to support Allocation of Unidentified Gas Value-Add Activities | Current | 2025-02-27 | SEFE Energy | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Current Apr 21): Manage Shipper Transfers | Yes | No | No | No | No
2025-03-19 | XRN 5894 | Updates to the CDSP Service Description Table (v37) | Implemented | 2025-03-04 | Xoserve | uklink@xoserve.com | Ad-hoc | 19/03/2025 | TBC: To be confirmed | Yes | Yes | Yes | Yes | No
2026-03-19 | XRN 5906 | Extending the PC4 Read Submission Window (Mod0884) | Implemented | 2025-03-10 | Xoserve | uklink@xoserve.com | Major | 27/02/2026 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | Yes | Yes | No | No
2025-06-16 | XRN 5937.2 | Removal of Non-Obligated Entry Capacity from Capacity Neutrality (Modification 0897S) | Implemented | 2025-03-24 | Xoserve | uklink@xoserve.com | Ad-hoc | 01/07/2025 |  | Yes | No | No | Yes | No
2025-06-05 | XRN 5913 | DDP Release 1 2025/2026 | Implemented | 2025-03-31 | Xoserve | uklink@xoserve.com | Ad-hoc | 31/05/2025 | N/A: Not applicable | Yes | Yes | Yes | Yes | No
2026-03-19 | XRN 5914 | Amend the Code Cut-Off Date to a Rolling Period (Mod0886) | Implemented | 2025-04-15 | SSE | uklink@xoserve.com | Major | 27/02/2026 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | Yes | Yes | No | No
2026-03-19 | XRN 5922 | Shorten the current code cut-off date (or Line in the Sand) from a 3 to 4-year period to a 2 to 3-year period (Modification 0896) | Implemented | 2025-04-23 | SEFE | uklink@xoserve.com | Major | 27/02/2026 | Service Area 4 (Current Apr 21): Meter Read/Asset processing | Yes | Yes | Yes | No | Yes
2025-07-07 | XRN 5923 | Updates to the suite of Performance Assurance Report Register (PARR) | Current | 2025-04-24 | CDSP | uklink@xoserve.com | Ad-hoc | TBC | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | Yes | Yes | No | No
2025-12-10 | XRN 5924 | Physical Information Exchange (PIX) Ongoing Support Options | Current | 2025-04-24 | CDSP | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | Yes | No
2025-07-11 | XRN 5933 | Business Plan Information Rules Independent Assurance | Current | 2025-05-13 | CDSP | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | Yes | No
2025-07-07 | XRN 5941 | Performance Assurance Committee (PAC) – Audit Performance Assurance Technique (PAT) Request | Current | 2025-05-30 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | No | No
2025-12-23 | XRN 5940 | Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890) | Current | 2025-05-30 | Centrica | uklink@xoserve.com | Ad-hoc | TBC | Service Area 2 (Current Apr 21): Monthly AQ Processes | Yes | Yes | Yes | No | No
2025-07-07 | XRN 5937 | Gemini Regulatory Change FY25/26 | Current | 2025-05-30 | NGT | uklink@xoserve.com | Ad-hoc | TBC | Service Area 14 (Current Apr 21): Gemini Services | Yes | Yes | Yes | Yes | No
2025-07-07 | XRN 5942 | DDP Release 2 2025/2026 | Implemented | 2025-06-03 | CDSP | uklink@xoserve.com | Ad-hoc | 31/07/2025 | N/A: Not applicable | Yes | Yes | No | No | No
2025-07-11 | XRN 5949 | New Priority Consumer Category related to Community Heating | Current | 2025-06-27 | NGT | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | Yes | Yes | No
2025-07-11 | XRN 5950 | DSC Invoice Number generation review | Current | 2025-06-27 | CDSP | uklink@xoserve.com | Unallocated | TBC | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | Yes | No
2025-08-18 | XRN 5955 | Private networks duplicate MPRNs - options for long-term fix | Current | 2025-07-24 | Cadent | uklink@xoserve.com | Unallocated | TBC |  | No | Yes | No | No | No
2026-03-12 | XRN 5805 | Alternative Solution to address instances where VBA macros are present in DN Templates | Current | 2025-08-19 | WWU | uklink@xoserve.com | Unallocated | 26/06/2026 | N/A: Not applicable | No | Yes | No | No | No
2025-09-10 | XRN 5968 | Identifying improvements to Meter Point Location Address Data processes | Current | 2025-08-28 | Cadent | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | No | Yes | No | No | No
2025-09-10 | XRN 5969 | Amendment to DSC T&Cs to include a requirement to provide data incident nominated contact details | Current | 2025-08-28 | CDSP | uklink@xoserve.com | Unallocated | TBC | Service Area 13 (Current Apr 21): Managing Change | Yes | Yes | Yes | Yes | No
2025-09-10 | XRN 5967 | DDP Release 3 2025/2026 | Implemented | 2025-08-28 | CDSP | uklink@xoserve.com | Ad-hoc | 02/10/2025 | N/A: Not applicable | Yes | Yes | Yes | No | No
2026-01-21 | XRN 5971 | Minor Release Drop 15 ( Parent Change ) | Implemented | 2025-08-28 | CDSP | uklink@xoserve.com | Minor | 05/12/2025 | N/A: Not applicable | No | Yes | Yes | No | No
2025-09-10 | XRN 5972 | CDSP provisions to support new Supplier Deed of Undertaking (DoU) Licence Condition (9a) | Current | 2025-09-01 | Cadent | uklink@xoserve.com | Unallocated | TBC | Service Area 7 (Current Apr 21): Customer Joiners/Leavers (UK Gas Market) | No | Yes | Yes | No | No
2025-11-13 | XRN 5987 | Modification 0915 – Debt Relief Scheme Payment (DRSP) | Current | 2025-09-22 | NGN | uklink@xoserve.com | Ad-hoc | TBC | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | Yes | No | No
2026-03-19 | XRN 5983 | February 26 Major Release (Parent Change) | Implemented | 2025-09-25 | Xoserve | uklink@xoserve.com | Major | 27/02/2026 |  | Yes | Yes | Yes | No | No
2025-10-08 | XRN 5985 | DDP Release 4 2025/2026 | Current | 2025-09-25 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | N/A: Not applicable | Yes | Yes | No | No | No
2025-10-08 | XRN 5937.3 | Facilitating Bi-Directional Connections Between IGT pipelines and the NTS (Modification 0887) | Current | 2025-09-26 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 14 (Current Apr 21): Gemini Services | Yes | No | Yes | Yes | No
2025-11-13 | XRN 5993 | DDP Release 5 2025/2026 | Current | 2025-10-27 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No
2025-11-13 | XRN 5992 | Holistic Performance Matrix Identified Changes to Class 4 PARR | Current | 2025-10-27 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 9 (Current Apr 21): Customer Reporting (all forms) | Yes | Yes | Yes | No | No
2025-11-13 | XRN 5994 | Emergency Contact Validation Service | Current | 2025-10-29 | Cadent | uklink@xoserve.com | Ad-hoc | TBC | Service Area 17: Distribution Network wholly funded activities | Yes | Yes | No | No | No
2025-12-01 | XRN 6001 | Modification 0909 - Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | Current | 2025-12-01 | SEFE Energy | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | No | No | No
2025-12-01 | XRN 6000 | Modification 0908 – Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading by a Shipper | Current | 2025-12-01 | Wales and West Utilities | uklink@xoserve.com | Unallocated | TBC | Service Area 22: Specific Services | Yes | Yes | Yes | No | No
2026-02-12 | XRN 6039 | Provision of IGT SMP Data to DNs | Current | 2026-01-09 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | TBC: To be confirmed | No | Yes | Yes | No | No
2026-03-12 | XRN 6045 | June 2026 Major Release (Parent Change) | Current | 2026-01-15 | Xoserve | uklink@xoserve.com | Major | 26/06/2026 | Service Area 3 (Current Apr 21): Manage updates to customer portfolio | Yes | Yes | Yes | Yes | No
2026-02-12 | XRN 6041 | UNC Modification 0922 (IGT UNC Modification 180) – CDSP Obligations required for the introduction of the Gas Shipper Obligation | Current | 2026-01-19 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | Yes | No
2026-02-12 | XRN 6050 | DDP Release 6 2025/2026 | Current | 2026-01-29 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | No | No
2026-03-12 | XRN 6056 | Introduction of new Supply Meter Point status of ‘IS’ (Isolation) - Cleanse and remove obsolete ‘CL’ (Clamped) status | Current | 2026-02-25 | Xoserve | uklink@xoserve.com | Major | TBC |  | Yes | Yes | Yes | No | No
2026-03-25 | XRN 6065 | Minor Release 16 | Current | 2026-03-03 | Xoserve | uklink@xoserve.com | Minor | 12/06/2026 |  | Yes | Yes | No | No | No
2026-03-25 | XRN 6067 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894) | Current | 2026-03-17 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | Yes | No
2026-03-25 | XRN 6066 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894A) | Current | 2026-03-19 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC | Service Area 10 (Current Apr 21): Invoicing Customers | Yes | Yes | No | Yes | No
2026-03-26 | XRN 6070 | DDP Release 1 2027/2028 | Current | 2026-03-25 | Xoserve | uklink@xoserve.com | Ad-hoc | TBC |  | Yes | Yes | Yes | No | No